## Slide 1: 4. Smarter Work Zone Initiative - Project Coordination
Smarter Work Zones
Image: FHWA
Notes: Key Message: Title slide
Background Information: None
Interaction: None
Notes: This module will introduce participants to Smarter Work Zones initiative and discuss the “Guide to Project Coordination for Minimizing Work Zone Mobility Impacts.” This is Module 4 of 6 Modules.

## Slide 2: Module Objectives
Discuss the “Guide to Project Coordination for Minimizing Work Zone Mobility Impacts”
Define project coordination
Discuss the five steps for achieving project coordination
Source: FHWA
Notes: Key Message: Review module objectives
Background Information: The objectives of this module will be to walk through the “Guide to Project Coordination for Minimizing Work Zone Mobility Impacts” as part of the Smart Work Zone Initiatives.
Interaction: None
Notes: The guide can be found at http://www.ops.fhwa.dot.gov/publications/fhwahop16013/index.htm#toc

## Slide 3: Project Coordination Defined
Coordination within a single project and/or among multiple projects within a corridor, network, or region, and possibly across agency jurisdictions
Compare impacts to uncoordinated projects
  This comparison becomes a measure of effectiveness
Notes: Key Message: FHWA has selected two methods of improving work zone safety as part of the EDC3 initiative.
Background Information: PC involves various strategies and actions, with the intent to improve a transportation agency’s ability to better manage and interact with multiple construction projects along a corridor or within a region toward the objective of improved safety and mobility:
Improved safety through a reduction in crashes and reduced crash severity and Enhanced mobility in the form of travel time reliability and reduced delay. The measure of effectiveness for PC efforts is determined through a comparison with the estimated impacts that would have occurred if the projects had not been coordinated in some fashion. PC can occur along a corridor, across a network of local streets, or within a broad region.
Interaction: N/A
Notes: We will now discuss the project coordination initiative goals and strategies.

## Slide 4: Benefits of Project Coordination (1 of 4)
Greater ability to reduce and manage traffic disruptions from road work
  Provides alternate routes for drivers
  Sets a maximum time delay for the work zone area
Earlier identification of project impacts
  Minimizes project delay, allowing schedule to stay on track
Notes: Key Message: introduce benefits of project coordination
Background Information: Project coordination has been discussed with the development of Transportation Management Plans (TMP). Delay from a project level has been stressed, but the intent is to also look at projects and the effort to manage traffic disruptions on a corridor and a network level—not just among the transportation agency’s projects, but including other work within the network, such as utility projects.
Early identification of project impacts will help reduce or manage work zone-related traffic disruptors. Project coordination should include roadwork by state and local DOT offices, such as maintenance and construction, as well as work performed by utilities, developers, and any other efforts that will impact road users. Better coordination of projects can be "win-win" for public agencies, road users, and citizens by reducing the need for additional work zones.
To ensure good implementation, we need to understand that the transportation system is a network. Work at one location will impact other locations. Also, since the highway infrastructure is aging and congestion is increasing, states, counties and cities are facing more management. Remember, road users may not be able to understand why our road is being cut by a utility company. This may be done six months after the road project. They know they are stuck in traffic, and most likely they will blame the traffic agency for not coordinating both projects. Therefore, project coordination is important for road activities. Project coordination needs to occur at the planning stage because it allows agencies to identify early on the right group during the development of the project. Coordination also helps agencies to identify, analyze and mitigate individual and accumulated work prior to construction.
Interaction: none
Notes: Go through each point and expand as applicable. This slide and the next slide go together.

## Slide 5: Benefits of Project Coordination (2 of 4)
Fewer number of work zones
  Adjacent construction projects on a corridor can be scheduled for closure at the same time
    (one larger closure instead of two smaller ones)
  Construction on alternate routes is not performed during already scheduled construction on the main route
Notes: Key Message: introduce benefits of project coordination
Background Information: Project coordination has been discussed with the development of Transportation Management Plans (TMP). Delay from a project level has been stressed, but the intent is to also look at projects and the effort to manage traffic disruptions on a corridor and a network level—not just among the transportation agency’s projects, but including other work within the network, such as utility projects.
Early identification of project impacts will help reduce or manage work zone-related traffic disruptors. Project coordination should include roadwork by state and local DOT offices, such as maintenance and construction, as well as work performed by utilities, developers, and any other efforts that will impact road users. Better coordination of projects can be "win-win" for public agencies, road users, and citizens by reducing the need for additional work zones.
To ensure good implementation, we need to understand that the transportation system is a network. Work at one location will impact other locations. Also, since the highway infrastructure is aging and congestion is increasing, states, counties and cities are facing more management. Remember, road users may not be able to understand why our road is being cut by a utility company. This may be done six months after the road project. They know they are stuck in traffic, and most likely they will blame the traffic agency for not coordinating both projects. Therefore, project coordination is important for road activities. Project coordination needs to occur at the planning stage because it allows agencies to identify early on the right group during the development of the project. Coordination also helps agencies to identify, analyze and mitigate individual and accumulated work prior to construction.
Interaction: none
Notes: Go through each point and expand as applicable. This slide and the next slide go together.

## Slide 6: Benefits of Project Coordination (3 of 4)
Dynamic adjustments to project schedule
Improved communications within and across agencies
Reduced numbers of road cuts
Notes: Key Message: continue to discuss benefits of project coordination
Background Information: A lack of project coordination can mean many road projects close to together, street cuts on recently paved roads resulting in reduced quality, increased agency and user costs, and significant impacts to road users resulting in many unsatisfied customers. San Francisco was able to reduce street cuts by 27 percent by coordinating right-of-way projects. Corridor-level transportation management plans ensure that at least one major north-south corridor and one major east-west corridor are left unrestricted for freight and passenger travel at all times.
Interaction: none
Notes: A continuation of previous slide.

## Slide 7: Benefits of Project Coordination (3 of 4)
Better quality road surfaces
Cost savings
Increased customer satisfaction
Provide locations in which drivers can select an alternate route to exit work zone road
Notes: Key Message: continue to discuss benefits of project coordination
Background Information: A lack of project coordination can mean many road projects close to together, street cuts on recently paved roads resulting in reduced quality, increased agency and user costs, and significant impacts to road users resulting in many unsatisfied customers. San Francisco was able to reduce street cuts by 27 percent by coordinating right-of-way projects. Corridor-level transportation management plans ensure that at least one major north-south corridor and one major east-west corridor are left unrestricted for freight and passenger travel at all times.
Interaction: none
Notes: A continuation of previous slide.

## Slide 8: Project Coordination Challenges
Establishing and maintaining accurate information about project schedules, plans, day-to-day activities
  Keeping all agency stakeholders engaged will produce accurate information and promote information sharing on an ongoing basis
Effects on individual project schedules
Notes: Key Message: Discuss potential challenges of project coordination.
Background Information: (broken into 2 slides) Basically go over the information on the slide.
Establishing and maintaining accurate information about project schedules, plans, day-to-day activities
  Keeping all agency stakeholders engaged will both produce accurate information and promote information sharing on an ongoing basis
Effects on individual project schedules
Quantifying the benefits of coordination or the negative effects if a lack of coordination
Institutional constraints regarding the availability of funds and when those funds must be spent
Agency missions and charters with respect to routes of responsibility, stakeholders, and users
Interaction: Do you see any challenges within your agency? What can we do to overcome these challenges?
Notes: See page 8 of the guide for more discussion

## Slide 9: Project Coordination Challenges (cont.)
Quantifying the benefits of coordination or the negative effects of a lack of coordination
Institutional constraints regarding the availability of funds and when those funds must be spent
Agency missions and charters with respect to
  Routes of responsibility,
  Stakeholders and
  Users
Notes: Key Message: Discuss potential challenges of project coordination.
Background Information: (broken into 2 slides) Basically go over the information on the slide.
Establishing and maintaining accurate information about project schedules, plans, day-to-day activities
  Keeping all agency stakeholders engaged will both produce accurate information and promote information sharing on an ongoing basis
Effects on individual project schedules
Quantifying the benefits of coordination or the negative effects if a lack of coordination
Institutional constraints regarding the availability of funds and when those funds must be spent
Agency missions and charters with respect to routes of responsibility, stakeholders, and users
Interaction: Do you see any challenges within your agency? What can we do to overcome these challenges?
Notes: See page 8 of the guide for more discussion

## Slide 10: Dimensions of Project Coordination
Project Coordination
Who is Involved?
What Can or Should Occur?
What Does It Accomplish?
Source: FHWA
Notes: Key Message: Introduce graphic and discuss.
Background Information: A guide has been developed to help provide a framework for coordination. The guide is not a silver bullet, but provides an approach that agencies can use as a start for addressing where you can mitigate some of the problems. It will also help you come up with a process tailored to your needs that achieves the intended coordination benefits. The guide breaks down:
What is project coordination?
Who is involved? There are opportunities for Project Coordination (PC) to occur within a single agency, such as when multiple projects are being performed along a single route or across multiple routes all under the agency’s control. In the same manner, PC can also occur between two or more agencies. Requiring and granting access permits for entities to work within another agency’s right-of-way are examples of this type of coordination, as are multi-agency regional committees and teams specifically established to share project information and work to resolve potential work activity conflicts across a corridor or regional network.
What's being coordinated? what is being accomplished, is perhaps the most important to understand conceptually. Given the overall objective of minimizing the work zone safety and mobility impacts of multiple projects, PC actions themselves should be capable of being described in terms of how they can or will accomplish this impact mitigation objective.
When or how can coordination be achieved? Project Coordination (PC) can occur during project planning and design. Coordination during these phases of project development typically focus on scheduling and sequencing of projects in a more impact-minimizing way.
It’s sort of a who, when, and what.
Interaction: none
Notes: none

## Slide 11: Project Coordination Opportunities Who Should be Involved?
Project Coordination
Single Agency
Multiple Agencies
Single Route
Multiple Routes
Source: FHWA
Notes: Key Message: discuss who should be involved
Background Information: There are opportunities for Project Coordination (PC) to occur within a single agency, such as when multiple projects are being performed along a single route or across multiple routes all under the agency’s control. In the same manner, PC can also occur between two or more agencies. Requiring and granting access permits for entities to work within another agency’s right-of-way are examples of this type of coordination, as are multi-agency regional committees and teams specifically established to share project information and work to resolve potential work activity conflicts across a corridor or regional network.
Interaction: how does this work in your agency?
Notes: none

## Slide 12: Project Coordination- Matrix When does coordination occur?
Planning and Design
Project Delivery
Two or More Agencies
Single Agency
Source: Guide to Project Coordination for Minimizing Work Zone Mobility Impacts”
Notes: Key Message: Set the framework for the next several slides.
Background Information: Imagine the process as a matrix. The first thing to do is consider whether there is one or more agencies involved and the phase during which coordination should be occurring. In most cases that is where a lot of agencies start. They can be better coordinated amongst their own sets of projects and activities. You can then expand that out across multiple agencies and even to some private sector developers.
These activities can be initiated and performed early in the project development process in the planning and design area.
Interaction: None
Notes: Have students turn to page 6 of the guide.

## Slide 13: Possible Activities: Single Agency, Planning and Design Phases
Develop a database of agency planned projects over the next 3-5 years
Develop a map showing project locations in the region, possibly color-coded to illustrate current, near-term, and long-term schedules
Notes: Key Message: Walk through example of possible activities during project coordination within an agency.
Background Information: The first thing to do is consider whether there is one or more agencies involved and the phase during which coordination should be occurring. In most cases that is where a lot of agencies start. They can be better coordinated amongst their own sets of projects and activities. You can then expand that out across multiple agencies and even to some private sector developers.
Various ways to do this include:
Developing a database of agency planned projects over the next 3-5 years.
Developing a map showing project locations in the region, possibly color-coded to illustrate current, near-term, and long term schedules.
Determining the sequence of the projects that will minimize total delays and disruptions to the traveling public in the corridor or region (i.e., WISE tool).
These activities can be initiated and performed early in the project development process in the planning and design area.
Interaction: None
Notes: None

## Slide 14: Possible Activities: Single Agency, Planning and Design Phases (cont.)
Determine the sequence of the projects that will minimize total delays and disruptions to the traveling public in the corridor or region
  i.e., Work Zone Impact and Strategy Estimator (WISE) tool
    Will discuss later
Source: FHWA
Notes: Key Message: Walk through example of possible activities during project coordination within an agency.
Background Information: The first thing to do is consider whether there is one or more agencies involved and the phase during which coordination should be occurring. In most cases that is where a lot of agencies start. They can be better coordinated amongst their own sets of projects and activities. You can then expand that out across multiple agencies and even to some private sector developers.
Various ways to do this include:
Developing a database of agency planned projects over the next 3-5 years.
Developing a map showing project locations in the region, possibly color-coded to illustrate current, near-term, and long term schedules.
Determining the sequence of the projects that will minimize total delays and disruptions to the traveling public in the corridor or region (i.e., WISE tool).
These activities can be initiated and performed early in the project development process in the planning and design area.
Interaction: None
Notes: None

## Slide 15: Possible Activities: Single Agency, Project Delivery
Implement a Transportation Management Plan (TMP) encompassing multiple agency projects
Conduct regular coordination meetings with staff of simultaneous corridor or regional projects to:
  Eliminate conflicts,
  Combine compatible lane closures into a single closure
  Etc.
Notes: Key Message: Walk through example of possible activities during project coordination within an agency.
Background Information: (broken into 2 slides) We’ll call the next phase the construction operations phase. This involves taking a broader look at coordination―considering what’s going on throughout a corridor, not just on a single project. It also involves taking a broader look at other agencies and the impact their activities may have on traffic.
Developing and implementing a regional transportation management plan that encompasses the various agency projects that are ongoing in a corridor or region
Conducting regular coordination meetings between staff of various projects going on simultaneously in a corridor or region to identify and eliminate potential lane closure conflicts, combine compatible lane closures into a single coordinated lane closure where possible, etc.
Establishing business processes to coordinate agency maintenance activities with nearby construction project efforts when possible
Linking an agency’s lane closure permitting approvals with agency construction and maintenance coordination efforts
Interaction: None
Notes: One can also read the list.

## Slide 16: Possible Activities: Single Agency, Project Delivery (cont.)
Establish processes to coordinate agency maintenance activities with nearby construction project efforts
Link an agency’s lane closure permitting approvals with agency construction and maintenance coordination efforts
Notes: Key Message: Walk through example of possible activities during project coordination within an agency.
Background Information: (broken into 2 slides) We’ll call the next phase the construction operations phase. This involves taking a broader look at coordination―considering what’s going on throughout a corridor, not just on a single project. It also involves taking a broader look at other agencies and the impact their activities may have on traffic.
Developing and implementing a regional transportation management plan that encompasses the various agency projects that are ongoing in a corridor or region
Conducting regular coordination meetings between staff of various projects going on simultaneously in a corridor or region to identify and eliminate potential lane closure conflicts, combine compatible lane closures into a single coordinated lane closure where possible, etc.
Establishing business processes to coordinate agency maintenance activities with nearby construction project efforts when possible
Linking an agency’s lane closure permitting approvals with agency construction and maintenance coordination efforts
Interaction: None
Notes: One can also read the list.

## Slide 17: Possible Activities: Multiple Agencies, Planning and Design Phase
Expand project database and mapping tools to include other agencies in the region, utility companies, and private-sector development projects
Establish a web-based approach to sharing and providing appropriate access to the database and map
Notes: Key Message: Walk through example of possible activities during project coordination within an agency.
Background Information: Next, look at coordination for planning and design across multiple agencies. These are two examples of approaches that have been successfully implemented by some agencies across the country. Coordination can be something as simple as having a database with the agency's planned products within the 3-5 project years, and then mapping that out visually. This can make it easier to see where the potential conflicts are and then being able to sequence these projects.
Interaction: None
Notes: None

## Slide 18: Possible Activities: Multiple Agencies, Project Delivery
Implement a TMP that considers and addresses
  Projects being performed by all agencies and
  Other stakeholders in the region
Conduct regular coordination meetings between stakeholders to:
  Resolve lane closure conflicts and
  Other coordination issues as they arise
Notes: Key Message: Walk through examples of possible activities during project coordination within an agency.
Background Information: We should be able to develop and implement regional transportation management plans as opposed to having multiple individual transportation management plans along a corridor. You may not be able to justify doing major improvements on a single project, but when you look across the multiple projects going on, you might be able to coordinate with the agencies involved, and the work would be beneficial for all projects. To get started, hold meetings within the agency to coordinate simultaneous projects and look for opportunities like combining lane closures for two projects so there is one single lane closure on one day rather than two closures on different days.
Some agencies are looking at ways to establish formal steps and procedures for maintenance efforts. They are checking on construction projects in the same region to see if there are opportunities to coordinate and piggyback on top of the each other. Again, this eliminates multiple enclosures on different days or nights when work can be done with one single closure. Some agencies have lane closure permitting processes for external agencies and are trying coordinate their work with construction and maintenance efforts. Those are examples of ways to coordinate project activities to achieve improved safety and mobility.
You can easily see how you can expand these kinds of activities to a multiple agency or multiple entity environment. This includes project activities and mapping efforts. It applies not just to one agency, but to all of the agencies within a region. It can also include private sector developers. Agencies can make the database and mapping tool available to everyone in the region; this way, all the entities involved can see what everyone else has going on. This can happen during planning and design. From an operations standpoint, projects should not be just focused on one agency’s plans. Sometimes city, State, and maybe even utility work can be incorporated. Hosting regional coordination meetings to make sure everyone is on the same page can support this kind of coordination. These meetings can also provide a way to resolve any conflicts that might be arising on a day-to-day basis. These are the types of beneficial outcomes that can be achieved through coordination.
Interaction: None
Notes: We’ve looked at coordination in a matrix format. We will now look at a proposed five step process.

## Slide 19: What Does Coordination Accomplish?
Mitigating work zone impacts
  Sequencing the order of multiple projects
  Combining projects
  Scheduling projects
Project 1
Project 2
Project 3
Notes: Key Message: review benefits of PC
Background Information: The third dimension of Project Coordination (PC), what is being accomplished, is perhaps the most important to understand conceptually. Given the overall objective of minimizing the work zone safety and mobility impacts of multiple projects, you should be able to describe PC activities in terms of how they can or will accomplish this impact mitigation objective. Some of the ways that work zone impacts can be mitigated through coordination include:
Sequencing the order in which multiple projects are completed to build additional capacity into the travel corridor or network incrementally, so that each completed project provides the greatest amount of benefit to travelers during each successive project.
Combining projects or project tasks along a travel route segment so that the impact to traffic occurs for the collective tasks at one time instead of individual impacts for each activity.
Scheduling projects or project tasks to avoid having significant capacity restrictions on a single travel route or on multiple roadways that serve as convenient alternatives for travelers when they encounter work zone congestion and delays.
Interaction: None
Notes: none

## Slide 20: Five Steps for Achieving Project Coordination
Source: FHWA
Notes: Key Message: talk about five steps
Background Information: These are the five simple steps to achieving project coordination. The first step is really establishing what an entity or agency wants to accomplish with respect to coordinating projects. Evidence strongly suggests getting the upper management support of the agency or agencies involved is critical. It takes support and the ability to have someone's back when trying to do something as complicated as coordinating a project among multiple entities. In some cases, you can establish who works together between the multiple agencies involved. Then at this point the first thing is to get the people involved and bringing the coordinating committee together. Those are really your decision-makers. Those who can act on behalf of the group they are representing. And give them the charge of figuring out how to coordinate activities. The next step is what the coordinating committee works on and figures out specifically what they want to do and how they will accomplish it.
The following slides give a few examples for each of these.
Interaction: none
Notes: none

## Slide 21: Step 1: Establish the Vision
Get support from upper management
Develop Memorandums of Understanding (MOUs) among the entities with which you plan to coordinate
MOU
Notes: Key Message: This is a proposed five step process for coordination.
Background Information: (broken into 2 slides) Establishing a successful PC process first requires a clear vision of what the process is to achieve. This vision needs to begin with―or at least be supported by―agency upper management, since coordination efforts can sometimes require changes to existing contract language, reallocation of staff resources, and/or forging a cooperative relationship with other agencies and stakeholders in the region. Towards this end, it may be necessary to develop formal memorandums of understanding (MOUs) between stakeholders to obtain buy-in for the PC efforts. A coordination committee made up of decision-makers with authority to speak on behalf of their agency or entity is also needed. These individuals may come from several areas of the organization such as construction, maintenance, design, operations, traffic engineering, contract administration, and public information. Technical subcommittees may also be needed to identify and resolve specific technical issues that arise.
Interaction: none
Notes: none

## Slide 22: Develop a coordination committee. Members may include staff from:
Construction
Maintenance
Design,
Operations
Traffic
Contracting
County, State, City
Utilities
Emergency Responders
Notes: Key Message: This is a proposed five step process for coordination.
Background Information: (broken into 2 slides) Establishing a successful PC process first requires a clear vision of what the process is to achieve. This vision needs to begin with―or at least be supported by―agency upper management, since coordination efforts can sometimes require changes to existing contract language, reallocation of staff resources, and/or forging a cooperative relationship with other agencies and stakeholders in the region. Towards this end, it may be necessary to develop formal memorandums of understanding (MOUs) between stakeholders to obtain buy-in for the PC efforts. A coordination committee made up of decision-makers with authority to speak on behalf of their agency or entity is also needed. These individuals may come from several areas of the organization such as construction, maintenance, design, operations, traffic engineering, contract administration, and public information. Technical subcommittees may also be needed to identify and resolve specific technical issues that arise.
Interaction: none
Notes: none

## Slide 23: Step 2: Develop Details of How Coordination will Occur
Identify data needed to allow coordination to occur
Obtain tools committee needs to plan, monitor, manage coordination
  Database software
  Mapping
  Traffic impact analyses and scheduling
Establish decision-making process for how project coordination vision will be achieved amongst stakeholders
Notes: Key Message: discuss how coordination will occur
Background Information: The next step is to develop the specific details of how PC will occur within this arrangement. The data or information that will be needed to accomplish PC must be identified. Roadway and traffic conditions that will exist and which may need to be considered within the projects are usually needed, such as travel times, traffic volumes and capacities, vehicle and load sizes that can be accommodated, etc. Tools that allow the committee to plan, monitor, and manage the projects will also be needed. These may include analytical tools to estimate expected traffic impacts, databases to log key information about each project or activity along a corridor or within a region, visualization tools such as geographic information system (GIS) programs that can map the projects in the database and make that map available to the various stakeholders in the region, and regular committee meetings. Also in this step, the committee will need to define the guidance that will be used to accomplish the PC vision. This could include strategies such as agreeing to a corridor or statewide TMP approach rather than a series of isolated project-level TMPs, establishing priorities to resolve conflicts between projects during construction, or methods of planning and scheduling projects for a particular construction season.
Interaction: none
Notes: none

## Slide 24: Step 3: Educate and Inform Personnel and Stakeholders
Provide reasons for and benefits to be gained by coordination
Provide information on the decision-making process to be followed
Important for Agency Staff
  Know what is expected
  Know what to do
  Re-educate for updates and staff turnover
Notes: Key Message: discuss benefits to stakeholders
Background Information: (broken into 2 slides) Step three is taking the processes and everything that has been developed by the committee and making sure that each agency is on board and understands not only what is going to be done but, more importantly, why it's going to be done. Field personnel are judged predominantly or historically by getting the project done on time and under budget. People need to understand why you may be asking them to change the way they have been doing things; for example, changing the schedule or the sequence of the work. If you make those kinds of changes during the design phase, it's important to make sure field staff are well aware of why and how this will occur. Educating your own agency staff and other stakeholders in the region is very important.
Interaction: none
Notes: none

## Slide 25: Step 3: Educate and Inform Personnel and Stakeholders (cont.)
Stakeholders Participation
  Understand what to expect
  Share their perspective
Train
  Importance of and how to use tools
  Importance of and how to develop Project Level TMPs
Notes: Key Message: discuss benefits to stakeholders
Background Information: (broken into 2 slides) Step three is taking the processes and everything that has been developed by the committee and making sure that each agency is on board and understands not only what is going to be done but, more importantly, why it's going to be done. Field personnel are judged predominantly or historically by getting the project done on time and under budget. People need to understand why you may be asking them to change the way they have been doing things; for example, changing the schedule or the sequence of the work. If you make those kinds of changes during the design phase, it's important to make sure field staff are well aware of why and how this will occur. Educating your own agency staff and other stakeholders in the region is very important.
Interaction: none
Notes: none

## Slide 26: Step 4: Implement the Process
Conduct regular coordination meetings to track progress of projects
Regularly update the project database and tracking, monitoring, and analysis tools
Notes: Key Message: step 4: implementation
Background Information: The fourth step is actual implementation of the PC process. Regular coordination meetings should be held at the corridor/regional level of all the affected stakeholders. For state DOTs, this may involve multiple divisions and offices (i.e., planning, construction, maintenance, operations, permitting, public information). A focus of the meetings should be on tracking the various projects in the corridor or region as they move through the project development process. There can be a long-range assessment, where expected general traffic impacts and anticipated schedules are compared; a medium-range assessment activity, where the traffic impacts, expected project staging and sequencing, and anticipated letting dates are discussed and examined in greater detail; and a short-term or current project assessment where upcoming day-to-day scheduling of lane closures and other bottlenecks created are examined and coordinated to minimize travel impacts as much as possible. Updates to the tracking databases and tools should occur regularly in this step as well.
Interaction: none
Notes: none

## Slide 27: Step 5: Refine the Process
Updates and changes to the process may be frequent initially
Changes decrease over time as process becomes institutionalized
Notes: Key Message: step 5: process improvement
Background Information: The final step is then to refine the PC process as the stakeholders become more comfortable with the efforts, learn what is working well, and identify what needs to be revised. Early on, this refinement may be fairly extensive and involve changes to committee and subcommittee structure and staff involvement. Over time, the refinements may become less frequent and less substantial.
Interaction: none
Notes: none

## Slide 28: What is the Work Zone Implementation Strategies Estimator (WISE)?
  Decision support software system
  Developed under the Strategic Highway Research Program (SHRP) 2 R11
Source: SHRP 2
Notes: Key Message: Introduce the WISE tool
Background Information: (broken into 2 slides) The Work Zone Impacts and Strategies Estimator (WISE) software tool was developed through the SHRP2 program to evaluate the impacts of various highway projects and compare alternatives. It is open-source software that is available from FHWA. Software support includes a user’s guide. The WISE software analyzes the impacts of multiple, concurrent work zones across a network or complex corridor on road users. This tool is intended to help agencies optimize the sequencing of renewal projects and analyze the cost-effectiveness of strategies for the minimization, management, and mitigation of road user costs from safety or operational perspectives. The WISE tool can be used at a planning level as well as the operational level. WISE software provides an integrated framework for users to evaluate planning decisions and operational strategies, eliminating the need to use separate software for model-building. With the integrated framework, planning-level decisions can be based on network- and corridor-level impacts. Users can import traffic networks from existing travel demand models. In addition, the tool has an optimization routine that will recommend efficient staging strategies. WISE can evaluate the impact of changes in route choice behavior as well as impacts from intelligent transportation systems.
Interaction: has anyone ever used this tool?
Notes: SHRP 2 R11 [Completed] Strategic Highway Research Program
Strategic Approaches at the Corridor and Network Level to Minimize Disruption from the Renewal Process. WISE, WORK ZONE IMPACT AND STRATEGY ESTIMATOR SOFTWARE (R11) A Final Report documenting the development of the work zone impact and strategy estimator, A User's Guide, and Software to analyze the impacts on road users of multiple, concurrent work zones across a network or complex corridor. This tool will help agencies assess the optimal sequencing of renewal projects, and help determine the cost-effectiveness of strategies to minimize, manage, and mitigate road user costs from safety or operational perspectives. The WISE software is fully developed and is being tested in Iowa and Arizona using historical data to validate its parameters. In addition, pilot tests in New York and Florida will use the software to analyze projects currently in the planning phase.

## Slide 29: WISE:
Carries coordination through to project planning/design decisions
Includes:
  Planning and
  Operation Modules
May be applied:
  Over relatively large networks, or
  Upon complex corridors
W
I
S
E
Notes: Key Message: introduce the WISE tool
Background Information: (broken into 2 slides) The Work Zone Impacts and Strategies Estimator (WISE) software tool was developed through the SHRP2 program to evaluate the impacts of various highway projects and compare alternatives. It is open-source software that is available from FHWA. Software support includes a user’s guide. The WISE software analyzes the impacts of multiple, concurrent work zones across a network or complex corridor on road users. This tool is intended to help agencies optimize the sequencing of renewal projects and analyze the cost-effectiveness of strategies for the minimization, management, and mitigation of road user costs from safety or operational perspectives. The WISE tool can be used at a planning level as well as the operational level. WISE software provides an integrated framework for users to evaluate planning decisions and operational strategies, eliminating the need to use separate software for model-building. With the integrated framework, planning-level decisions can be based on network- and corridor-level impacts. Users can import traffic networks from existing travel demand models. In addition, the tool has an optimization routine that will recommend efficient staging strategies. WISE can evaluate the impact of changes in route choice behavior as well as impacts from intelligent transportation systems.
Interaction: has anyone ever used this tool?
Notes: None

## Slide 30: WISE (cont.):
Uses basic:
  Network geometry (link/node and number of lanes) and
  Traffic volume information
Helps evaluate work zone impacts and determine proactive strategies to reduce those impacts
    Provides effective project coordination up front in planning and programming
Notes: Key Message: introduce the WISE tool
Background Information: (broken into 2 slides) The Work Zone Impacts and Strategies Estimator (WISE) software tool was developed through the SHRP2 program to evaluate the impacts of various highway projects and compare alternatives. It is open-source software that is available from FHWA. Software support includes a user’s guide. The WISE software analyzes the impacts of multiple, concurrent work zones across a network or complex corridor on road users. This tool is intended to help agencies optimize the sequencing of renewal projects and analyze the cost-effectiveness of strategies for the minimization, management, and mitigation of road user costs from safety or operational perspectives. The WISE tool can be used at a planning level as well as the operational level. WISE software provides an integrated framework for users to evaluate planning decisions and operational strategies, eliminating the need to use separate software for model-building. With the integrated framework, planning-level decisions can be based on network- and corridor-level impacts. Users can import traffic networks from existing travel demand models. In addition, the tool has an optimization routine that will recommend efficient staging strategies. WISE can evaluate the impact of changes in route choice behavior as well as impacts from intelligent transportation systems.
Interaction: has anyone ever used this tool?
Notes: None

## Slide 31: Knowledge Check
Define project coordination
List the five steps for achieving project coordination
Notes: Key Message: Go over what was discussed in the module.
  Background Information:
Review steps for achieving project coordination:
  Establish the Vision
  Develop Details of How Coordination will Occur
  Educate and Inform Personnel and Stakeholders
  Implement the Process, and
  Refine the Process
Interaction: Engage participants to see if they are understanding materials.
Notes: none

## Slide 32: Questions
Notes: Key Message: Questions
Est. Presentation Time: Less than 1 minute(s)
Explanation of Cues/Builds: None
Suggested Comments: Self explanatory
Suggested Questions: Any questions before we move on?
Additional Information: None
Possible Problems: If no questions, you may ask a few yourself.