## Slide 1: 6. Exercises
Smarter Work Zones
6. Exercises
Source: FHWA
Notes: Key Message: Title slide
Background Information: None
Interaction: None
Notes: This module will provide will provide exercises to apply information that has been presented in the previous modules. This module is the sixth and final module. We will provide an opportunity to for you to provide a class evaluation.
Divide up into groups of 4 to 6.

## Slide 2: Exercises
Hands-on opportunity to apply the concepts learned
Five exercises
Break into teams
Notes: Key Message: Exercises
Background Information: None
Interaction: None
Notes:

## Slide 3: Exercise No. 1: Freeway Work
Interstate highway with two lanes in each direction
Distance from point A to point B is approximately 4+ miles with a work zone at the midpoint
The work can be done by closing one lane in each direction using nighttime lane closures on the mainline
Queuing would be a problem if lanes were closed during the daytime, (approx. 2.5- 3 miles in length).
Notes: Key Message: Talk about the background of exercise 1
Background Information: This is an interstate highway with two lanes in each direction. Distance from point A to point B is approximately 4+ miles with a work zone at the midpoint. The work can be done by closing one lane in each direction using nighttime lane closures on the mainline. Queuing would be a problem if lanes were closed during the daytime, (approx. 2.5- 3 miles in length).
Interaction: None
Notes: May have to go to the next slide to illustrate.

## Slide 4: Exercise No. 1
A
B
Source: FHWA
Notes: Key Message: Talk about the background of exercise 1
Background Information: This is an interstate highway with two lanes in each direction. Distance from point A to point B is approximately 4+ miles with a work zone at the midpoint. The work can be done by closing one lane in each direction using nighttime lane closures on the mainline. Queuing would be a problem if lanes were closed during the daytime, (approx. 2.5- 3 miles in length).
Interaction: None
Notes: None

## Slide 5: Exercise No. 1: Phase 1
Based on the five steps for achieving Project Coordination that were presented, develop the details of the steps for coordination in this project
Notes: Key Message: Describe the goal for exercise 1
Background Information: Break into small groups and have the groups discuss how they would accomplish this project based on the five project coordination steps. Determine what additional information you may need.
Interaction: Have group talk about this exercise for 15-30 minutes
Notes: None

## Slide 6: Exercise No. 1: Phase 1 Steps
1: Establish the Vision
2: Develop Details of How Coordination will Occur
3: Educate/Inform Personnel and Stakeholders
4: Implement the Process
5: Refine the Process
Notes: Key Message: Describe the goal for exercise 1
Background Information: 1: Establish the Vision
  Consider safety, mobility, work productivity and durability, and customer satisfaction
2: Develop Details of How Coordination will Occur
3: Educate/Inform Personnel and Stakeholders
4: Implement the Process
5: Refine the Process
Interaction: Have group talk about this exercise for 15-30 minutes
Notes: None

## Slide 7: Exercise No. 1, Phase 2:
What ITS would you consider if the project was five days?
What would you do different if the project lasted for four months?
Notes: Key Message: have participants answer the questions.
Background Information: First: The project will be completed in 5 days
Then: The project will be completed in 4 months: - First, consider what the project will be completed in five days. What must be done for each of the five steps?
- Next, consider the project lasts four months. What must be done for each of the five steps?
Interaction: small group discussion in which each group will report their findings to the class.
Notes: None

## Slide 8: Exercise No. 2: Modified Freeway Work
Same scenario as No. 1, except
  There is a stream crossing with bridges being replaced at the work zone using stage construction
  Only one lane will remain open in each direction
  The work will last for four months with the lane closures in place 24 hours a day
Notes: Key Message: introduce exercise 2
Background Information: Same scenario as above, except
  There is a stream crossing with bridges being replaced at the work zone using stage construction
  Only one lane will remain open in each direction
  The work will last for four months with the lane closures in place 24 hrs. a day
Interaction: small group discussion and large group report back
Notes: None

## Slide 9: Exercise No. 2
What coordination issues do you see with this project?
What ITS would you consider?
Notes: Key Message: introduce exercise 2
Background Information: read scenario and answer questions.
Interaction: small group discussion and large group report back
Notes: None

## Slide 10: Exercise No. 3 Scenario: Corridor Widening
Project consists of upgrading and widening an 89-mile Interstate corridor from 2 lanes to 3 lanes in each direction
The widening can be accomplished by adding a lane in each direction in the median
Approximately 30 miles will have a closed median with barrier wall
Notes: Key Message: introduce exercise 3
Background Information: read scenario and answer questions.
Interaction: small group discussion and large group report back
Notes: None

## Slide 11: Exercise No. 3 Scenario: Corridor Widening (cont.)
ADT: 45,000 - 90,000 vpd
  25 - 40% truck traffic
A major shipping corridor for through state travel with:
  119 mainline bridge structures
  45 overhead structures
Travel delays across the state should be kept to a maximum of 60 minutes
Notes: Key Message: introduce exercise 3
Background Information:
45,000 –90,000 ADT- with 25-40% truck traffic
A major shipping corridor for through state travel
Delays on travel time across the state should be kept to a max. of 60 min.
119 mainline bridge structures and 45 overhead structures within the project
Interaction: small group discussion and large group report back
Notes: None

## Slide 12: Exercise No. 3 Scenario: Corridor Widening (cont.)
There are two major cities, populations of approximately 150,000 separated by 55 miles on the route
Traverses 3 districts within the state
Queuing would be a problem if lanes were closed during the daytime
Only nighttime lane closures on the mainline would be allowed
Queuing would not be a problem
Notes: Key Message: introduce exercise 3
Background Information:
There are two major cities, populations of approx. 150,000 separated by 55 miles on the route
Traverses 3 districts within the state
Queuing would be a problem if lanes were closed during the daytime
Only nighttime lane closures on the mainline would be allowed
Queuing would not be a problem
Interaction: small group discussion and large group report back
Notes: None

## Slide 13: Exercise No. 3 Scenario: Corridor Widening (cont.)
Ramp closures also possible
Construction cost will exceed $2 billion
Construction could be completed in 3 years
Notes: Key Message: introduce exercise 3
Background Information:
Ramp closures also possible
Construction cost will exceed $2 billion
Construction could be completed in 3 years
Interaction: small group discussion and large group report back
Notes: None

## Slide 14: Exercise No. 3 Roadway Characteristics
Two 12-foot wide lanes
10-foot wide right shoulder
6-foot wide median shoulders
Median width of 44 feet in urban areas
Approximately 15 miles for each urban area
  Remaining has a median width of 66 feet
Notes: Key Message: introduce exercise 3
Background Information: read scenario and answer questions.
Interaction: small group discussion and large group report back
Notes: None

## Slide 15: Exercise No. 3 Roadway Characteristics
A
B
85 miles
55 miles
Notes: Key Message: introduce exercise 3
Background Information: read scenario and answer questions.
Interaction: small group discussion and large group report back
Notes: None

## Slide 16: Exercise No. 3
Based on the five steps for achieving Project Coordination that were presented, develop the details of the steps for coordination in this project
Notes: Key Message: introduce exercise 3
Background Information:
Based on the five Steps for Achieving Project Coordination that were presented, expand on these steps for this project.
Interaction: small group discussion and large group report back
Notes: None

## Slide 17: Exercise No. 4: Corridor Widening Modified
Completing the project in a three-year period
Multiple simultaneous contracts
Continuous project across the state would be the least overall disruptive to traffic
Notes: Key Message: As time permits, introduce exercise 4
Background Information:
It was decided that completing the project in a three year period, with multiple contracts simultaneously as a continuous project across the state would be the least overall disruptive to traffic. If this project were to be constructed as continuous project across the state, provide as complete a list as possible of challenges and coordination issues for the project.
Would any of these be a “deal breaker”?
Interaction: small group discussion and large group report back
Notes: None

## Slide 18: Exercise No. 4: Corridor Widening Modified (cont.)
If this project were to be constructed as continuous project across the state, provide:
  As complete a list as possible of the challenges and coordination issues
Would any of these be a “deal breaker”?
Notes: Key Message: As time permits, introduce exercise 4
Background Information:
It was decided that completing the project in a three year period, with multiple contracts simultaneously as a continuous project across the state would be the least overall disruptive to traffic. If this project were to be constructed as continuous project across the state, provide as complete a list as possible of challenges and coordination issues for the project.
Would any of these be a “deal breaker”?
Interaction: small group discussion and large group report back
Notes: None

## Slide 19: Exercise No. 4: Corridor Widening Modified - ITS usage
  Based on the ITS Implementation Guide, provide as much detail to the six steps as possible for this project.
    Step 1 – Assessment of Needs
    Step 2 – Concept of Operations
    Step 3 – Detailed System Planning
    Step 4 – Procurement
    Step 5 – System Deployment
    Step 6 – System Operation, Maintenance, and Evaluation
Notes: Key Message: As time permits, introduce exercise 4
Background Information:
  Based on the ITS Implementation Guide, expand and provide as much added detail to the six steps as possible for this project.
    Step 1 – Assessment of Needs
    Step 2 – Concept of Operations
    Step 3 – Detailed System Planning
    Step 4 – Procurement
    Step 5 – System Deployment
    Step 6 – System Operation, Maintenance, and Evaluation
Interaction: small group discussion and large group report back
Notes: None

## Slide 20: Exercise No. 4 Steps
1: Establish the Vision
2: Develop Details of How Coordination will Occur
3: Educate/Inform Personnel and Stakeholders
4: Implement the Process
5: Refine the Process
Notes: Key Message: Describe the goal for exercise 4
Background Information: 1: Establish the Vision
  Consider safety, mobility, work productivity and durability, and customer satisfaction
2: Develop Details of How Coordination will Occur
3: Educate/Inform Personnel and Stakeholders
4: Implement the Process
5: Refine the Process
Interaction: Have group talk about this exercise for 15-30 minutes
Notes: None

## Slide 21: Exercise No. 5: A Better Way?
Play the “devil’s advocate”:
  Convince the group there is a better way of doing this than doing it all at one time as a “big” project
Hint: You may have to look at staging, funding and sequencing of projects to convince everyone that there is a better way
Notes: Key Message: As time permits, introduce exercise 5
Background Information:
Play the “devils advocate”:
-Convince the group there is a better way of doing this than doing it all at one time as a “big” project
Hint: You may have to look at staging, funding and sequencing of projects to convince everyone there is a better way
Interaction: small group discussion and large group report back
Notes: None

## Slide 22: Exercise No. 5
What ITS applications would your agency use for this project and provide details on how your agency would want the system to work?
What do you want the system to do for you and the public?
Notes: Key Message: As time permits, introduce exercise 5
Background Information: read scenario and answer questions.
Interaction: small group discussion and large group report back
Notes: None

## Slide 23: Knowledge Check
What lessons did you learn from these exercises?
Would you make any changes to the process?
Notes: Key Message: Knowledge Check
Background Information: None
Interaction: What lessons did you learn from these exercises?
Would you make any changes to the process
Notes: Have suggested changes ready to initiate the discussion.

## Slide 24: Questions
Notes: Key Message: Questions
Est. Presentation Time: Less than 1 minute(s)
Explanation of Cues/Builds: None
Suggested Comments: Self explanatory
Suggested Questions: Any questions before we move on?
Additional Information: None
Possible Problems: If no questions, you may ask a few yourself.

## Slide 25: Closing
Smarter Work Zones
Image: FHWA
Notes: Key Message: Course closing
Est. Presentation Time: As needed
Explanation of Cues/Builds: None
Suggested Comments: We are done! Let’s close the course!
Suggested Questions: None
Additional Information: None.
Possible Problems: None

## Slide 26: Review of Course Objectives
Defined Smarter Work Zones
Provided a comprehensive overview of corridor and project work zone coordination
Discussed ITS to support effective work zone management and operations’
Provided guidance for using work zone ITS
Provided real-world examples of successful corridor-based Smarter Work Zone project coordination strategies using ITS
Notes: Key Message: Summarize the Modules
Background Information: This course provided the concept of Smarter Work Zones and the process of using ITS in effective Work Zone management and operations.
In Module 2 we provided background information regarding project coordination and ITS in work zones. We defined what is meant by smarter work zones. We looked at a local project that has used or could have used smarter work zone concepts.
Module 3 discussed project coordination and technology applications for work zones.
Module 4 provided detailed information regarding using smarter work zone ITS applications.
In Module 5 looked at various case studies which have used project coordination and ITS technologies and how these have reduced work zone impacts.
In Module 6 provided an exercise for participants to use various aspects of the course and to discuss ITS applications.
Interaction: None
Notes: None

## Slide 27: Check the “Parking Lot”
Pending questions or issues?
Notes: Key Message: Discuss the “parking lot”
Background Information: Instructor should go through the items/questions that were pending (“parked”) and make sure all questions are properly addressed.
Interaction: Ask to see if there are any questions
Notes: None

## Slide 28: Course Evaluation Form
Notes: Key Message: Completion of evaluation forms
Background Information: Please complete the evaluation form using a pen or a thin felt tip. There is no need to enter any personal information or information about the course (date, etc.). Simply X the box that best represents your views. Written comments (4.2) are always welcomed.
Interactivity: None
Notes: None

## Slide 29: Thank you!
Smarter Work Zones
Image: FHWA
Notes: Key Message: Course closing
Est. Presentation Time: As needed
Explanation of Cues/Builds: None
Suggested Comments: Thank you for your attention. We hope you found this a worthwhile experience!
Suggested Questions: None
Additional Information: None
Possible Problems: None