## Slide 1: 5. Project Coordination Examples
Smarter Work Zones
Image: FHWA
Notes: Key Message: Title slide
Background Information: None
Interaction: None
Notes: This module will provide examples of Smarter Work Zones that have used coordination of roadway construction projects to reduce work zone conflicts. As time permits, cover several examples and discuss various ways the host agency could follow the examples provided in this module. This module is the fifth module of seven modules.

## Slide 2: Module Objectives
Review project coordination examples
  Single project
Corridor Coordination (Focus of Examples)
  Multiple projects
  Network and regional consideration
  Agency jurisdictions
Notes: Key Message: review module objectives
Background: Coordination is required within a single project but is also needed among multiple projects within a corridor, network, or region, and possibly across agency jurisdictions to minimize work zone traffic impacts. Project coordination has been part of the Transportation Management Plan (TMP) for quite a while now, but many times did not consider the impacts of other projects within a region or along a corridor.
Interaction: none
Notes: none

## Slide 3: Project Coordination Examples
Example 1: WSDOT’s (Washington State DOT) Regional Project Coordination
Example 2: Michigan’s I-94 Corridor
Notes: Key Message: introduce two project coordination examples
Background Information: This module will be looking at two coordination examples. The first is WSDOT’s (Washington States DOT) Regional Project Coordination and the next is Michigan’s I-94 Corridor coordination effort.
Interaction: none
Notes: none

## Slide 4: WSDOT’s Regional Project Coordination
Puget Sound region of Washington encompasses:
  Seattle
  Tacoma
  Olympia, and
  Everett
Northwest and Olympic WSDOT regions
Many regional and local projects taking place
Notes: Key Message: The first coordination project we will look at is Washington (WS) States regional project coordination effort in the Seattle area, which was headed up by WS DOT’s regional office in Seattle.
Background Information:
Seattle, one of the largest metropolitan cities in the Northwest,
Located between the ocean and the cascade Mountains, has a north- south orientation.
Seattle has lots of congestion due to incredibly fast growth. One of the fastest growing cities, which led to the need to do better with traffic coordination.
Within the region there is the worlds largest ferry organization along with numerous other agencies and transit systems. Within these systems any one project can impact the operation of the other systems.
Interaction: None
Notes: None

## Slide 5: WSDOT’s Regional Project Coordination
Legislature approves funding and defines when it will be available for individual projects
Many factors are considered when prioritizing project
Notes: Key Message: provide overview of Washington DOT regional project coordination
Background Information: (Broken into 2 slides)
Problems needed to solve-
The legislature, as well as local governing bodies, tend to set funding for a project. Once that funding is in place they just want to make it happen. They are not thinking about construction traffic they are thinking about how to get this urban project done.
Need to move schedules around to make project teams aware that they should not do major closures during certain windows of time.
Difficult to prevent conflicting lane or road closures on parallel routes.
  Example: During a University of Washington graduation, there were multiple closures with bad timing, which caused extreme traffic problems with out of towners, resulting in very upset travelers.
Better coordination of planned construction is needed.
Interaction: None
Notes: None

## Slide 6: WSDOT’s Regional Project Coordination (cont.)
Traffic impacts may not be known or considered
Difficult to prevent conflicting lane or road closures on parallel routes
Need for better coordination of planned construction activities
Source: WSDOT
Notes: Key Message: provide overview of Washington DOT regional project coordination
Background Information: (Broken into 2 slides)
Problems needed to solve-
The legislature, as well as local governing bodies, tend to set funding for a project. Once that funding is in place they just want to make it happen. They are not thinking about construction traffic they are thinking about how to get this urban project done.
Need to move schedules around to make project teams aware that they should not do major closures during certain windows of time.
Difficult to prevent conflicting lane or road closures on parallel routes.
  Example: During a University of Washington graduation, there were multiple closures with bad timing, which caused extreme traffic problems with out of towners, resulting in very upset travelers.
Better coordination of planned construction is needed.
Interaction: None
Notes: The Washington State Department of Transportation (WSDOT) facilitates a collaborative, multi-agency construction traffic planning effort focused on communication and coordination amongst projects and agencies in the state. These coordination efforts include long-term, mid-term, and short-term information sharing, supported by tools developed by WSDOT. s a result of work zone coordination efforts, WSDOT and the local and regional agencies involved recognize benefits:
Reduced potential for conflicting lane/road closures.
Regularly scheduled meeting time for key personnel to discuss closures.
Enhanced public information resources, such as maps posted to the WSDOT Web site, that provide a big picture of the coordinated closures.
Enhanced public information dissemination, reaching a greater number of stakeholders across multiple affected locations.

## Slide 7: Support from Leadership
Agency leadership recognized the need to improve coordination for planned construction activities
The agency received support and funding to develop a software program internally that would coordinate projects
Notes: Key Message: must have support from key leadership
Background Information: (Broken into 2 slides)
Need support from leadership, executives in traffic and all the agencies, who take a big hit from the traveling public when “traffic nightmares” happen, especially from construction and/or maintenance projects.
Need the staff resources and executive leadership to provide a culture shift and project teams, from being focused on time and on budget and then dealing with traffic issues after the fact.
Interaction: None
Notes: None

## Slide 8: Support from Leadership (cont.)
Important because it includes a culture shift
Helps encourage internal and external stakeholders to participate
Notes: Key Message: must have support from key leadership
Background Information: (Broken into 2 slides)
Need support from leadership, executives in traffic and all the agencies, who take a big hit from the traveling public when “traffic nightmares” happen, especially from construction and/or maintenance projects.
Need the staff resources and executive leadership to provide a culture shift and project teams, from being focused on time and on budget and then dealing with traffic issues after the fact.
Interaction: None
Notes: None

## Slide 9: Project Goals
Include transit stakeholders
Establish relationship with transit agencies
Collaboration between regions and jurisdictions to provide a neutral assessment of projects with cross-regional or cross-jurisdictional impacts
– Internal marketing
Notes: Key Message: review project goals
Background Information:
There was duplication of effort with project teams calling each other over and over again. There is only so much engagement one project team can have with other organizations, there is a little bit of a challenge with thinking not about just the other project teams around you, but other agencies and the transit system. There was not a central place for information. Maintenance work needed to be scheduled also. There were missed
opportunities, where maintenance work could have shared a Work Zone instead of digging up the street twice.
Goal was to establish relationship with transit and other agencies within the region to look at projects to see how to coordinate these projects to lessen the impacts to traffic.
Interaction: None
Notes: None

## Slide 10: Construction Impact Analysis Tool
WSDOT-developed tool
Has two components:
  – Mapping tool
  – Database
Notes: Key Message: discuss tools they used
Background Information: (broken into 2 slides)
A Construction Impact Analysis (CIA) Tool was developed. It was developed with two components, a mapping tool and a database. Some people like a map while others like a chart. The use of the tool allows you to change the parameters of time and geography so that you can zoom in, zoom out, look at a week, a day, a month. You can easily manipulate the data to look at it in different ways, trying to identify those conflicts between projects in the mid to long term. It also helped to coordinate maintenance and utility activities and special events that create traffic congestion problems.
Interaction: None
Notes: Examples of a map created with the CIA tool for the Seattle region is shown.

## Slide 11: Construction Impact Analysis (CIA) Tool (cont.)
Identifies conflicts between projects
Helped to formalize and facilitate mid to long-term activities
Coordinates maintenance or utility activities or special events
Source: WSDOT
Notes: Key Message: discuss tools they used
Background Information: (broken into 2 slides)
A Construction Impact Analysis (CIA) Tool was developed. It was developed with two components, a mapping tool and a database. Some people like a map while others like a chart. The use of the tool allows you to change the parameters of time and geography so that you can zoom in, zoom out, look at a week, a day, a month. You can easily manipulate the data to look at it in different ways, trying to identify those conflicts between projects in the mid to long term. It also helped to coordinate maintenance and utility activities and special events that create traffic congestion problems.
Interaction: None
Notes: Examples of a map created with the CIA tool for the Seattle region is shown.

## Slide 12: CIA Inputs
Updated on a quarterly basis
Inputs are solicited via an email to project teams in 8 counties within Olympic and Northwest regions and local jurisdictions
Longer-term projects planned for up to 2 years into the future
Maintenance and utility projects
Source: WSDOT
Notes: Key Message: review CIA inputs on the slide.
Background Information: (broken into 2 slides)
On a quarterly basis, agency solicits emails from project teams and makes phone calls.
The folks who gather the data really work hard to figure out who is the right person on each project team to build a relationship with, to get the needed information. As to who does the information gathering, it varies; sometimes it is the engineering managers, sometimes it is a technician, it really varies as a team. Agency looks at longer term projects, but concentrates on the upcoming 24 months. This includes maintenance and utility projects.
Example Input:
– Location: I-5 from NE 117th St to SR 104 (Milepost 173.14 to 177.75)
– Pavement Repair–Date: 8/1/2014 –10/5/2014
– Impacts: Planned partial closure, nighttime, Sun-Thu;
Possible partial closure daytime Sun.
Interaction: None
Notes: None

## Slide 13: CIA Example Input
Location: I-5 from NE 117th St to SR 104
  Milepost 173.14 to 177.75
Pavement repair dates: 8/1/2014 - 10/5/2014
Impacts:
  Planned partial closure
  Nighttime
  Sunday-Thursday
Possible partial closure daytime on Sundays
Notes: Key Message: review CIA inputs on the slide.
Background Information: (broken into 2 slides)
On a quarterly basis, agency solicits emails from project teams and makes phone calls.
The folks who gather the data really work hard to figure out who is the right person on each project team to build a relationship with, to get the needed information. As to who does the information gathering, it varies; sometimes it is the engineering managers, sometimes it is a technician, it really varies as a team. Agency looks at longer term projects, but concentrates on the upcoming 24 months. This includes maintenance and utility projects.
Example Input:
– Location: I-5 from NE 117th St to SR 104 (Milepost 173.14 to 177.75)
– Pavement Repair–Date: 8/1/2014 –10/5/2014
– Impacts: Planned partial closure, nighttime, Sun-Thu;
Possible partial closure daytime Sun.
Interaction: None
Notes: None

## Slide 14: CIA Outputs
Distributed on a quarterly basis to approximately 400 stakeholders
Outputs include:
  Detailed maps of scheduled projects
  Gantt charts detailing the specifics of upcoming projects
Source: WSDOT
Notes: Key Message: talk about some of the results of the tool
Background Information: Construction Impacts Analysis (CIA) tool outputs include detailed maps and Gantt charts outlining the specifics of upcoming projects. These are distributed on a quarterly basis to approximately 400 stakeholders.
Interaction: None
Notes: None

## Slide 15: CIA Gantt Charts Output Example
Source: Construction Impact Analysis Tool
Notes: Key Message: talk about some of the results of the tool
Background Information: Construction Impacts Analysis (CIA) tool outputs include detailed maps and Gantt charts outlining the specifics of upcoming projects. These are distributed on a quarterly basis to approximately 400 stakeholders.
Interaction: None
Notes: May not be legible. Describe in generic terms. A Gantt chart is a type of bar chart that illustrates a project schedule. This chart lists the tasks to be performed on the vertical axis, and time intervals on the horizontal axis. The width of the horizontal bars in the graph shows the duration of each activity.

## Slide 16: CIA Outputs (cont.)
Hot spot and watch list areas are identified prior to the summer construction season
Based on:
  The number of projects in close proximity and
  Other types of impacts that could cause traffic impacts
Source: WSDOT
Notes: Key Message: talk about more results of the tool
Background Information: (Broken onto 2 slides)
A Hotspot is an area with a high number of projects in close proximity. This is where the agency will engage teams. The agency has had hotspots go away because, as teams coordinate to figure out schedules and work out contracts, congestion is mitigated and it is no longer a hotspot. You will notice in the example of Redmond, there were multiple projects affecting every major roadway. Redmond is home to Microsoft, for those of you who do not know. This is a huge suburban employment location. Numerous projects were planned, but nobody realized they were happening at the same time. They caught it early and got other cities, transit agencies, and utilities talking early to eliminate and coordinate the projects.
Interaction: None
Notes: None

## Slide 17: CIA Outputs Example
Redmond Hotspot
  Multiple projects affecting every major roadway into city
  Only 1 WSDOT project, but many local projects
  Minimize impacts to local community
Source: WSDOT
Notes: Key Message: talk about more results of the tool
Background Information: (Broken onto 2 slides)
A Hotspot is an area with a high number of projects in close proximity. This is where the agency will engage teams. The agency has had hotspots go away because, as teams coordinate to figure out schedules and work out contracts, congestion is mitigated and it is no longer a hotspot. You will notice in the example of Redmond, there were multiple projects affecting every major roadway. Redmond is home to Microsoft, for those of you who do not know. This is a huge suburban employment location. Numerous projects were planned, but nobody realized they were happening at the same time. They caught it early and got other cities, transit agencies, and utilities talking early to eliminate and coordinate the projects.
Interaction: None
Notes: None

## Slide 18: Coordination Meetings
Annually
Discuss upcoming projects for couple of construction seasons
Attendees include:
  WSDOT
  Local road
  Transit agencies
  Private freight representatives
  Port representatives
Notes: Key Message: provide background on coordination meetings
Background Information: (Broken onto 2 slides)
Agency promotes annual meetings as a part of the kickoff of construction season. Occurs in February or early March. Projects for the next couple of construction seasons are discussed. People in attendance include people from traffic offices and city folks who are doing transit planning. The event planners for Seattle Mariners, the Seahawks, the universities, those are engaged in the transportation for those websites. More frequent meetings are held for local agencies impacted for downtown Seattle hotspots meet every 2 months. Weekly meetings are conducted to coordinate maintenance activities like cleaning out storm drains or inspecting bridges.
Interaction: None
Notes: None

## Slide 19: Coordination Meetings
More frequent meetings are held for local agencies
  Every 2 months for Seattle hotspots
  Weekly to coordinate maintenance activities:
  Cleaning out storm drains or
  Inspecting bridges
Notes: Key Message: provide background on coordination meetings
Background Information: (Broken onto 2 slides)
Agency promotes annual meetings as a part of the kickoff of construction season. Occurs in February or early March. Projects for the next couple of construction seasons are discussed. People in attendance include people from traffic offices and city folks who are doing transit planning. The event planners for Seattle Mariners, the Seahawks, the universities, those are engaged in the transportation for those websites. More frequent meetings are held for local agencies impacted for downtown Seattle hotspots meet every 2 months. Weekly meetings are conducted to coordinate maintenance activities like cleaning out storm drains or inspecting bridges.
Interaction: None
Notes: None

## Slide 20: Institutionalizing Project Coordination
Stakeholders see the value of using the CIA tool
No requirements to submit project inputs, but understand the benefits of coordinating projects to minimize congestion impacts on local jurisdictions
Notes: Key Message: discuss how to institutionalize project coordination
Background Information: (broken into 2 slides)
In addition to the annual meetings, the agency does hold more frequent meetings, particularly for downtown Seattle. There are weekly meetings held by a different groups who are focused on the short-term impacts. They use some of the data from the tools for that meeting. They separate the kind of mid-term to long-term planning, which has worked well, having enough overlap so that projects are smoothed out. Taking advantage of these opportunities, institutionalizing coordination. We have not written a bunch of requirements, it has not been necessary, we have been getting the information we need. Others are more willing to share as a service rather than as requirement.
Interaction: is this possible at your agency?
Notes: None

## Slide 21: CIA Outputs are Routinely Used For…
Approval of state road closures by WSDOT regions
Revision of bus routes and schedules
Development of schedules by project teams
Development of special provisions in contracts
  Lists projects that must be coordinated using the CIA tool
Source: WSDOT
Notes: Key Message: discuss how to institutionalize project coordination
Background Information: (broken into 2 slides)
In addition to the annual meetings, the agency does hold more frequent meetings, particularly for downtown Seattle. There are weekly meetings held by a different groups who are focused on the short-term impacts. They use some of the data from the tools for that meeting. They separate the kind of mid-term to long-term planning, which has worked well, having enough overlap so that projects are smoothed out. Taking advantage of these opportunities, institutionalizing coordination. We have not written a bunch of requirements, it has not been necessary, we have been getting the information we need. Others are more willing to share as a service rather than as requirement.
Interaction: is this possible at your agency?
Notes: None

## Slide 22: Lessons Learned
Shifting focus from individual projects to network performance is important
Internal marketing helps demonstrate the value
Buy-in from management is important
Project coordination helps plan future work zone impacts with affected regions
Notes: Key Message: review lessons learned from the project.
Background Information: Multi-agency communications and culture change is important to collaboratively shift the focus from individual projects to network performance
Internal marketing helps demonstrate the value of project coordination and encourages stakeholder involvement
Buy-in from management to support the potential need for additional staff and resources is important
Project coordination can help plan future work zone impacts with all affected regions
Interaction: None
Notes: None

## Slide 23: I-94 Corridor Management
Source: FHWA
Notes: Key Message: introduce next example
Background Information: The next example will be Michigan’s I-94 Corridor.
Interaction: None
Notes: None

## Slide 24: Michigan’s I-94 Corridor
A major thoroughfare
271 miles across the state from Indiana to Canada
Source: Michigan DOT
Notes: Key Message: provide background on project
Background Information: (broken into 2 slides)
Michigan’s I-94 Corridor is a major thoroughfare stretching 271 miles across the state from Indiana to Canada:
primary connection between Detroit and Chicago.
varies from three lanes to two lanes in lower rural areas.
In 2010, 19 consecutive construction projects on the corridor led to lengthy delays resulting in creation of “One Corridor Focus” initiative which required I-94 be managed as one single unit with one overall travel time delay (TTD). Effort led by Corridor Operations Partnership (COP)
Interaction: None
Notes: None

## Slide 25: Michigan’s I-94 Corridor
  3 Regions
    Southwest
    Metro
    University
  8 Transportation Service Centers
  9 Counties
  Creation of “One Corridor Focus” initiative
Source: Michigan DOT
Notes: Key Message: provide background on project
Background Information: (broken into 2 slides)
Michigan’s I-94 Corridor is a major thoroughfare stretching 271 miles across the state from Indiana to Canada:
primary connection between Detroit and Chicago.
varies from three lanes to two lanes in lower rural areas.
In 2010, 19 consecutive construction projects on the corridor led to lengthy delays resulting in creation of “One Corridor Focus” initiative which required I-94 be managed as one single unit with one overall travel time delay (TTD). Effort led by Corridor Operations Partnership (COP)
Interaction: None
Notes: None

## Slide 26: I-94 Corridor Operations Partnership Mission:
  Improve traffic operations and system reliability along the I‐94 corridor statewide
Notes: Key Message: discuss the partnership
Background Information: (Broken into 3 slides) A team from the three regions and service center was created to develop ideas to move traffic through the corridor faster. It was titled the I-94 Corridor Operations Partnership (COP).
COP Mission:
  – Improve traffic operations and system reliability along the I‐94 corridor statewide
COP Objectives:
  – Unification of the I-94 corridor with one focus
  – Travel Reliability –40 min delay max for entire corridor( about 15% increase in normal travel time)
COP Sub-teams:
  – Corridor Performance Team - had the task of developing goals, setting up performance standards and actions to achieve them in the planning and design stages of the project.
  – Active Corridor Management Team - involved with improving management of active works owns along the corridor.
Interaction: None
Notes: None

## Slide 27: I-94 Corridor Operations Partnership Objectives:
Unification of the I-94 corridor with one focus:
  Travel reliability –40 minimum delay maximum for the entire corridor
Notes: Key Message: discuss the partnership
Background Information: (Broken into 3 slides) A team from the three regions and service center was created to develop ideas to move traffic through the corridor faster. It was titled the I-94 Corridor Operations Partnership (COP).
COP Mission:
  – Improve traffic operations and system reliability along the I‐94 corridor statewide
COP Objectives:
  – Unification of the I-94 corridor with one focus
  – Travel Reliability –40 min delay max for entire corridor( about 15% increase in normal travel time)
COP Sub-teams:
  – Corridor Performance Team - had the task of developing goals, setting up performance standards and actions to achieve them in the planning and design stages of the project.
  – Active Corridor Management Team - involved with improving management of active works owns along the corridor.
Interaction: None
Notes: None

## Slide 28: I-94 Corridor Operations Partnership Sub-Teams:
Corridor Performance Team
Active Corridor Management Team
Source: Michigan DOT
Notes: Key Message: discuss the partnership
Background Information: (Broken into 3 slides) A team from the three regions and service center was created to develop ideas to move traffic through the corridor faster. It was titled the I-94 Corridor Operations Partnership (COP).
COP Mission:
  – Improve traffic operations and system reliability along the I‐94 corridor statewide
COP Objectives:
  – Unification of the I-94 corridor with one focus
  – Travel Reliability –40 min delay max for entire corridor( about 15% increase in normal travel time)
COP Sub-teams:
  – Corridor Performance Team - had the task of developing goals, setting up performance standards and actions to achieve them in the planning and design stages of the project.
  – Active Corridor Management Team - involved with improving management of active works owns along the corridor.
Interaction: None
Notes: None

## Slide 29: Current Performance Measures – Travel Time Delay (TTD)
Threshold of 40 minutes
  15% increase in total travel time from end-to-end
Source: Michigan DOT
Notes: Key Message: talk about performance measures for corridor
Background Information: The team divided up I-94 into three sections, which did not match regional boundaries, forcing the teams to be more active in their coordination.
To fix the three segments along I-94 any colors on the map represent works zones that were active.
green, were no lane closures, traffic moving at or near posted speed.
yellow were reduced capacity during non-peak travel periods.
red were the ones that were going to happen during peak travel times.
Interaction: None
Notes: Describe the segments and the travel time delay for each segment from the slide.

## Slide 30: Current Performance Measures – Travel Time Delay (TTD)
Segment 1: Indiana Border to I-69
  TTD max 15 min
Segment 2: I-69 to I-75
  TTD max 15 min
Segment 3: I-75 to Canada
  TTD max 10 min
Notes: Key Message: talk about performance measures for corridor
Background Information: The team divided up I-94 into three sections, which did not match regional boundaries, forcing the teams to be more active in their coordination.
To fix the three segments along I-94 any colors on the map represent works zones that were active.
green, were no lane closures, traffic moving at or near posted speed.
yellow were reduced capacity during non-peak travel periods.
red were the ones that were going to happen during peak travel times.
Interaction: None
Notes: Describe the segments and the travel time delay for each segment from the slide.

## Slide 31: Current Performance Measures – Travel Time Delay (TTD))
Source: Michigan DOT
Notes: Key Message: talk about how performance measures were measured
Background Information: A list of each project was compiled the with calculated delays during peak and off-peak times to see if delay goals could be met. Each project is charted to provide a week by week summary of which projects are active. The rows on the bottom show estimated delays to provide a snapshot if goals are met or not. This data can then be used to adjust projects and/or dates, if possible.
Interaction: None
Notes: Not legible. Provide handout

## Slide 32: Corridor Level Standards Developed To:
Ensure customer experience is consistent and reliable
Reduce confusion and driver frustration
Improve compliance with work zone signage
Notes: Key Message: introduce corridor standards
Background Information: (broken into 2 slides)
Corridor level standards were developed to:
  Ensure customer experience from one work zone to another is consistent and reliable
  Reduce confusion and driver frustration
  Improve compliance with work zone signage, thus improving safety and reducing crashes
Standards include:
  – Left lanes will be closed first
  – Minimum 11’ work zone lane width (12’ preferred)
  – 2’ minimum paved shoulder
  – Emergency pull-outs where no refuge
Interaction: none
Notes: Go through the list on the slide.

## Slide 33: Corridor Level Standards Include:
Left lanes will be closed first
Minimum 11’ work zone lane width (12’ preferred)
Two-foot minimum paved shoulder
Emergency pull-outs where no refuge
Notes: Key Message: introduce corridor standards
Background Information: (broken into 2 slides)
Corridor level standards were developed to:
  Ensure customer experience from one work zone to another is consistent and reliable
  Reduce confusion and driver frustration
  Improve compliance with work zone signage, thus improving safety and reducing crashes
Standards include:
  – Left lanes will be closed first
  – Minimum 11’ work zone lane width (12’ preferred)
  – 2’ minimum paved shoulder
  – Emergency pull-outs where no refuge
Interaction: none
Notes: Go through the list on the slide.

## Slide 34: Active Corridor Management Goals:
Improved performance of individual work zones
Coordinated effort for corridor projects
To share
  Challenges
  Solutions
  Best practices
Source: Michigan DOT
Notes: Key Message: Discuss how they managed the corridor
Background Information: (broken into 2 slides)
Active corridor management teams were set up with goals for active work zones established, which include:
  –Improved performance of individual work zones
  –Coordinated effort for corridor projects
  –Sharing of challenges, solutions and best practices
Actions include:
  –Work zone delay measurement
  –Bi-weekly corridor work zone meeting
    •Incident and messaging coordination
    •Discuss performance results and determining actions to reduce impacts if necessary
Interaction: None
Notes: None

## Slide 35: Active Corridor Management Actions:
Work zone delay measurement
Bi-weekly corridor work zone meeting
  Incident and messaging coordination
  Discuss performance results
  Determine actions to reduce impacts if necessary
Source: Michigan DOT
Notes: Key Message: Discuss how they managed the corridor
Background Information: (broken into 2 slides)
Active corridor management teams were set up with goals for active work zones established, which include:
  –Improved performance of individual work zones
  –Coordinated effort for corridor projects
  –Sharing of challenges, solutions and best practices
Actions include:
  –Work zone delay measurement
  –Bi-weekly corridor work zone meeting
    •Incident and messaging coordination
    •Discuss performance results and determining actions to reduce impacts if necessary
Interaction: None
Notes: None

## Slide 36: Current Performance Measures: User Delay Cost
Easily defined
Comprehendible metric for both
  Transportation professionals
  The public
  Others
Notes: Key Message: User delay cost
Background Information: User delay cost was used as the performance measure. Mainly it was thought to be more easily understood by the public and other partners in highway operations. Travel time reliability was considered, but is more complex to understand.
Interaction: None
Notes: Go through the slide.

## Slide 37: Current Performance Measures: User Delay Cost
Source: Michigan DOT
Notes: Key Message: User delay cost
Background Information: User delay cost was used as the performance measure. Mainly it was thought to be more easily understood by the public and other partners in highway operations. Travel time reliability was considered, but is more complex to understand.
Interaction: None
Notes: Go through the slide.

## Slide 38: Customer Groups
MDOT focused efforts on three major causes of non-recurring congestion:
  Work zones
  Emergency responders
  Winter operations
Notes: Key Message: talk about the customers
Background Information: Three customer causes of non-recurring congestion were considered, these were:
Work Zones
Emergency responders along the corridor
Winter operations along I-94
Interaction: None
Notes: None

## Slide 39: 2011 User Delay Cost (UDC) On I-94
Reduce UDC on I-94
  Used speed map snapshots to determine delay
  Tracked on 124 miles of SW Region
2011
Notes: Key Message: review the various figure for user delay costs
Background Information: (Broken into 4 slides) Various user delay cost have been used on I-94. These are shown on the slide for the various years. In 2013 changed to University of Maryland RITIS software to calculate UDC for speeds under 60 MPH. It was a fairly good system and easier to use than previous attempts.
Interaction: None
Notes: WIG, Wildly Important Goal. Good opportunity to explain MDOT philosophy.

## Slide 40: 2012 User Delay Cost (UDC) On I-94
Reduce UDC on I-94
  Continued speed map methodology
  Expanded to all three regions to cover all 271 miles
2012
Notes: Key Message: review the various figure for user delay costs
Background Information: (Broken into 4 slides) Various user delay cost have been used on I-94. These are shown on the slide for the various years. In 2013 changed to University of Maryland RITIS software to calculate UDC for speeds under 60 MPH. It was a fairly good system and easier to use than previous attempts.
Interaction: None
Notes: WIG, Wildly Important Goal. Good opportunity to explain MDOT philosophy.

## Slide 41: 2013 User Delay Cost (UDC) On I-94
Limit UDC on I-94
  Changed to Regional Integrated Transportation Information System (RITIS) Software to calculate UDC for speeds under 60 MPH
  Customer satisfaction became overall MDOT WIG (Wildly Important Goal)
2013
Notes: Key Message: review the various figure for user delay costs
Background Information: (Broken into 4 slides) Various user delay cost have been used on I-94. These are shown on the slide for the various years. In 2013 changed to University of Maryland RITIS software to calculate UDC for speeds under 60 MPH. It was a fairly good system and easier to use than previous attempts.
Interaction: None
Notes: WIG, Wildly Important Goal. Good opportunity to explain MDOT philosophy.
The Regional Integrated Transportation Information System (RITIS) is an automated data sharing, dissemination, and archiving system that includes many performance measure, dashboard, and visual analytics tools that help agencies to gain situational awareness, measure performance, and communicate information between agencies and to the public.

## Slide 42: 2014 User Delay Cost (UDC) On I-94
Limit UDC on I-94
  Continued RITIS methodology
  UDC continued to support customer satisfaction
2014
Notes: Key Message: review the various figure for user delay costs
Background Information: (Broken into 4 slides) Various user delay cost have been used on I-94. These are shown on the slide for the various years. In 2013 changed to University of Maryland RITIS software to calculate UDC for speeds under 60 MPH. It was a fairly good system and easier to use than previous attempts.
Interaction: None
Notes: WIG, Wildly Important Goal. Good opportunity to explain MDOT philosophy.

## Slide 43: Regional Integrated Transportation Information System (RITIS)
Operation focus shift
ITS infrastructure
Vehicle speed probe data
Manual calculation of delay
Automated calculation of delay
Notes: Key Message: discuss tool Michigan uses
Background Information: (broken into 2 slides) The Regional Integrated Transportation Information System can provide some information to engineers fairly quickly. The Regional Integrated Transportation Information System (RITIS) is an automated data sharing, dissemination, and archiving system that includes many performance measures, a dashboard, and visual analytics tools that help agencies to gain situational awareness, measure performance, and communicate information between agencies and to the public. RITIS automatically fuses, translates, and standardizes data obtained from multiple agencies in order to provide an enhanced overall view of the transportation network. Participating agencies are able to view transportation and related emergency management information through innovative visualizations and use it to improve their operations and emergency preparedness. RITIS also uses regional standardized data to provide information to third parties, the media, and other traveler information resources including web sites, paging systems, and 511. There are three main RITIS components including: real-time data feeds, real-time situational awareness tools, and archived data analysis tools.
Interaction: None
Notes: Explain the Manual Calculation of Delay bullet to the class along with the other bullets. (see MDOT report)

## Slide 44: RITIS
Source: Michigan DOT
Notes: Key Message: discuss tool Michigan uses
Background Information: (broken into 2 slides) The Regional Integrated Transportation Information System can provide some information to engineers fairly quickly. The Regional Integrated Transportation Information System (RITIS) is an automated data sharing, dissemination, and archiving system that includes many performance measures, a dashboard, and visual analytics tools that help agencies to gain situational awareness, measure performance, and communicate information between agencies and to the public. RITIS automatically fuses, translates, and standardizes data obtained from multiple agencies in order to provide an enhanced overall view of the transportation network. Participating agencies are able to view transportation and related emergency management information through innovative visualizations and use it to improve their operations and emergency preparedness. RITIS also uses regional standardized data to provide information to third parties, the media, and other traveler information resources including web sites, paging systems, and 511. There are three main RITIS components including: real-time data feeds, real-time situational awareness tools, and archived data analysis tools.
Interaction: None
Notes: Explain the Manual Calculation of Delay bullet to the class along with the other bullets. (see MDOT report)

## Slide 45: Measuring Work Zone Performance on I-94
Source: Michigan DOT
Notes: Key Message: Review performance measure MDOT used
Background Information: this shows some of the various performance measures that have been used.
Interaction: None
Notes: MOT is Maintenance of Traffic

## Slide 46: Performance Measures – SW Region
Limit delays through all work zones to less than 10 minutes for 90 percent of days each work zone is in place during the 2015 construction season
Source: Michigan DOT
Notes: Key Message: talk about performance measure
Background Information: (broken into 2 slides) Current performance measures are to limit delays through all work zones to less than 10 minutes for 90% of days each work zone is in place. Weekly meetings are held to discuss upcoming impacts of work zones and to coordinate messaging.
Interaction: None
Notes: None

## Slide 47: Performance Measures – SW Region
Hold weekly work zone meetings to:
  Discuss upcoming impactful work and
  Coordinate messaging
Source: Michigan DOT
Notes: Key Message: talk about performance measure
Background Information: (broken into 2 slides) Current performance measures are to limit delays through all work zones to less than 10 minutes for 90% of days each work zone is in place. Weekly meetings are held to discuss upcoming impacts of work zones and to coordinate messaging.
Interaction: None
Notes: None

## Slide 48: Findings
Performance metrics are necessary to determine whether your program is successful
  Are the right metrics being measured?
    Selecting performance measures must be customized to the agency
Notes: Key Message: review findings
Background Information: (Broken into 4 slides) Findings for the Program include:
Performance metrics are necessary to find if your program is successful.
  – Are we measuring the right things? Choosing the right measures and thresholds takes time.
Tracking a project’s 24-7 performance maintains staff focus on mobility and improves decision making toward operations.
Process requires full support from top management.
User Delay Cost has a relationship to actual contract bid cost. Finding appropriate balance isn’t easy, but measuring it provides a better end result for motorists.
Interaction: None
Notes: None

## Slide 49: Findings (cont.)
Tracking a project’s 24-7 performance maintains staff focus on mobility and improves decision making on operations-related issues
Notes: Key Message: review findings
Background Information: (Broken into 4 slides) Findings for the Program include:
Performance metrics are necessary to find if your program is successful.
  – Are we measuring the right things? Choosing the right measures and thresholds takes time.
Tracking a project’s 24-7 performance maintains staff focus on mobility and improves decision making toward operations.
Process requires full support from top management.
User Delay Cost has a relationship to actual contract bid cost. Finding appropriate balance isn’t easy, but measuring it provides a better end result for motorists.
Interaction: None
Notes: None

## Slide 50: Findings (cont.)
The process requires full support from top management
Notes: Key Message: review findings
Background Information: (Broken into 4 slides) Findings for the Program include:
Performance metrics are necessary to find if your program is successful.
  – Are we measuring the right things? Choosing the right measures and thresholds takes time.
Tracking a project’s 24-7 performance maintains staff focus on mobility and improves decision making toward operations.
Process requires full support from top management.
User Delay Cost has a relationship to actual contract bid cost. Finding appropriate balance isn’t easy, but measuring it provides a better end result for motorists.
Interaction: None
Notes: None

## Slide 51: Findings (cont.)
User Delay Cost has a relationship to actual contract bid cost
Finding appropriate balance isn’t easy
Measuring it provides a better end result for motorists
Notes: Key Message: review findings
Background Information: (Broken into 4 slides) Findings for the Program include:
Performance metrics are necessary to find if your program is successful.
  – Are we measuring the right things? Choosing the right measures and thresholds takes time.
Tracking a project’s 24-7 performance maintains staff focus on mobility and improves decision making toward operations.
Process requires full support from top management.
User Delay Cost has a relationship to actual contract bid cost. Finding appropriate balance isn’t easy, but measuring it provides a better end result for motorists.
Interaction: None
Notes: None

## Slide 52: For Further Information
To look at other smarter work zone coordination examples that have been used by other agencies, go to the National Work Zone Clearinghouse at:
https://www.workzonesafety.org/swz
https://www.workzonesafety.org/swz/webinars/
Notes: Key Message: provide information of where student can go to find out more
Background Information: work zone safety clearinghouse has a copy of the webinars and links to case studies to find out more information.
Interaction: None
Notes: None

## Slide 53: Knowledge Check
Name the two projects we discussed
Name 2-3 lessons learned from these projects
Notes: Key Message: Recap
Background Information: To gauge student understanding
Interaction: None
Notes: None

## Slide 54: Questions
Notes: Key Message: Questions
Est. Presentation Time: Less than 1 minute(s)
Explanation of Cues/Builds: None
Suggested Comments: Self explanatory
Suggested Questions: Any questions before we move on?
Additional Information: None
Possible Problems: If no questions, you may ask a few yourself.