## Slide 1: Developing and Implementing Transportation Management Plans
6. TMP Strategies
Image: ATSSA
Notes: Key Message: Title Slide
Background Information: In this module, we will discuss TMP Strategies that DOTs can use to minimize or mitigate work zone safety and mobility impacts. We’ll also have some exercises where you will work to match strategies to work zone scenarios based on what we’ve learned so far.
Interaction: N/A
Notes:

## Slide 2: Objectives
Identify TMP Strategies
Define possible TMP Strategies
  Temporary Traffic Control Plan (TTCP)
  Transportation Operations (TO)
  Public Information and Outreach (PI & O)
List available tools
Notes: Key Message: Review module objectives
Background Information: Module 6 provides an overview, and then discusses identification of TMP strategies; possible TMP strategies; and tools that some Agencies are using to help with selecting appropriate TMP strategies. The module ends with an exercise to help you apply what you have learn
Interaction:
Notes:

## Slide 3: Strategies deployed to:
Improve safety and mobility of work zones
Reduce work zone impacts on the community/ businesses
Image: FHWA
Notes: Key Message: Provide an overview of available strategies
Background Information:
TMP strategies are intended to improve the safety and mobility of work zones and reduce the work zone impacts on the community and businesses. Strategies should be selected to enable smooth traffic flow, minimize traffic delays, and maintain or improve safety for road users and workers. Strategies should also maintain access for businesses and residents, allow for emergency response, and address the needs of other stakeholders. TMP strategies should also support the timely completion of the project.
Interaction: None
Notes: None

## Slide 4: Successful Strategies
Minimize traffic delays
Maintain or improve safety for road users and workers
Maintain business and resident access
Allow for emergency response
Address needs of other stakeholders
Support timely completion of the work
Notes: Key Message: Provide an overview of available strategies
Background Information:
TMP strategies are intended to improve the safety and mobility of work zones and reduce the work zone impacts on the community and businesses. Strategies should be selected to enable smooth traffic flow, minimize traffic delays, and maintain or improve safety for road users and workers. Strategies should also maintain access for businesses and residents, allow for emergency response, and address the needs of other stakeholders. TMP strategies should also support the timely completion of the project.
Interaction: None
Notes: None

## Slide 5: TMP Strategies under the Rule
The Work Zone Safety and Mobility Rule (Rule) breaks out TMP Strategies into three categories:
  Temporary Traffic Control (TTC)
  Transportation Operations (TO)
  Public Information and Outreach (PI & O)
Some agencies have additional categories
Notes: Key Message: TMP Strategies can be broken out into three categories
Background Information:
The work Zone Safety and Mobility Rule breaks out TMP strategies into three categories: temporary traffic control, transportation operations, and public information and outreach.
Some agencies have created additional categories of strategies to include in their TMPs. A few states include incident management strategies as a separate category in their TMPs for significant projects. A few states have added a new category called performance monitoring strategies that includes any specific observational, logging, and recording activities that are required during the project for work zone performance measurement purposes.
Interaction: None
Notes: None

## Slide 6: Considerations - Motorists
Motorist
Non-motorist
  Accessibility
Incident response
Business access
Residential access
Image: FHWA
Notes: Key Message: Considerations before selecting a strategy
Background Information: Motorists: In developing a TMP, consider the needs of motorists. Motorists must be provided with information in advance to make a safe decision. Road users generally respond to positive guidance. Guidance is often provided using traffic control devices such as advanced and localized signing, temporary traffic signals, and pavement markings. In some cases, flaggers are used to provide guidance. Guidance can also be combined with Intelligent Transportation Systems (ITS), which provide real-time information about lane closure and travel delays. It is important that the information provided be clear, concise, and accurate. Inaccurate, untimely, or inconsistent messages can lead the public and other stakeholders to lose trust in work zone signage or the Agency’s ability to provide reliable information.
Non-motorist needs are also important, particularly in urban settings where there is significant pedestrian traffic. Pedestrian accommodations should be at least similar to those existing prior to construction and may require providing an alternate pedestrian route. Any planned detours must comply with the Americans with Disabilities Act (ADA).
Incident response: Take into account the needs of first responders in responding to an incident in or near the work zone. Consideration should also be given to the impacts a work zone may have on the ability of responders to reach nearby hospitals or other emergency care facilities. Consider whether or not alternate routes are advisable, and plan for appropriate signing, should a detour become advisable.
Business access: Businesses need to continue to operate during road work, so employees, customers, and those bringing deliveries need to be able to reach businesses affected by a work zone. Access may require a temporary entrance or signage clearly marking an obscured entrance. Keeping businesses informed, and considering work schedules and peak customer periods in developing your TMP can foster good relationships with business stakeholders.
Residential access: When a project significantly affects the access of residents to their neighborhood, the TMP should include strategies aimed at keeping those residents informed and limiting the duration of the impacts.
Interaction: None
Notes: None

## Slide 7: Identifying TMP Strategies
Image: FHWA
Notes: Key Message: The purpose of each TMP is to mitigate safety and mobility concerns within each strategy category
Background Information:
The TTC component of the TMP implements the chosen project design strategy. This includes lane widths, taper lengths, speed limits, and the layout of traffic control devices in the traffic control plan to guide users through the work zone.
TO components address strategies to improve work zone operations, such as communications and detector requirements for a work zone traffic monitoring and incident management system, estimating traffic diversion patterns and rates to determine potential impacts, and appropriately improving operations on alternate routes, such as through signal timing adjustments, in response.
The PI & O component uses estimated traffic volumes that the project will affect to determine the PI & O needs. The PI & O strategies selected should be effective in communicating with affected stakeholders and coordinating with stakeholders to carry out the PI & O program.
Interaction: None
Notes: None

## Slide 8: Identified TMP Strategies Should be Based on:
Type of work zone
Traffic conditions
Anticipated impacts
Project constraints
Project phasing or staging
Conditions in the surrounding area
  Alternate routes/modes
  Access
Image: ATSSA
Notes: Key Message: Final strategy selection is based on several factors.
Background Information:
Selection of TMP strategies is based on various factors, including the type of work zone, such as an urban interstate paving project; traffic conditions, such as traffic demand and truck volumes; and anticipated work zone impacts, such as delay and queues. Project constraints, such as increased right of way or construction costs and phasing, as well as the conditions in the surrounding area, such as available alternate routes and transportation modes, should also guide the selection of strategies.
Interaction: None
Notes: None

## Slide 9: Agency-related Factors
Agency WZ policies
  Maximum queue lengths/delays allowed
Lane closure policies that specify when a lane closure is permitted
Analytical/modeling tools used by the agency
Concerns of stakeholders
Image: ATSSA
Notes: Key Message: Strategy selection may be narrowed due to agency policy.
Background Information:
Some state transportation agencies have developed policies limiting the amount of delay and the queue length in advance of a work zone. They may also have lane closure policies, or strategies, that they use as guidance in determining daily permitted lane closure times.
Permitted lane closure times define what times of the day, week, or season a lane closure is allowed on a facility and at a specific location or segment.
Some agencies may require the use of specific analysis tools to predict delays, queues, and the impacts of detours and compare these for various strategies.
Interaction: None
Notes: None

## Slide 10: Example TMP Strategy
Analysis to strategy selection
Preliminary assessments resulted in 4 options:
  Continuous (24/7) Closure
  72-Hour Weekday Closures
  55-Hour Weekend Closures
  10-Hour Night time Closures
Alternatives assessment (schedule, delay, and Agency costs) resulted in one option:
  Continuous (24/7) Closure
Notes: Key Message: Discuss example TMP strategy
Background Information:
In most cases, a preliminary assessment of impacts may result in more than one option. As design progresses, more information may become available on the feasibility of each approach, leading to detailed assessment and selection of the most viable option.
In the example shown here, the preliminary assessment resulted in four options. Various measures of effectiveness such as schedule, delay, and Agency costs were considered to arrive at the best option, which was a continuous closure.
Interaction: None
Notes: None

## Slide 11: Example: Caltrans TMP Strategies
Level of TMP | Types of Conditions | Types of Strategies
“Blanket” TMP | No expected delays Off-peak work Low volume roads Moving lane closures | PCMS Freeway Service Patrol Traffic Management Team Only work during off-peak hours
“Minor” TMP (Majority of TMPs fall into this category) | Minimal impacts expected Lane closure required Some mitigation measures needed | Night work only Portable & Fixed CMS Enhanced enforcement Traffic Management Team Highway Advisory Radio
Notes: Key Message: Example of Caltrans strategy selection approach.
Background Information:
California Department of Transportation (Caltrans) TMPs are categorized into three levels based on project characteristics and projected delay. For each TMP level, Caltrans provides examples of the types of conditions that would be present for a project to be in that category and possible strategies to use. This table serves as a guide for Caltrans TMP developers.
Interaction: None
Notes: None

## Slide 12: Example: Caltrans TMP Strategies
Level of TMP | Types of Conditions | Types of Strategies
“Major” TMP (~5% of TMPs are major) | Significant impacts expected Multi-jurisdictional in scope Longer duration Multiple contracts involved | Same as for minor TMP plus: Extended closures (TTC) Moveable barriers to reverse lanes during peak periods (TTC) Detours (TO) Reduced lane widths (TO) Public awareness campaign (PI & O) Website (PI & O)
Notes: Key Message: Example of Caltrans strategy selection approach.
Background Information:
Continued from previous slide.
Interaction: None
Notes: None

## Slide 13: TTC Strategies
Full road closures
Phasing/staging
Traffic control devices
  Signing
  Striping
  Temporary signals
  Moveable barrier
  Crash cushions
  PCMS, etc.
Coordination among multiple projects
Image: ATSSA
Notes: Key Message: There are several strategies that can be applied to maximize mobility without compromising safety. Some will be part of the TTC plan, others will relate to TO and PI & O.
Background Information:
Temporary Traffic Control strategies can be categorized into level of closure (e.g., full or partial), phasing or staging of construction, and traffic control devices. Knowing where there are other nearby work zones that can affect traffic flow is also an important part of the planning process.
We will now look at various TTC strategies.
Interaction: None
Notes: None

## Slide 14: TTC Strategies: 1. Full Road Closures
Full closure (24/7)
Weekend full closure
Limited capacity closure
  For example, 72-hour closure during one weekday (Friday or Monday) and the weekend
Nighttime/off-peak closure
Intermittent closure
  Including rolling roadblocks
  Depending on work activity
Notes: Key Message: Full road closures are again becoming a popular transportation management strategy.
Background Information: When traffic volumes were light, it was common to close the road and complete work in the closed roadway section. However as traffic volumes increased working adjacent to traffic became necessary especially on the Interstate system. Closing the road was rarely used. Lane closures on high speed roadways put the workers and moving traffic very close. Working in one or two lanes at a time slows the progress of work. Recently in an attempt to shorten the duration of work zones, agencies have closed major urban routes and done work on a full-time basis while the road was closed. Experience with full road closures has been very good and has reduced the time a road is affected by reconstruction. Some of the various types of closures are shown here.
Full closure is becoming a popular strategy for several reasons. It is supported by the Work Zone Safety Rule as an effective exposure control measure and is considered to offer the greatest safety to workers compared to other exposure control options. Full closure also shortens project duration because worker efficiency is maximized and because it has been shown to be successful in urban areas where alternate networks exist.
Interaction: Have you used any full road closures.
Notes: None

## Slide 15: Full Closure Example
I-95 near Wilmington, Delaware
  Local newspaper
  Public meetings
  Radio
  Bus routes
  “Planning & Survival Guide”
Image: Delaware DOT
Notes: Key Message: Another example of a full closure.
Background Information: 7 month project Ads in local newspapers, outreach events, public meetings, “Survival Guide,” colorful character known as the traffic “creep,” radio, Express bus routes. The morning the full closure started, media were on hand to witness the congestion they expected would ensue. Questioning whether they were in the right place, the media were confused by the lack of congestion.
The I-405 full closure in LA is another good example, “Carmageddon” was a massive PI & O campaign and very successful.
Interaction: None
Notes: None

## Slide 16: Partial Road Closure Example
Image: FHWA
Notes: Key Message: Full road closures may be safer for workers also.
Background Information: This picture shows the closure of one direction of traffic on I-84 in Portland. Crews are able to pave without working in traffic.
Interaction: None
Notes: None

## Slide 17: TTC Strategies: 2. Phasing or Staging
Construction can be phased or staged by:
  Halves/Sides
  Adjacent/Parallel
  Serial/Segmental
  Closure/Detour
  Combinations
Image: ATSSA
Notes: Key Message: This slide shows other Traffic control strategies by phasing or staging,
Background Information: The slides to follow show various examples of these and other traffic control strategies.
Interaction: None
Notes: None

## Slide 18: Lane Closures
Images: FHWA
Notes: Key Message: This slide depicts construction by halves or sides. One lane of a multi-lane facility is closed while work is being done on the other half or side.
Background Information: This work zone type closes off one or more normal traffic lanes. Capacity and delay analyses may be required to determine whether serious congestion will result from lane closures. In some cases, use of the shoulder or median area as a temporary lane will help mitigate the problems arising from the loss in capacity. Upgrading or replacement of existing pavement or shoulder, or placement of temporary pavement may be necessary.
Interaction: None
Notes: None

## Slide 19: One-Lane, Two-Way Operation
Images: FHWA
Notes: Key Message: Briefly walk through application
Background Information: AKA Shared Right-of-Way. This work zone type involves utilizing one lane for both directions of traffic. This work zone type is typically only used on bridges or small, short-term projects. Flaggers or temporary traffic signals are normally used to coordinate the two directions of traffic.
Interaction: None
Notes: None

## Slide 20: Road Closures with a Diversion
Image: FHWA
Notes: Key Message: Briefly walk through application
Background Information: This work zone involves the total closure of the roadway (one or both directions) where work is being performed and the traffic is rerouted to a temporary roadway constructed within the highway right-of-way. This application may require the acquisition of a temporary easement and usually requires extensive preparation of the temporary roadway. Generally, temporary runarounds are designed for a posted speed reduction of no more than 5 mph to 15 mph below the existing posted speed of the route.
Interaction: None
Notes: None

## Slide 21: Temporary Road Closures
Images: FHWA
Notes: Key Message: Briefly walk through application
Background Information: This work zone type involves stopping all traffic in one or both directions for a relatively short period to allow the work to proceed. After a specific time, depending on traffic volumes, the roadway is re-opened and all vehicles can travel through the area. This application is normally only appropriate on low-volume roadways or during periods where there are very low volumes (e.g., Sunday morning, nighttime).
Interaction: None
Notes: None

## Slide 22: Lane Shift
Images: FHWA
Notes: Key Message: Briefly walk through application
Background Information: This work zone type is configured by reducing the width of one or more lanes to retain the number of lanes normally available to traffic. This application is the least disruptive of all work zone types, but it is generally only appropriate if the work area is mostly outside the normal traffic lanes. Note that narrow lane widths may reduce the facility’s capacity, especially where there is significant truck traffic. The use of shoulders as part of the lane width helps reduce the amount of lane width reduction that may be required; however, the structural adequacy of the shoulders should be checked. Especially where this application is applied to long-term work zones, it will require the removal of the current lane markings to avoid motorist confusion.
Interaction: None
Notes: None

## Slide 23: Median Crossovers
Images: FHWA
Notes: Key Message: Briefly walk through application
Background Information:
This work zone type involves routing one direction of the traffic stream across the median to the opposite traffic lanes. This application might also incorporate the use of shoulders and/or lane constrictions to maintain the same number of lanes. Due to the inherent high traffic volumes and, in most cases, higher speeds, it will be necessary to consider higher geometric criteria due to the higher motorist expectations. This approach involves the reconstruction of all lanes in one direction while the opposing lanes share the same roadway with traffic in the other direction. For high volume four-lane facilities, both shoulders may be rebuilt to provide four reduced-width lanes. For six-lane facilities, traffic is generally restricted to two lanes in each direction. This may require using the shoulders, reducing the lane widths, and/or providing minor widening. Under certain circumstances, depending on the median width and shoulder configuration, the inner lane of the two-way operation may not be readily accessible in the event of emergencies. Providing for emergency turnouts and/or emergency vehicle access at appropriate intervals on the segment under construction may be considered. Some advantages and disadvantages of this strategy include:
Advantages
• It provides an effective work area.
• Generally, workers are well separated from the traffic stream.
• Work site access can be arranged with minimal interference from the general traffic flow.
Disadvantages
• Positive separation of the traffic streams is required.
• There are potential emergency access problems throughout the project.
• There may be special problems at interchanges with traffic crossing the work zone.
• Reduced capacity.
The use of this application is encouraged under the following conditions:
• all safety issues can reasonably be addressed,
• construction time can be reduced,
• pavement and shoulder structures can be reasonably upgraded, and
• roadway geometrics allow crossover construction.
There are design issues relative to designing two-way applications and crossovers (e.g., maximum length, pavement widths, pavement design, speed reductions). If this application is used, separate opposing traffic on high-speed facilities (i.e., posted speeds of 45 mph or greater) with positive barriers throughout the length of the two-way operation. Drums, cones, or vertical panels may be substituted for positive barriers in low-speed urban situations. This drawing depicts some of the channelization devices that may be used with this layout. Consider also the option of reconstructing the shoulder to allow it to be used as a travel lane.
Interaction: None
Notes: None

## Slide 24: Crossover Example
Image: ATSSA
Notes: Key Message: Example of a crossover
Background Information: This shows a crossover, but also show the closure of the road where work is being done, also by halves or sides.
Interaction: None
Notes: None

## Slide 25: Restrict Hours of Work
Night work only
Weekend work only
Lane closure restrictions
  Work when traffic volumes are lower
Image: FHWA
Notes: Key Message: Another traffic control measure is restricting the hours of work.
Background Information: walk through various ways of restricting work hours based on traffic demand.
Interaction: None
Notes: None

## Slide 26: Night Work
Image: FHWA
Notes: Key Message: Picture shows night work with some good lighting.
Background Information:
Interaction: None
Notes: None

## Slide 27: But do it safely
Image: ATSSA
Notes: Key Message: Another picture of night work.
Background Information: Lighting is poor when workers are just using the headlights of the their vehicles to do the work. May be able to see the workers, but can they see the work they are doing (Wiring reinforcement for the patch.)
Interaction: None
Notes: None

## Slide 28: TTC Strategies: 3. Traffic Control Devices
Advance warning signs
Temporary traffic barrier
See the MUTCD Part 6 for other devices and typical applications
Image: ATSSA
Notes: Key Message: Additional examples.
Background Information:
Planning for the use and positioning of traffic control devices such as signs, temporary signals, moveable barrier, crash cushions, DMS, etc. are an important part of the TTCP. Motorists can easily become confused in a complex work zone, and positive direction on how to navigate the altered configuration can both improve mobility as well as reduce the potential for crashes.
Interaction: None
Notes: Refer to MUTCD Part 6 for information on typical applications for the deployment of the minimum acceptable level of traffic control for given work zone scenarios.

## Slide 29: TTC Strategies: Project Coordination
Coordinating among multiple projects in the same corridor enables agencies to:
  Effectively manage overall impacts
  Effectively use resources
  Avoid conflicts in roles and responsibilities
  Avoid additional costs
  Avoid conflicts in TTC Plans and other future strategies
Notes: Key Message: The impacts from failure to coordinate can have widespread negative impacts, so reaching out to intra- and interagency counterparts is crucial.
Background Information:
Project schedules should be coordinated and public outreach efforts and traffic management efforts can sometimes be shared across projects. Coordination among owners of different road projects that can affect each other is crucial to achieving the objectives of any TTC. Poor coordination can result in significant delays, conflicting messages leading to unsafe conditions, and a public relations “nightmare.”
Developing relationships with your counterparts in other agencies, defining roles and responsibilities, and holding either formal or informal meetings to share information will lead to cooperative relationships that will facilitate strategy identification and development of an effective TTCs.
In some cases, agencies have developed regional TMPs to help coordinate efforts across all the projects in an area or on a corridor. The Oregon DOT’s corridor-level approach ensures that all the projects within the corridor and their individual TMPs are integrated, resulting in less conflict and more efficient use of resources.
Interaction: None
Notes: Additional information on overarching coordination activities is in the next section. Limit this discussion to project-level coordination.

## Slide 30: Transportation Operation Strategies
Demand Management
Corridor Network Management
Work Zone Safety Management
Traffic/Incident Management and Enforcement Strategies
Notes: Key Message: Discuss transportation operation strategies
Background Information:
Transportation operations strategies can mitigate work zone impacts by using improved transportation operations and management of the transportation system in and around the work zone. Strategies include demand management, where the strategies inform motorists to consider traveling another way, such as by transit or carpool, to reduce the volume of cars flowing through the work zone. This is particularly useful when the Agency is unable to provide the necessary capacity in a work zone.
Infrastructure or corridor management strategies are where the responsible Agency makes decisions that can affect the road user such as, signal re-timing, parking restrictions, and lane control.
Strategies specifically focused on safety include speed management, barrier installations, and temporary rumble strips.
The last category includes strategies that involve monitoring traffic conditions and making adjustments to traffic operations based on changing conditions. These strategies include more improved detection, verification, response, and clearance of crashes; adequate enforcement of traffic regulations in work zones; and the use of ITS and traffic management centers to monitor and manage traffic.
Interactivity: None
Notes: None

## Slide 31: TO Strategies: 1. Demand Management
Transit improvements
Carpool incentives
Congestion pricing
Image: FHWA
Notes: Key Message: Demand management can be challenging, but there are effective ways to bring it about.
Background Information:
  Demand management strategies include transit improvements, carpool incentives and congestion pricing.
Through significant experience, two basic lessons have been learned about travel demand management: (1) it is not easy and (2) it can be done. The effort required for a successful demand management program is extensive. Several of these strategies are very dependent on the successful engagement and cooperation of major businesses and employers.
Some common strategies that can reduce vehicle flow rates through work zones include reducing total travel, reducing vehicle trips, and reducing the number of vehicles traveling through the work zone.
Reduce total travel: The first tactic is to reduce the total demand on the network by discouraging non-essential travel, especially during peak periods. The next step is to secure the cooperation of major employers and their employees in making some temporary accommodations during critical phases. Public and employer outreach programs solicit reductions in total travel through a reduction in the home-to-work trips. Alternative work schedules and work from home are common techniques. These types of initiatives used to face a lot of resistance. At a time of instant communications and information transfer many businesses and agencies have grown comfortable with the idea that employees do not have to be at a specific location at prescribed and common times.
Reduce vehicle trips: The next tactic is to reduce the number of vehicle trips on the affected network. As you know, in general the U.S. has very low vehicle occupancy rates. The one person per vehicle scenario is always inefficient but at times when capacity is substantially reduced it becomes unworkable. The number of vehicles on the network can be reduced by shifting essential trips on other modes and increasing vehicle occupancy.
Reduce vehicles traveling through the work zone: The number of vehicles passing through a work zone can be reduced by publicizing and clearly marking alternative routes.
Maintain and augment capacity: Now we are going to look at the supply or capacity side. Whenever a lane is removed from service, there is a reduction in capacity. Additionally, because of reduced speeds, capacity is often lost in work zones even when all lanes are open. There are a number of techniques that can be used to maintain and augment capacity through the work zone: Shoulders are often converted to travel lanes. In some cases, substantial construction is needed (width, pavement structure, slope, superelevation, rumble strips); Diversions (runarounds) are offline temporary roadways that provide nearly equal capacity.
Ridesharing and incentive programs: This strategy was successfully implemented on the New York Avenue reconstruction project in Washington, DC. The District DOT provided the first 2,000 New York Avenue commuters with a $50 per month incentive to use ride-sharing alternatives such as buses, rail transit, or organized vanpools. The program also provided one-on-one advice to help commuters determine which alternatives were best for their individual needs.
Interaction: None
Notes: None

## Slide 32: TO Strategies Aim to:
Reduce total travel
Reduce vehicle trips
Reduce vehicles traveling through the work zone
Maintain and augment capacity
Ridesharing and incentive programs
Image: FHWA
Notes: Key Message: Demand management can be challenging, but there are effective ways to bring it about.
Background Information:
  Demand management strategies include transit improvements, carpool incentives and congestion pricing.
Through significant experience, two basic lessons have been learned about travel demand management: (1) it is not easy and (2) it can be done. The effort required for a successful demand management program is extensive. Several of these strategies are very dependent on the successful engagement and cooperation of major businesses and employers.
Some common strategies that can reduce vehicle flow rates through work zones include reducing total travel, reducing vehicle trips, and reducing the number of vehicles traveling through the work zone.
Reduce total travel: The first tactic is to reduce the total demand on the network by discouraging non-essential travel, especially during peak periods. The next step is to secure the cooperation of major employers and their employees in making some temporary accommodations during critical phases. Public and employer outreach programs solicit reductions in total travel through a reduction in the home-to-work trips. Alternative work schedules and work from home are common techniques. These types of initiatives used to face a lot of resistance. At a time of instant communications and information transfer many businesses and agencies have grown comfortable with the idea that employees do not have to be at a specific location at prescribed and common times.
Reduce vehicle trips: The next tactic is to reduce the number of vehicle trips on the affected network. As you know, in general the U.S. has very low vehicle occupancy rates. The one person per vehicle scenario is always inefficient but at times when capacity is substantially reduced it becomes unworkable. The number of vehicles on the network can be reduced by shifting essential trips on other modes and increasing vehicle occupancy.
Reduce vehicles traveling through the work zone: The number of vehicles passing through a work zone can be reduced by publicizing and clearly marking alternative routes.
Maintain and augment capacity: Now we are going to look at the supply or capacity side. Whenever a lane is removed from service, there is a reduction in capacity. Additionally, because of reduced speeds, capacity is often lost in work zones even when all lanes are open. There are a number of techniques that can be used to maintain and augment capacity through the work zone: Shoulders are often converted to travel lanes. In some cases, substantial construction is needed (width, pavement structure, slope, superelevation, rumble strips); Diversions (runarounds) are offline temporary roadways that provide nearly equal capacity.
Ridesharing and incentive programs: This strategy was successfully implemented on the New York Avenue reconstruction project in Washington, DC. The District DOT provided the first 2,000 New York Avenue commuters with a $50 per month incentive to use ride-sharing alternatives such as buses, rail transit, or organized vanpools. The program also provided one-on-one advice to help commuters determine which alternatives were best for their individual needs.
Interaction: None
Notes: None

## Slide 33: Transportation Operation Strategies: 2. Corridor Network Management
Signal re-timing
Parking restrictions
Lane controls
Moveable barrier systems
Image: ATSSA
Notes: Key Message: Discuss transportation operation strategies
Background Information:
Transportation operations strategies can mitigate work zone impacts by using improved transportation operations and management of the transportation system in and around the work zone. Strategies include demand management, where the strategies inform motorists to consider traveling another way, such as by transit or carpool, to reduce the volume of cars flowing through the work zone. This is particularly useful when the Agency is unable to provide the necessary capacity in a work zone.
Infrastructure or corridor management strategies are where the responsible Agency makes decisions that can affect the road user such as, signal re-timing, parking restrictions, and lane control.
Strategies specifically focused on safety include speed management, barrier installations, and temporary rumble strips.
The last category includes strategies that involve monitoring traffic conditions and making adjustments to traffic operations based on changing conditions. These strategies include more improved detection, verification, response, and clearance of crashes; adequate enforcement of traffic regulations in work zones; and the use of ITS and traffic management centers to monitor and manage traffic.
Interactivity: None
Notes: None

## Slide 34: Moveable Barrier Systems
Image: Barrier Systems, Inc.
Notes: Key Message: Example of capacity management
Background: This is an example of a moveable barrier being used to implement a reversible lane. This is two-way traffic on one directional roadway. By using part of the shoulders as travel lanes, five lanes have been created on a directional roadway with four permanent lanes. The barrier that separates directional travel is moved twice a day to allow three lanes in the heavy direction of flow.
Interactivity: None
Notes: Photo obtained from Barrier Systems Inc.

## Slide 35: TO Strategies Examples
Dynamic Lane Merge
Real-Time ITS Message
Queue warning systems
Images: International Road Dynamics, Inc.
Notes: Key Message: Implementation examples.
Background Information:
Dynamic lane merge is another option. Using this technique, traffic is directed to use both lanes (open and closed lanes) until it reaches the designated merge point (close to the taper) where traffic is instructed to take turns merging into the open lane. In congested conditions, this helps reduce queue lengths approaching a lane closure, improving both safety and mobility.
Real-time ITS Message: Informative real time messages help drivers to react positively to changes occurring in traffic ahead and to make informed route choices. Clear and accurate information is the key to maintaining road user trust.
Queue Warning Systems: Systems to alert drivers of stopped traffic (queue) ahead.
Interaction: None
Notes: Photos by International Road Dynamics, Inc.

## Slide 36: TO Strategies Examples
Variable Speed Limit (VSL)
  Changes the speed limits in real time
Image: Virginia DOT
Notes: Key Message: discuss example
Background Information:
Variable speed limits, or VSL, technology is not often used in the U.S., but on large projects with significant duration, this may be a good tool to control traffic merging. In this example, the system was used successfully on the I-495 Woodrow Wilson Bridge Project in the Washington, D.C. area. VSL systems can help to maximize traffic flow and improve safety by slowing vehicles down gradually before they reach a lane reduction when there is congestion. This reduces the need for abrupt changes in speed and sudden braking, improving both safety and mobility.
Interaction: None
Notes: None

## Slide 37: Transportation Operation Strategies: 3. Work Zone Safety Management
Training and certification
Review and approval of TTC Plans
Positive protection
Innovative contracting
  Minimize worker exposure
Image: FHWA
Notes: Key Message: Discuss transportation operation strategies
Background Information:
Transportation operations strategies can mitigate work zone impacts by using improved transportation operations and management of the transportation system in and around the work zone. Strategies include demand management, where the strategies inform motorists to consider traveling another way, such as by transit or carpool, to reduce the volume of cars flowing through the work zone. This is particularly useful when the Agency is unable to provide the necessary capacity in a work zone.
Infrastructure or corridor management strategies are where the responsible Agency makes decisions that can affect the road user such as, signal re-timing, parking restrictions, and lane control.
Strategies specifically focused on safety include speed management, barrier installations, and temporary rumble strips.
The last category includes strategies that involve monitoring traffic conditions and making adjustments to traffic operations based on changing conditions. These strategies include more improved detection, verification, response, and clearance of crashes; adequate enforcement of traffic regulations in work zones; and the use of ITS and traffic management centers to monitor and manage traffic.
Interactivity: None
Notes: None

## Slide 38: TO Strategies: Innovative Contracting
Design – Build
  Accelerates process – work can begin as design is being completed
A + B Bidding
  Encourages reduced construction time
  Minimizes impacts
Lane Rental
  Charges assessed to contractor for lane closure
Incentive/Disincentive
  Encourages contractor to minimize construction time
Notes: Key Message: Discuss innovative contracting
Background Information:
In recent years, agencies have developed innovative contracting mechanisms that include operational strategies for accelerating the project timeline, minimizing impacts, and creating a link between the achievement of specific operational characteristics and incentive payments.
Interaction:
Notes: None

## Slide 39: Transportation Operation Strategies: 4. Traffic/Incident Management and Enforcement Strategies
ITS for traffic monitoring/management
Transportation Management Center
Travel time updates on project delays
Tow/freeway service patrol
Increased penalties for work zones
Dedicated police enforcement
Notes: Key Message: Discuss transportation operation strategies
Background Information:
Transportation operations strategies can mitigate work zone impacts by using improved transportation operations and management of the transportation system in and around the work zone. Strategies include demand management, where the strategies inform motorists to consider traveling another way, such as by transit or carpool, to reduce the volume of cars flowing through the work zone. This is particularly useful when the Agency is unable to provide the necessary capacity in a work zone.
Infrastructure or corridor management strategies are where the responsible Agency makes decisions that can affect the road user such as, signal re-timing, parking restrictions, and lane control.
Strategies specifically focused on safety include speed management, barrier installations, and temporary rumble strips.
The last category includes strategies that involve monitoring traffic conditions and making adjustments to traffic operations based on changing conditions. These strategies include more improved detection, verification, response, and clearance of crashes; adequate enforcement of traffic regulations in work zones; and the use of ITS and traffic management centers to monitor and manage traffic.
Interactivity: None
Notes: None

## Slide 40: TO Strategies Examples
Law Enforcement and Service Patrols-Incident Response
Images: FHWA
Notes: Key Message: Walk through example
Background Information:
In many work zone activities, capacity is reduced due to lane closures or even lane shifts or distractions from work activities. It can be helpful to have a service patrol to help remove disabled vehicles and restore capacity quickly. Law enforcement presence can increase the awareness of motorists and help manage traffic speeds.
In developing a TMP, incident response needs to considered. It is important to make the TMP
implementation team aware of the process and various roles and responsibilities in case of an accident.
Interaction: none
Notes: none

## Slide 41: Public Information and Outreach Strategies
Public awareness strategies include:
  Newsletters, brochures
  Press releases
  Mass media (earned or paid)
  Project web site
  Public meetings, workshops, community events
  Social media
Notes: Key Message: PI & O strategies can be broken down into public awareness strategies and driver awareness strategies.
Background Information:
The public information component in the TMP has the potential to reduce work zone impacts by providing both general and specific information concerning road projects. These strategies include public awareness strategies and motorist information strategies.
Public awareness strategies educate and reach out to the public, businesses, and the community and provide general information about a road project, the work zone, and travel options. Through public information and outreach campaigns, agencies can identify the concerns of stakeholder groups and created targeted messages to reassure them that their needs will be met during the construction period. The key is to engage the public early in the TMP development process, particularly affected neighborhoods and businesses, and keep them informed throughout the project.
Numerous approaches exist to provide the public with general information about a project.
These approaches include newsletters and brochures, press releases, the use of mass media advertising, project websites, meetings and community events, and social media. Regardless of medium, the key is accurate, timely, and consistent information. Coordination with your Agency's public information office will help to ensure success, particularly for significant projects.
Interaction:
Notes:

## Slide 42: PI & O Strategies
Motorist PI & O strategies include
  Radio traffic news
  PCMS
  Email alerts/social media outlets
  Highway advisory radio
  Trucking associations
Image: ATSSA
Notes: Key Message: PI & O strategies can be broken down into public awareness strategies and driver awareness strategies.
Background Information:
Motorist information strategies provide specific information that is current and possibly even real-time to road users regarding traffic conditions to expect. Motorist information is generally provided during a trip, after the road user is already in a vehicle. However, notices on social media, such as Facebook and Twitter feeds, can warn drivers about closures and anticipated delays before they begin their trips, allowing them to plan alternate routes or delay their planned trip.
Some motorist information strategies are shown here. Working with traffic reporters to provide near real-time information about lane closures and delays on radio traffic reports can be a good way to reach motorists already enroute in their cars. Changeable message signs and highway advisory radio allow the DOT to provide timely information about traffic conditions such as lane closures, queues, and delays, and can generally be updated by the DOT whenever needed. In areas with significant commercial vehicle traffic, the Agency should consider targeting some information to truckers, such as through a trucking association.
Interaction:
Notes:

## Slide 43: State Examples: Maryland SHA
Red Flag Summary
    Assists in determining any problem areas or issues
Work Zone Design Checklist
  Helps designers identify
    Traffic control options
    Work zone impacts, and
    TMP strategies
Notes: Key Message: Walk through state examples
Background Information:
A number of States have developed tools to assist their planners and designers in identifying impacts and selecting strategies to address those .
Maryland’s red flag summary assists in determining issues that are present and should be considered during project development.
Maryland’s work zone design checklist helps designers identify traffic control options, work zone impacts, and TMP strategies. It also helps ensure that all appropriate work zone options, impacts, and strategies have been considered.
California uses TMP data sheets to gather and summarize TMP-related information, including preliminary TMP strategies and costs. Caltrans prepares a data sheet for every project and includes a work description and available information about traffic patterns.
Tennessee DOT developed a TMP workbook to aid its staff in developing TMPs. The first part of the Workbook on Project Significance Determination is completed by the planning staff, and then the workbook is passed forward to designers to complete the sections on TMP strategies during project design.
Additional Information:
Notes:

## Slide 44: State Examples: Caltrans
TMP Data Sheets
    Used to gather and summarize TMP-related, including preliminary TMP strategies and costs
Notes: Key Message: Walk through state examples
Background Information:
A number of States have developed tools to assist their planners and designers in identifying impacts and selecting strategies to address those .
Maryland’s red flag summary assists in determining issues that are present and should be considered during project development.
Maryland’s work zone design checklist helps designers identify traffic control options, work zone impacts, and TMP strategies. It also helps ensure that all appropriate work zone options, impacts, and strategies have been considered.
California uses TMP data sheets to gather and summarize TMP-related information, including preliminary TMP strategies and costs. Caltrans prepares a data sheet for every project and includes a work description and available information about traffic patterns.
Tennessee DOT developed a TMP workbook to aid its staff in developing TMPs. The first part of the Workbook on Project Significance Determination is completed by the planning staff, and then the workbook is passed forward to designers to complete the sections on TMP strategies during project design.
Additional Information:
Notes:

## Slide 45: State Examples: MnDOT
Work Zone Impact Assessment Decision Tree
  Helps staff make decisions about appropriate level of TMP to develop based on the impacts assessment results
  Developed work zone impact considerations worksheet to use with the decision tree
Notes: Key Message: Walk through state examples
Background Information:
Minnesota DOT helps staff make decisions regarding the appropriate level of TMP to be developed depending on the work zone impacts through a series of steps. Each district or local road authority is encouraged to develop and implement a general traffic delay-restriction policy for its jurisdiction. Minnesota DOT also developed a work zone impact considerations worksheet to help identify project impacts and potential mitigation strategies.
Minnesota DOT’s toolbox provides guidance for selecting an appropriate intelligent work zone system to address work zone traffic issues. The toolbox contains illustrations of systems typically deployed.
Interaction: None
Notes: None

## Slide 46: State Examples: MnDOT
Intelligent Work Zone (IWZ) Toolbox
  Toolbox contains illustrations of IWZ systems that can be deployed
  Provides guidelines for selecting an appropriate system
Notes: Key Message:. Walk through state examples
Background Information:
Minnesota DOT helps staff make decisions regarding the appropriate level of TMP to be developed depending on the work zone impacts through a series of steps. Each district or local road authority is encouraged to develop and implement a general traffic delay-restriction policy for its jurisdiction. Minnesota DOT also developed a work zone impact considerations worksheet to help identify project impacts and potential mitigation strategies.
Minnesota DOT’s toolbox provides guidance for selecting an appropriate intelligent work zone system to address work zone traffic issues. The toolbox contains illustrations of systems typically deployed.
Interaction: None
Notes: None

## Slide 47: State Examples: MoDOT
TMP Strategy Database
  Suggests possible TMP strategies based on user inputs about the project
  Helps planners and designers select strategies and develop TMPs in a more systematic way
Notes: Key Message: walk through additional state examples
Background Information:
Missouri DOT developed a TMP Strategy Database that helps planners and designers select work zone management strategies and develop TMPs in a more systematic way. The database returns possible appropriate work zone management strategies based on user inputs about project-related characteristics. Construction personnel can use the program to find a solution should a concern arise while the work zone is in operation.
Tennessee DOT developed a TMP workbook to aid its staff in developing TMPs. The first part of the Workbook on Project Significance Determination is completed by the planning staff, and then the workbook is passed forward to designers to complete the sections on TMP strategies during project design.
Interaction: None
Notes: None

## Slide 48: MoDOT Customer Survey
Online feedback system
Allows users to provide comments so they can be contacted
Notes: Key Message: MoDOT Customer Survey
Background Information:
Missouri also has an only customer survey where users can leave comments and request to be contacted.
Interaction:
Notes: Language: MoDOT strives to provide excellent customer service. If you wish to be contacted with regards to any comments/questions you provide with this survey, please submit your phone number and/or email allowing a staff member to respond.
Additional Information: http://www.modot.org/workzones/Comments.htm and https://www.modot.org/work-zone-customer-survey

## Slide 49: State Examples: TDOT
TMP Workbook
  Helps guide and document TMP development
Notes: Key Message: walk through additional state examples
Background Information:
Missouri DOT developed a TMP Strategy Database that helps planners and designers select work zone management strategies and develop TMPs in a more systematic way. The database returns possible appropriate work zone management strategies based on user inputs about project-related characteristics. Construction personnel can use the program to find a solution should a concern arise while the work zone is in operation.
Tennessee DOT developed a TMP workbook to aid its staff in developing TMPs. The first part of the Workbook on Project Significance Determination is completed by the planning staff, and then the workbook is passed forward to designers to complete the sections on TMP strategies during project design.
Interaction: None
Notes: None

## Slide 50: Resources for Identifying Strategies
A list of TMP resources developed by both FHWA as well as several States is available at: https://ops.fhwa.dot.gov/wz/resources/final_rule/tmp_examples.htm
Work Zone Safety Information Clearinghouse TMP page: https://workzonesafety.org/topics-of-interest/transportation-management-plans/
Notes: Key Message: provide participants a place for additional resources
Background Information:
Interaction: None
Notes: None

## Slide 51: Questions
Notes: Key Message: Questions
Est. Presentation Time: Less than 1 minute(s)
Explanation of Cues/Builds: None
Suggested Comments: Let’s take your questions.
Suggested Questions: Any questions before we move to the next module?
Additional Information: None
Possible Problems: If no questions, you may want to ask your own.