## Slide 1: Developing and Implementing Transportation Management Plans
7. TMP Approval and Implementation
Image: ATSSA
Notes: Key Message: Title Slide
Background Information:
This module discusses TMP approval and activities during implementation of the TMP. As discussed in earlier modules, the TMP is a living document, and as construction progresses even the best design can change. Traffic conditions or other factors can also change, resulting in the need to adjust work zone management efforts. In cases where there are substantial changes to the TMP, these should be documented as an addendum to the TMP and signed-off by the DOT.
Interaction: N/A
Notes: None

## Slide 2: Objectives
TMP Review and Approval
TMP Implementation and Monitoring
TMP Revisions
Post-Project Evaluation
Notes: Key Message: Review module objectives
Background Information:
Module 7 covers TMP review and approval; TMP implementation and monitoring; TMP revisions; and post-project evaluation. Module 7 concludes with an exercise to help you apply what you have learned.
Interaction: N/A
Notes: None

## Slide 3: TMP Review
Includes suggestions/comments and feedback on TMP from TMP reviewer(s)
Can lead to solutions not identified earlier
Ensures consistency with DOT policy
Helps with TMP revision and performance monitoring
Can provide training and sharing of ideas for future projects
Notes: Key Message: Discuss TMP reviews and their purpose
Background Information: Having a step for TMP review by District managers or senior project managers generally leads to more effective TMPs. TMP review may include suggestions and comments from TMP reviewers that can lead to solutions not identified earlier. During TMP review, the reviewers can help make sure that the TMP is developed in accordance with Agency policy and guidelines, leading to greater consistency.
Review efforts may lead to TMP revisions, which can then be done before a project goes to bid, reducing the need for potentially costly changes later. The review process can also provide input to performance monitoring and future training.
Interaction: N/A
Notes: None

## Slide 4: TMP Approval
Similar to existing Agency procedures for approval of other plans (e.g., TTC Plan)
Based on what is written in each Agency’s work zone policy
Image: FHWA
Notes: Key Message: Approval process
Background Information: A TMP must be approved before implementation. The process for TMP approval can be similar to your Agency’s procedures for approval of other plans such as temporary traffic control plans. Most Agencies have the approval process documented in the formal work zone policy or in a procedures manual.
Interaction: N/A
Notes: None

## Slide 5: TMP Review and Approval – Examples
Oregon – by region
Montana – part of PS&E
California – just before project goes to bid
Maryland – district manager and PI Officer
Rhode Island – 3 sign offs before PS&E review
Notes: Key Message: Discuss review and approvals of TMP
Background Information: States have different review and approval processes for TMPs. Several States include TMP review and approval as part of the review process for the Plans, Specifications and Estimate (PS&E) package. Some States route the TMP for review separately, either in hardcopy or electronically. There are also variations across Agencies in who is required to review a TMP. A State needs to adopt a process that best suits its needs and achieves the goals of work zone safety and mobility.
Oregon – Each region has it own TMP review
Montana – TMP approval is conducted as part of the PS&E checklist
California – Signature line for TMP Manager is on project ready-to-list form so TMP is signed off just before project goes to bid
Maryland – District/relevant central office managers and Public information Officer sign off on TMP
Rhode Island – Requires Chief Engineer, State Traffic Engineer, and Traffic Management Chief (oversees the TMC) to sign TMP as part of PS&E review
Interaction: How does your state review and approve TMPs? Would any of the example above fit for this state?
Notes: None

## Slide 6: TMP Implemen-tation and Monitoring
Image: FHWA
Notes: Key Message: Cover Steps for TMP implementation and monitoring
Background Information: Once the TMP is approved and the project is awarded, there may be revisions to the TMP based on pre-construction coordination meetings or any alternate approaches proposed by the Contractor before implementation. Once implemented, the TMP strategies need to be monitored throughout construction and until official “handover” to ensure they are working as intended.
Interaction: N/A
Notes: None

## Slide 7: Pre-Construction Coordination
Partnering-agency and contractor work in joint, non-adversarial relationship
Value Engineering - systematic application of recognized techniques by multi-disciplined team
May lead to TMP Revisions
Resolve any pre-construction coordination issues
Notes: Key Message: discuss coordination prior to construction
Background Information: A pre-construction meeting provides an opportunity to get contractor input prior to construction. The two most common approaches used to facilitate Contractor participation are partnering and value engineering.
Partnering and value engineering can lead to suggestions for construction changes that can reduce work zone impacts or may increase them. In such cases the TMP may need to be revised and any substantial revisions must be approved by the Agency.
The pre-construction meeting can help resolve and pre-construction issues.
In some cases, components of the TMP may need to be implemented prior to construction (e.g., public relations campaign, improvements to detour routes, etc.).
Assessing proposed changes and revising the TMP are discussed later in this module.
Interaction: N/A
Notes: None

## Slide 8: Objectives During Construction
Implement the TMP
Actively monitor and manage the work zone during construction
Revise TMP and implement appropriate revisions, as needed
Document any findings, lessons learned for use in the future
Notes: Key Message: during construction phase
Background Information: The goals during construction include implementing the TMP and actively monitoring and managing the Work Zone. This includes revising and implementing appropriate revisions as needed and documenting any findings for lessons learned for use in future projects.
Interaction: N/A
Notes: None

## Slide 9: During Construction
Install TMP components (TTC, TO, and PI & O)
Inspection of TTC component
Observation/Measurement of TO component
Communication with public (PI & O component)
Consult with stakeholders
Notes: Key Message: Discuss TMPs during construction phase
Background Information: During construction the TMP components are installed, the TTC, TO and PI&O.
Other items include inspection of the TTC components, observation/measurement of To components and communication with the public , PI component. In many cases construction staff may have the lead in these activities along with keeping stakeholders informed.
Install TMP components (TTC, TO, and PI)
Inspection of TTC component
Observation/Measurement of TO component
Communication with public (PI component) - Construction staff may have lead in coordination and implementation of PI strategies
Consult with stakeholders to: Keep stakeholders informed, seek input on and knowledge of regional issues, improve inter-agency and intra-agency coordination and response to WZ issues
Interaction: N/A
Notes: None

## Slide 10: Trained Personnel
Federal WZ Safety and Mobility language - Requires the agency and the contractor designate a trained person at the project-level to implement the TMP and other safety and mobility aspects of the project.
Contractor – Certification required?
Agency
Notes: Key Message: Implementing the TMP during construction requires trained personnel.
Background Information: State and Local Transportation Agencies and the Contractor must have a trained person to implement the TMP. These designated responsible persons need to have primary responsibility for this duty and need to be regularly present at the job site so they can carry out this responsibility. The responsible persons for the Agency and Contractor should have “sufficient authority” to take action, should the work zone strategies be deemed ineffective
Interaction: N/A
Notes: None

## Slide 11: TCP Implementation- Setup
Setup Inspection
  Should be done initially and after each phase change
  Does plan address site conditions?
    Adequate sight distance
    Access provided to residences and businesses
    Roadside appurtenances
Notes: Key Message: Discuss TCP implementation
Background Information: One of the first things in implementing the TCP in the field before construction can begin is the traffic control setup. The setup inspection should be done initially and after each phase change. The overall function of the TCP should be checked to see if the plan addresses actual site conditions, looking to see if adequate sight distance has been provided, access to residences and businesses are adequate or per plan, and if roadside appurtenances have been protected. The locations of devices should be adjusted as needed and additional devices or traffic control measures added.
Many states have a checklist to help remind inspectors of items to check during their inspection. It includes those items already mentioned.
The setup Inspection:
Should be done initially and after each phase change
  Does plan address site conditions? Adequate sight distance, Adjust location of devices, Additional measures needed, Access provided to residences and businesses, Are Roadside appurtenances protected?
Interaction: N/A
Notes: None

## Slide 12: TCP Implementation – Inspection
Initial Setup
Drive through
  Positive guidance
  Hazards delineated
  Appropriate sign messages
  PCMS messages reflect current conditions
  Others?
Image: ATSSA
Notes: Key Message: Inspect TCP after installed
Background Information: After the initial TCP setup the project should be driven through to see if positive guidance has been provided, hazards have been delineated, and signing is appropriate.
Interaction: Is the signing appropriate in this picture?
Notes: None

## Slide 13: Inspection Areas
Temporary Concrete Barrier (TCB)
  Barrier End Treatments
Delineation (incl. Pavement Markings)
Clearances
Excavation & Drop-Offs
Ramps (Entrance & Exit)
Speed Limit Enforcement
Nighttime Work
Notes: Key Message: review some potential implementation issues
Background Information: This slide provides a list (although not all inclusive) of various items that should be considered during the implementation of the TCP.
Temporary Concrete Barrier (TCB)-Barrier End Treatments
Delineation (incl. Pavement Markings)
Clearances
Excavation & Drop-Offs
Ramps (Entrance & Exit)
Speed Limit Enforcement
Nighttime Work
Worker Protective Equipment
Pedestrian pathways established -ADA compliant
The following slides show photos of some “poor” examples of traffic control that would illustrate some of the implementation issues listed.
Interaction: N/A
Notes: None

## Slide 14: Delineation in Work Zones
From MUTCD Part 6:
“Adequate warning, delineation, and channelization should be provided to assist in guiding road users in advance of and through the TTC zone...”
Notes: Key message: Review language in MUTCD
Background information:
From 2009 MUTCD Part 6B.01 (Page 6B-2)
Motorists, bicyclists, and pedestrians should be guided in a clear and positive manner while approaching and traversing TTC zones and incident sites. The following principles should be applied:
Adequate warning, delineation, and channelization should be provided to assist in guiding road users in advance of and through the TTC zone or incident site by using proper pavement marking, signing, or other devices that are effective under varying conditions. Providing information that is in usable formats by pedestrians with visual disabilities should also be considered.
TTC devices inconsistent with intended travel paths through TTC zones should be removed or covered. However, in intermediate-term stationary, short-term, and mobile operations, where visible permanent devices are inconsistent with intended travel paths, devices that highlight or emphasize the appropriate path should be used. Providing traffic control devices that are accessible to and usable by pedestrians with disabilities should be considered.
C. Flagging procedures, when used, should provide positive guidance to road users traversing the TTC zone.
Interaction: N/A
Notes: None

## Slide 15: Adequate Delineation?
Image: ATSSA
Notes: Key Message: Review Example
Background Information: You can see the drop off during the daytime, but could you see it at night?
Interaction: What would you do to make it better?
Notes: None

## Slide 16: TCP Implementation Issues
PCMS
  Appropriate Messages
  Reflect current conditions
Static Signing
  Visible
  Breakaway supports
Notes: Key Message: review project signs
Background Information: Signs should have correct message and be installed properly.
Interaction: N/A
Notes: None

## Slide 17: Pavement Markings & Replacement
From MUTCD Part 6:
“Pavement marking obliteration shall remove the non-applicable pavement marking material, and the obliteration method shall minimize pavement scarring. Painting over existing pavement markings with black paint or spraying with asphalt shall not be accepted as a substitute for removal or obliteration.”
Notes: Key Message: review pavement marking removal and temporary placement
Background Information: Based on the MUTCD, conflicting pavement marking should be removed, and the removal process should minimize scarring of the pavement. Painting over is not acceptable.
Need to investigate better methods of removing striping
Interaction: Has anyone actually used painting to cover up markings?
Notes: None

## Slide 18: Pavement Example
Image: ATSSA
Notes: Key Message: Pavement marking example
Background Information: Need to investigate better methods for removing or covering inappropriate pavement markings.
Interaction: N/A
Notes: None

## Slide 19: Barrier End Treatments
Must be installed according to manufacturer’s instructions, as well as in compliance with crash test conditions
Image: ATSSA
Notes: Key Message: Introduce barrier end treatments
Background Information: The ends of temporary concrete barrier should be protected by an acceptable end treatment or placed outside the clear zone.
Interaction: N/A
Notes: None

## Slide 20: Barrier End Treatment- Example
Image: ATSSA
Notes: Key Message: Example of impact attenuator sand barrel array
Background Information: Impact attenuator sand barrel array protecting a blunt end of the temporary concrete barrier.
Ned to be installed correctly and designed for the proper speed and application.
Interaction: N/A
Notes: None

## Slide 21: Flagging Operations
Trained – certification?
Properly located for adequate sight distance?
Devices and apparel appropriate?
Proper procedures
  Facing traffic
  Eye contact
  Supplemental hand signals
Image: ATSSA
Notes: Key Message: discuss flagging operations
Background Information: Flagging operations should be done properly. What type of training or certification is required by your state? Some of the things to consider are: is the flagger properly located, are proper devices being used and does he have appropriate apparel? Are proper procedures being followed.
Interaction: N/A
Notes: None

## Slide 22: Flaggers – Properly trained?
Image: ATSSA
Notes: Key Message: training is key
Background Information: What is wrong with this situation?
Flagger not holding the sign, leaning on a car parked within the operation.
Interaction: N/A
Notes: None

## Slide 23: A quick reminder of proper procedures….
Image: ATSSA
Notes: Key Message:
Background Information: The flagger is to stop, slow and release traffic.
Interaction: N/A
Notes: None

## Slide 24: Construction Operations
Sequencing of the operations
  As planned?
  Adjustments to TTC required?
Edge Drop-offs
  State policy?
  Engineering judgment?
  Positive protection required?
Notes: Key Message: Discuss things to consider on construction operations
Background Information: Has the sequencing of the work been planned properly. Do drop-offs meet policy are should they be protected.
Interaction: N/A
Notes: None

## Slide 25: Drop-off Policy Example
DO | Treatment
Less than 2” | May use LOW SHOULDER sign
2”- 5” | Shall use SHOULDER DROPOFF sign OR
2”- 5” | 6:1 wedge desirable 4:1 wedge minimum No signs required
5” – 12” | 6:1 wedge desirable 4:1 wedge minimum Group 2 devices required
> 12” | Group 2 devices and wedge Consider temporary barrier
Source: Virginia Work Area Protection Manual
Notes: Key Message: Example a drop-off policy
Background Information: A drop-off condition created and restored within the same work period is usually not be subject to the use of barriers, however, Group 2 devices are required (WAPM A-4)
The SHOULDER DROP OFF sign may be eliminated if a 6:1 (desirable) to 4:1 (minimum) wedge is used between the travel lane and the shoulder (WAPM 6H-120)
Interaction: N/A
Notes: Virginia specific and not required in every state. Use as an example.

## Slide 26: Ramps (Entrances & Exits)
Image: FHWA
Notes: Key Message: review ramp plan
Background Information: Ramp entrances and exits require special consideration and should be designed to provide adequate room for merging and exiting.
Interaction: N/A
Notes: None

## Slide 27: Ramp Entrance- Example
Image: ATSSA
Notes: Key Message: review picture
Background Information: This entrance actually looks fairly good.
Interaction: N/A
Notes: None

## Slide 28: Braking Marks due to Exit- Example
Image: ATSSA
Notes: Key Message: Review picture
Background Information: This picture indicates considerable braking due to vehicles having to slow down at a ramp exit up ahead.
Interaction: Discuss ways to improve this exit to improve safety
Notes: None

## Slide 29: Pedestrian Accommodations
All road users must be accommodated
  Maintain pathway or provide pedestrian detour
ADA requirements
  Longitudinal channelizing devices
  No tape, rope, or plastic chain
Image: FHWA
Notes: Key Message: Introduce pedestrian accommodations
Background Information: If there are pedestrian accommodations prior to construction they should be provided for during construction. Temporary facilities, including pedestrian routes around worksites, are also covered by the accessibility requirements of the Americans with Disabilities Act of 1990 (ADA) (Public Law 101-336, 104 Stat. 327, July 26, 1990. 42 U.S.C. 12101-12213 (as amended)).
Interaction: N/A
Notes: MUTCD 6D. A smooth, continuous hard surface should be provided throughout the entire length of the temporary pedestrian facility. There should be no curbs or abrupt changes in grade or terrain that could cause tripping or be a barrier to wheelchair use. The geometry and alignment of the facility should meet the applicable requirements of the “Americans with Disabilities Act Accessibility Guidelines for Buildings and Facilities (ADAAG)” (see Section 1A.11).
Tape, rope, or plastic chain strung between devices are not detectable, do not comply with the design standards in the “Americans with Disabilities Act Accessibility Guidelines for Buildings and Facilities (ADAAG)” (see Section 1A.11), and should not be used as a control for pedestrian movements. In general, pedestrian routes should be preserved in urban and commercial suburban areas. Alternative routing should be discouraged. The highway agency in charge of the TTC zone should regularly inspect the activity area so that effective pedestrian TTC is maintained.

## Slide 30: Channelizing Pedestrians
Devices used to channelize pedestrians shall be detectable to users of long canes and visible to persons having low vision
Continuous detectable edging
Detectable?
Image: ATSSA
Notes: Key Message: Discuss the use of cones and visually impaired persons
Est. Presentation Time: 1-2 minute(s)
Explanation of Cues/Builds: None
Suggested Comments: Cones should not be used for pedestrian channelization or as pedestrian barriers in TTC zones on or along sidewalks unless they are continuous between individual devices and detectable to users of long canes. Yellow caution tape is not acceptable.
Suggested Questions: Can a blind person walk in between cones and unknowingly enter a work zone? Yes! We need detectable perimeters or cones that are very close together.
Additional Information: Photo source unknown
Possible Problems: Avoid getting into an ADA discussion here. Not within the scope of this course.

## Slide 31
Longitudinal
Channelizing Devices (LCDs) provide a continuous detectable edge
(but no protection!)
Image: ATSSA
Notes: Key Message: Provide an example of the previous point.
Est. Presentation Time: Less than 1 minute(s)
Explanation of Cues/Builds: None
Suggested Comments: Longitudinal Channelizing Devices (LCDs) provide a continuous detectable edge (but no protection!). There are there to provide “ADA” detectability.
Suggested Questions: What would happen if a vehicle impacts these LCDs?
Additional Information: None
Possible Problems: None

## Slide 32: Pedestrian Pathway Maintained?
Images: ATSSA
Notes: Key Message: briefly discuss a couple of examples
Background Information: Maintain access and pedestrian accessibility.
Interaction: N/A
Notes: None

## Slide 33: Maintenance of Devices (1 of 3)
Routine (Daily) Inspections
  During working hours
  After work has stopped
    Last duty of inspector before leaving the project site – drive through and be sure devices are in proper location
    Devices often moved for contractor access during working hours
Notes: Key Message: Review when to inspection and maintain devices
Background Information: Traffic control devices should be routinely inspected to insure the devices are in the proper location during work hours and after working hours.
Interaction: N/A
Notes: None

## Slide 34: Maintenance of Devices (2 of 3)
Payment for maintenance
  Clearly establish basis in contract specifications
    Included in pay item
    Separate for some items
      Surveillance?
      Attenuator maintenance?
Notes: Key Message: maintenance of devices continued
Background Information: Payment for maintenance of devices has to be clearly established in the contract specifications either by pay item, or included in other items. Some items may require separate payment in order to keep them maintained.
Interaction: N/A
Notes: None

## Slide 35: Maintenance of Devices (3 of 3)
23 CFR 630 Subpart K requires adoption of quality standards guidelines
Training for Inspectors
Quality of devices maintained
Image: ATSSA
Notes: Key Message: introduce quality standard guidelines
Background Information: Most states have adopted or have Quality Standards for traffic control devices. ATSSA has a guide that has been adopted by several states.
Interaction: N/A
Notes: None

## Slide 36: Quality Standards
Guidelines for determining the acceptability of a traffic control device
  Acceptable
  Marginal
  Unacceptable
Some states have developed guidelines or adopted those of ATSSA
Image: ATSSA
Notes: Key Message: Discuss quality standards
Background Information: Quality standards provide guidelines for the acceptability of traffic control devices.
Quality Guideline booklets assists contractors and agency personnel to determine when a traffic control device has outlived its usefulness by illustrating three levels of device conditions: acceptable, marginal, and unacceptable. The guideline describes devices such as signs, barricades, drums, cones tubes, warning lights, arrow panels, changeable message signs, and markers. The guideline normally provide pictures of acceptable, marginal and unacceptable devices.
ACCEPTABLE: Devices that meet the quality requirements such as design, size, color, weight, etc. in the plans and specifications, shall be considered to be acceptable for use on highway construction or contract maintenance projects.
MARGINAL: Devices that meet the quality criteria for marginal may remain in the work zone until their number exceeds the specified percentage of that type of device or until it is determined that they have become unacceptable.
UNACCEPTABLE: Devices in the unacceptable category shall not be delivered to the jobsite. When found in the work zone, they shall be replaced or repaired within 12 hours of notification or as contained in the contract specifications.
Interaction: N/A
Notes: None

## Slide 37: Traffic Operation Implementation
Alternate routes
Emergency vehicle access to work area or through project
Speed control measures
Coordination with other projects in corridor
Queuing
Image: ATSSA
Notes: Key Message: review traffic operation around and through work zone
Background Information: We will now look at traffic operations implementation. The implementation of various traffic operations should be considered which include strategies to encourage the use of alternate routes and check if they are working.
Some items may require checking once traffic control has been installed while others could require frequent checking during the project to see if new or different issues have developed.
The alternate routes should also be looked at to see if there are operational issues.
Alternate routes: Are the implemented strategies to encourage use working? Operational issues on alternate routes?
Emergency vehicle access should be available through the project.
Are work zone Speed Control measures working? Are there coordination issues with other projects in the corridor and is Queuing an issue?
We will now look at some of these items in more detail.
Interaction: N/A
Notes: None

## Slide 38: Traffic Operation Implementation
Work zone ITS
  Systems installed properly and calibrated to provide accurate information?
  PCMS messages legible and accurate?
  Dynamic Merge System applied properly?
  Loss of device credibility?
Image: FHWA
Notes: Key Message: discuss other elements to traffic operations
Background Information: Work zone ITS systems should be checked frequently to see that they are working properly. Are PCMS messages legible and accurate? Is the Dynamic Merge System working as it should and then is there a loss of credibility of any devices?
Interaction: N/A
Notes: None

## Slide 39: Speed Control Measures
Signing
  Placement and maintenance of signs
  Remove conflicting signs
Law enforcement officers
  Involve in planning and preconstruction
  Jobsite involvement
    Active enforcement
    Presence
    Not in buffer space
Notes: Key Message: discuss speed control measures
Background Information: Speed control measures such as signing should be placed and maintained properly throughout the work zone with existing or any conflicting speed limit signs covered or removed. If law enforcement is going to be used in the work zone they should be involved in the planning and preconstruction meetings and their involvement as to active enforcement or presence should be clear to all. Officers should not be in the buffer space but rather in the advance warning area.
Interaction: N/A
Notes: None

## Slide 40: Work Zone Speed Limit
Image: ATSSA
Notes: Key Message: Example reduced speed limit trailer and feedback signing
Background Information: Placement and use of speed limit signs should be in accordance with standards.
Interaction: N/A
Notes: None

## Slide 41: Location of Law Enforcement
Image: ATSSA
Notes: Key Message: Location of Law Enforcement
Background Information: The location of law enforcement should be in a proper location to be effective. The preferred location is on the shoulder in the advance warning area
Interaction: Where should law enforcement be placed?
Notes: None

## Slide 42: PI&O Implementation
Coordination with local media
  News releases
  Interviews with project personnel
Printed materials distributed
Website updated
Feedback from public
Image: FHWA
Notes: Key Message: discuss ways to coordinate with the public
Background Information: Depending on the project and the amount of disruption to the traveling public much of the public information campaign may have already been implemented once the actual project is begins. But any coordination with media, new releases such as interviews with project personnel, regarding the project should be done. Any printed material concerning the project regarding delays, alternate routes and duration should be available and have been distribute distributed, website and other systems such as social media should be updated to provide motorist with current information.
Interaction: N/A
Notes: None

## Slide 43: The TMP is implemented Now what?
Our work is not done
All the TMP efforts culminate in one thing:
  How does the TMP work in the field?
    Are conditions as expected?
    Do major issues arise?
    Are there many complaints?
    Minimize impacts?
Notes: Key Message: Discuss what to do after implementation
Background Information: All the efforts of WZ planning, impacts assessment, coordination, design, and TMP development culminate in one thing:
How does the TMP work in the field?
  Are conditions as expected?
  Do major issues arise?
  Are there many complaints or “bad press”?
Interaction: N/A
Notes: None

## Slide 44: Did I expect this? 
But instead got this?

Images: ATSSA
Notes: Key Message: Did I get the results I expected
Background Information: Significant work zone queues happen, and extra crashes often come with the back-ups. Realistically, we cannot avoid every back-up or congestion - even with excellent project planning.
But we do need manage them and possibly mitigate them when they happen, and learn what we can to do the most knowledgeable planning we can next time.
Interaction: N/A
Notes: None

## Slide 45: How did this happen to my project?
Image: ATSSA
Notes: Key Message: review picture
Background Information: This picture is just reiterating the fact the results of a TMP are not what we expected.
Interaction: N/A
Notes: None

## Slide 46: How is the TMP working?
Great >>>> No changes are needed
Poorly>>>>
  What went wrong?
  Can we fix it?
  If not, what can we do?
Ok>>>>Some tweaks might be needed
What can we learn for next time?
Notes: Key Message: Is it working?
Background Information: Now we will look at monitoring the TMP. Did the plan work, what went wrong and if not what can be done to fix it and then what lessons have we learned for the future?
In this step, work zone safety and mobility are monitored and/or measured to determine how well the TMP and the work zone are performing. Once construction begins, it is the responsibility of the agency, construction management team, and/or the contractor team to monitor and/or measure the actual work zone impacts of the project. They determine if the actual impacts comply with agency policies, fall within a reasonable range of what was anticipated and whether the impacts meet the desired level of safety and mobility performance for that work zone.
Interaction: N/A
Notes: None

## Slide 47: Monitoring TMP performance helps to:
Assess predicted impacts
Gauge effectiveness
Document changes and event occurrences
Determine TMP revisions
Protect against litigation
Determine elements to include/correct in future TMPs
Notes: Key Message: Why TMPs should be monitored
Background Information: The benefits of TMP monitoring and good documentation cannot be overstated. They not only allow you to improve performance over time, but can protect you from unwarranted litigation. Monitoring helps in identifying when adjustments are needed to the TMP strategies deployed on the current project. Monitoring also helps with determining what strategies work well, under what conditions and any lessons learned to avoid similar mistakes in the future.
Monitoring TMP performance helps to:
Assess whether predicted impacts closely resemble actual field conditions
Gauge effectiveness of TMP strategies in managing impacts
Document changes and event occurrences during construction
Determine TMP revisions
Protect against litigation
Determine elements to include/correct in future TMPs
Interaction: N/A
Notes: None

## Slide 48: What should TMPs monitor?
Recurring congestion
Crashes
Community and environmental impacts
Combined issues/impacts with nearby concurrent projects
TTC Maintenance
Compliance with contract requirements
Notes: Key Message: What should TMPs monitor?
Background Information: Monitoring TMP implementation is important to ensure Contractor compliance with all requirements. The requirements are stipulated to ensure that the work zone is safe and there is minimal interruption of traffic. It is the responsibility of the DOT to provide oversight of the Contractor to ensure compliance with all DOT rules and regulations. It is the responsibility of the Contractor to ensure that they comply with the DOT requirements and to the best extent possible provide a safe and efficient work zone.
The DOT needs to monitor for recurring congestion exceeding the Agency’s policy.
This can be in the form of travel time, queue length, or any other performance measures set forth in the Agency policy.
Impacts could be due to the project work zone itself or due to the combined impact of other projects nearby. To ensure compliance, the project site must also be monitored for safety, and any deficiencies noted. Personnel should make a note of any crashes that occur within the construction limits and regularly inspect temporary traffic control devices for placement and visibility.
Interaction: N/A
Notes: None

## Slide 49: How to Monitor
Field observations
Floating car studies
ITS –detectors, sensors
Traffic management centers (TMCs)
Record/diary logs
Public feedback/complaints
Crash investigations
Construction and safety inspections
Notes: Key Message: How to monitor
Background Information:
Methods that can be used to monitor the conditions of a work zone include field observations, such as recording traffic control devices that have been regularly knocked over, or queue length and when queues form and dissipate. Sampling using floating car studies, particularly during peak traffic periods, can provide insight on TMP performance. The use of technology, such as permanent or temporary detectors and cameras, can provide real-time measurement of performance and a rich source of data for post-project assessment. Traffic management centers, where available, can be helpful in monitoring.
Diary logs of project events and incidents such as crashes and queue spillover, as well as public feedback or complaints, aid in monitoring both during the project and in performance assessment at the project end. The results of inspections and crash investigations also provide information about performance.
The next few slides provide some examples of state practices that may be beneficial to this state.
Interaction: N/A
Notes: None

## Slide 50: Ohio Work Zone Crash Data Analysis
Image: Ohio DOT
Notes: Key Message: review Ohio example
Background Information:
Ohio DOT breaks a sample of work zones into half-mile segments, sorts crashes into their proper segment, and performs a before-after comparison of the preconstruction and construction crash frequencies for each segment. In this example, preconstruction crash data show that there were an average of 31 crashes for 7 months, or 4.4 crashes per month.
During construction, data gathered every two weeks showed crashes increased significantly to 48 in three months, an average of 16 per month. In such cases, Ohio DOT does a review to determine the contributing circumstances and mitigation treatments to address the issue.
Interaction: Ask participants if they use this practice. Would this work in their state? Create a discussion of how to incorporate into their process.
Notes: None

## Slide 51: Rhode Island DOT Monitoring Example
Require construction staff to document all monitoring activities
    Made this clear during training sessions for construction staff
Line item in contracts requiring the contractor to monitor TMP implementation
Notes: Key Message: Review RIDOT example
Background Information:
RIDOT requires construction staff to document all monitoring activities and has made this clear during training sessions for construction staff. In addition, RIDOT occasionally includes a line item in their contracts requiring the contractor to monitor TMP implementation.
RIDOT has developed a specific set of performance monitoring TMP strategies and includes a post-construction work zone performance assessment section in their TMP template that is to be completed by the RIDOT TMP Implementation Manager upon completion of the work to document lessons learned and provide recommendations on how to improve the TMP process and/or modify guidelines.
Require construction staff to document all monitoring activities
  Made clear during training sessions for construction staff
Occasionally include a line item in contracts requiring contractor to monitor TMP implementation
Developed set of performance monitoring TMP strategies
Include post-construction WZ performance assessment section in their TMP template
  Completed by RIDOT TMP Implementation Manager
  Document lessons learned
  Provide recommendations on how to improve the TMP process and/or modify guidelines
Interaction: Ask participants if they use this practice. Would this work in their state? Create a discussion of how to incorporate into their process.
Notes: None

## Slide 52: Rhode Island DOT Monitoring Example (cont.)
Developed set of TMP performance strategies
Include post-construction assessment their TMP template
    Completed by the RIDOT TMP Implementation Manager
    Documents lessons learned
    Provides recommendations on how to improve the TMP process and/or modify guidelines
Notes: Key Message: Review RIDOT example
Background Information:
RIDOT requires construction staff to document all monitoring activities and has made this clear during training sessions for construction staff. In addition, RIDOT occasionally includes a line item in their contracts requiring the contractor to monitor TMP implementation.
RIDOT has developed a specific set of performance monitoring TMP strategies and includes a post-construction work zone performance assessment section in their TMP template that is to be completed by the RIDOT TMP Implementation Manager upon completion of the work to document lessons learned and provide recommendations on how to improve the TMP process and/or modify guidelines.
Require construction staff to document all monitoring activities
  Made clear during training sessions for construction staff
Occasionally include a line item in contracts requiring contractor to monitor TMP implementation
Developed set of performance monitoring TMP strategies
Include post-construction WZ performance assessment section in their TMP template
  Completed by RIDOT TMP Implementation Manager
  Document lessons learned
  Provide recommendations on how to improve the TMP process and/or modify guidelines
Interaction: Ask participants if they use this practice. Would this work in their state? Create a discussion of how to incorporate into their process.
Notes: None

## Slide 53: Post-Project Evaluation
TMP Monitoring/Revisions (project level)
Post Project Evaluation (project level)
Process Review (agency-wide)
Notes: Key Message: discuss post-project evaluation
Background Information:
The findings from TMP Monitoring and any TMP changes, as well as any post project evaluations done, should be recorded. Some Agencies prepare an evaluation report at the completion of significant projects. These records can help the Agency better develop TMPs in the future.
The results of TMP evaluations from several projects across the State or at the District level are useful while doing a Process Review. A process review is required every 2 years by the Work Zone Safety and Mobility Rule and is intended to help improve work zone policy and procedures, including TMP development and implementation.
Interaction: N/A
Notes: None

## Slide 54
Image: FHWA
Notes: Key Message: discuss post-project evaluation
Background Information:
The findings from TMP Monitoring and any TMP changes, as well as any post project evaluations done, should be recorded. Some Agencies prepare an evaluation report at the completion of significant projects. These records can help the Agency better develop TMPs in the future.
The results of TMP evaluations from several projects across the State or at the District level are useful while doing a Process Review. A process review is required every 2 years by the Work Zone Safety and Mobility Rule and is intended to help improve work zone policy and procedures, including TMP development and implementation.
Interaction: N/A
Notes: None

## Slide 55: Post-Project Evaluation: Elements to consider
Overall statement reflecting TMP usefulness
Areas of TMP effectiveness
Changes to original TMP and results of those changes
Public reaction to the results of the TMP
Lessons learned
Notes: Key Message: Continue discussing post-project evaluation
Background Information:
The main emphasis of post-project evaluation is to note what worked well and what did not. In addition to an overall assessment of how well the TMP worked, it is helpful to make notes about which TMP strategies worked well based on monitoring results and the reaction from the public and other stakeholders. Notes about TMP changes made, how effective they were, and whether the process worked smoothly are also a good idea. Sometimes the most useful information to future TMP developers is lessons learned.
Interaction: N/A
Notes: None

## Slide 56: Document Performance Findings
Summary of the following information:
  Compare actual impacts versus the impacts
  Effectiveness of TMP and management strategies
  Best practices
  Lessons learned
  Recommendations for policy or procedural change
Notes: Key message: Documentation of findings
Background information: This step involves the documentation of the findings of the work zone impacts monitoring process. This documentation should be done throughout the course of the project construction phase. If possible, after the project is complete, this information should be summarized to document:
A comparison of the actual work zone impacts versus the anticipated work zone impacts of the project.
The effectiveness of the implemented TMP and its constituent management strategies.
Best practices.
Innovative approaches/techniques/technologies used on the project.
Lessons learned and mistakes to avoid.
Any recommendations for policy or procedural change.
Such performance documentation, if performed at the individual project-level, supports the assessment of work zone performance on a large scale (regional/district level, agency-level, State-level, etc.). Information for project-level assessments provides the basis for conducting overall agency work zone performance assessment (discussed in Section 8.0 of this document).
Interactivity: None
Notes: None

## Slide 57: Post-Project Evaluation Example: Michigan (MDOT)
Crash data analysis
Mobility performance analysis
  Travel time runs
  Portable trailers with sensors
  Compiled into regional and Statewide measures
Notes: Key Message: review Michigan example
Background Information:
Michigan DOT measures work zone performance, specifically in the areas of work zone crashes and travel time. Crash data is retrieved through the Transportation Management System (TMS) database. Performance can be presented as total numbers of crashes as well as a detailed breakdown of crashes on a project-by-project basis. Travel time is determined through various methods such as real-time measurement of vehicle speeds and occupancy using portable trailers with sensors that are rotated between work zones.
Michigan DOT also uses co-op assistance from students for data collection, such as driving through work zones to measure queues and record delay time. Michigan DOT combines the project mobility data into regional and Statewide measures of the percent of its work zones meeting mobility goals.
Interaction: N/A
Notes: None

## Slide 58: Exercise
Project Description
  Replacement Structures – both EB and WB carrying mainline I-44 over Winsel Creek near Sullivan
    Structures are twin 178’ single span
    2 - 12’ travel lanes
    10’ outside shoulder
    6’ inside shoulder
    40’ median
Notes: Key Message: Discuss and review exercise
Background Information: Read the exercise, please answer the questions on this slide.
Interaction: Interact with participants and start discussion on answers to questions.
Notes: None

## Slide 59: I-44 over Winsel Cr. - Sullivan
Image: Google Maps
Notes: Key Message: Discuss and review exercise
Background Information: Read the exercise, please answer the questions on this slide.
Interaction: Interact with participants and start discussion on answers to questions.
Notes: None

## Slide 60: I-44 over Winsel Cr. - Sullivan
Interchange B
Interchange A
Project Location
Image: Google Maps
Notes: Key Message: Discuss and review exercise
Background Information: Read the exercise, please answer the questions on this slide.
Interaction: Interact with participants and start discussion on answers to questions.
Notes: None

## Slide 61: I-44 over Winsel Cr. – Project Location
Image: Google Maps
Notes: Key Message: Discuss and review exercise
Background Information: Read the exercise, please answer the questions on this slide.
Interaction: Interact with participants and start discussion on answers to questions.
Notes: None

## Slide 62: Interstate-44 Winsel Creek Area
4-lane divided highway – 2 lanes in each direction
I -44 ADT – 44,000 vpd – peak during summer months – Peak daily volumes on Fridays
  35% Trucks
  High % of recreation vehicles
2-way ADT – 4,500 vpd on each frontage road
5% grade both directions from structure
Posted Speed Limit – 70 MPH
Notes: Key Message: Discuss and review exercise
Background Information: Read the exercise, please answer the questions on this slide.
Interaction: Interact with participants and start discussion on answers to questions.
Notes: None

## Slide 63: Project Environment
30 minutes from St. Louis metro area – an hour to downtown
Major truck route for freight from South and West
Local manufacturing – supply for major factories in St. Louis metro
Major route for recreational travelers
  Lake of the Ozarks
  Campgrounds
  High weekend volumes
Notes: Key Message: Discuss and review exercise
Background Information: Read the exercise, please answer the questions on this slide.
Interaction: Interact with participants and start discussion on answers to questions.
Notes: None

## Slide 64: Part 1: Impacts and Alternatives
Assess impacts (non-quantitative)
  Significant project?
    Why or why not?
Identify stakeholders
Identify and evaluate alternative strategies
  Contract options
  Construction options
  Traffic management options
Notes: Key Message: Discuss and review exercise
Background Information: Read the exercise, please answer the questions on this slide.
Interaction: Interact with participants and start discussion on answers to questions.
Notes: None

## Slide 65: Part 2: TMP Development
Components of the TMP:
  Based on anticipated impacts and roadway characteristics – determine what components the TMP should contain
Notes: Key Message: Discuss and review exercise
Background Information: Read the exercise, please answer the questions on this slide.
Interaction: Interact with participants and start discussion on answers to questions.
Notes: None

## Slide 66: Questions
Notes: Key Message: Questions
Est. Presentation Time: Less than 1 minute(s)
Explanation of Cues/Builds: None
Suggested Comments: Let’s take your questions.
Suggested Questions: Any questions before we move to the next module?
Additional Information: None
Possible Problems: If no questions, you may want to ask your own.

## Slide 67: Developing and Implementing Transportation Management Plans
Closing and Exam
Image: ATSSA
Notes: Key Message: Title Slide
Background Information:
This module discusses TMP approval and activities during implementation of the TMP. As discussed in earlier modules, the TMP is a living document, and as construction progresses even the best design can change. Traffic conditions or other factors can also change, resulting in the need to adjust work zone management efforts. In cases where there are substantial changes to the TMP, these should be documented as an addendum to the TMP and signed-off by the DOT.
Interaction: N/A
Notes: None

## Slide 68: Course Objectives
Explain the TMP basics
Identify why TMPs are important
Apply impact assessment findings into the TMP
List TMP strategies
Identify key stakeholders for TMP coordination
Explain how to implement and monitor TMPs
Notes: Key Message: Outline what students will know or be able to do upon completing this course.
Background Information:
Upon completing this course, students will understand the process for developing, implementing, and monitoring TMPs.
The primary intended audience for this training is transportation agency staff, including technical staff, (planners, designers, traffic engineers, highway/safety engineers, etc); management and executive-level staff responsible for setting policy and program direction; field staff responsible for building projects and managing work zones; and staff responsible for assessing performance in these areas.
Interaction: None.
Notes: None.

## Slide 69: Course Contents
Module 2: Work Zone Safety and Mobility Rule
Module 3: TMP Basics
Module 4: TMP Coordination
Module 5: Work Zone Impacts Assessment
Module 6: TMP Strategies
Module 7: TMP Approval and Implementation
Wrap-Up: General exercise and post course
assessment.
Notes: Key Message: Outline course contents
Background Information:
In Module 2: Work Zone Safety and Mobility Rule—we’ll talk about the Rule and its provisions, specifically as they pertain to the TMP process. We’ll also look at various states “work zone safety and mobility polices” and available resources regarding TMP’s.
Moving on to Module 3: TMP Basics—we’ll discuss what a TMP is and why it’s needed, give an overview of the TMP process including the potential steps to be included in the TMP.
In Module 4: TMP Coordination (includes exercise)—we’ll talk about the appropriate level of coordination during the TMP development and implementation process, stakeholders that should be involved during coordination, coordination issues that need to be considered, and ways to achieve coordination while developing TMPs.
In Module 5: Work Zone Impacts Assessment (includes exercise)—we’ll look at work zone impacts assessment, the types of impacts to be concerned with, why and when to assess impacts, and a process that can be used to assess work zone impacts.
In Module 6: TMP Strategies (includes exercise)—we’ll talk about how to identify TMP Strategies and examples of possible TMP strategies.
Finally, for Module 7: TMP Approval and Implementation—we’ll discuss TMP review and approval, TMP implementation and monitoring, TMP revisions, and post-project evaluation.
Where applicable each module will have examples of how various agencies are approaching various aspects of the rule provide examples of applications that have been used various projects.
We’ll conclude the course with a general exercise and post course assessment.
Interaction: None.
Notes: None.

## Slide 70: Check the “Parking Lot”
Pending questions or issues?
Parking
Lot
Image: Microsoft
Notes: Key Message: Discuss the “parking lot”
Background Information: Instructor should go through the items/questions that were pending (“parked”) and make sure all questions are properly addressed.
Interactivity: None
Notes: None

## Slide 71: Pilot Course Feedback
What can we do to improve course?
Length of course
Course content
Exercises
Notes: Key Message: Completion of evaluation forms
Background Information: Please complete the evaluation form using a pen or a thin felt tip. There is no need to enter any personal information or information about the course (date, etc.). Simply X the box that best represents your views. Written comments (4.2) are always welcomed. You may turn it in along with your exam and exam booklet.
Interactivity: None
Notes: None

## Slide 72: Course Evaluation Form
Mark with an ‘X”
If a correction is needed, fill it in and “X” again
Image: ATSSA
Notes: Key Message: Completion of evaluation forms
Background Information: Please complete the evaluation form using a pen or a thin felt tip. There is no need to enter any personal information or information about the course (date, etc.). Simply X the box that best represents your views. Written comments (4.2) are always welcomed. You may turn it in along with your exam and exam booklet.
Interactivity: None
Notes: None

## Slide 73: Exam
25 multiple choice questions
4 pts. each = 100 pts
30 minutes
Open book, open notes
Passing grade = 80%
Image: ATSSA
Notes: Key Message: Discuss the exam
Background Information: None
Interactivity: None
Notes: None

## Slide 74: After the Exam
Turn in ALL exam materials!
Other materials are yours to keep
You may leave when finished!
ATSSA will send exam results/certificate in 2-4 weeks
Notes: All exam materials must be returned to the instructor.

## Slide 75: Developing and Implementing Transportation Management Plans
Thank you for choosing ATSSA for your training needs
Image: ATSSA
Notes: Key Message: Complete exam procedure
Background Information: When you are done with the test, return both the exam and answer sheet to me. If you still have it, also return the evaluation form to me. You may then leave. Good luck and thank you for choosing ATSSA for your training needs. We hope you found this course to be a learning experience. Thank you!
Interactivity: None
Notes: None