## Slide 1: Developing and Implementing Transportation Management Plans
3. Transportation Management Plan (TMP) Basics
Image: ATSSA
Notes: Key Message: Title slide to introduce module 3.
Background Information: In module 2, the Work Zone Safety and Mobility Rule brought forth the concept of a Transportation Management Plan(TMP). This module will provide more detail of the basics of a Transportation Management Plan (TMP)—the what, why, when, and who of TMP development. Examples from various States are used to illustrate a particular concept, but are not the only way the concepts can be implemented.
Interactions: None
Notes: None

## Slide 2: TMPs: The Basics
Discuss what a TMP is and why it is needed
Review state examples of Significant Project criteria
Describe the TMP process, format, and implementation costs
Notes: Key Message: Overview of module
Background Information: This Module provides a general description of a TMP and explains why a TMP is needed and what benefits it provides. The module then addresses how TMP requirements are affected if a project is significant or not and provides some examples of significant project criteria. The module also covers when to develop the TMP, who is involved, and possible processes and formats. The module concludes with a brief discussion on TMP costs.
Interaction: None
Possible Problems: None

## Slide 3: What is a TMP?
A set of coordinated strategies
Shows how traffic impacts will be managed during construction by identifying a set of coordinated transportation management strategies
Is scalable
  Projects with more expected impacts may need more analysis and more strategies
Notes: Key Message: A TMP lays out a set of coordinated transportation management strategies and describes how they will be used to manage the work zone impacts of a road project. To support the identification and application of these strategies, FHWA expanded the existing requirement for developing a Traffic Control Plan (TCP) for handling traffic at each WZ to now require the development and implementation of a Transportation Management Plan (TMP).
Background Information:
Effective WZ management can require a combination of strategies.
  Projects with more expected impacts may need more analysis and more strategies, such as temporary traffic control measures and devices, operational strategies, and public information and outreach.
Inclusion of such strategies in the TMP helps to improve safety, reduce traffic and mobility impacts, and promote coordination in and around the WZ.
Interaction: None.
Notes: None.

## Slide 4: What is a TMP? (2 of 2)
Required components of a TMP depend on whether a project is a “significant project”
TMP must always include a Temporary Traffic Control (TTC) Plan
For significant projects, TMPs must also have:
    A traffic operations (TO) component
    A public information and outreach (PIO) component
Notes: Key Message: The TMP is designed to encourage broader thinking about traffic impacts and ways to reduce them.
Background Information:
One of the goals of the updated Rule is to expand WZ impacts management beyond just traffic control.
To encourage this broader thinking, one of the components of the updated Rule expands the existing requirement for developing a traffic control plan (TCP) for handling traffic at each work zone to now require the development and implementation of a transportation management plan (TMP) for road projects.
The TMP must always include a Temporary Traffic Control (TTC) plan but,
For significant projects, TMPs must also have:
  Traffic operations (TO) component
  Public information and outreach (PIO) component
Interaction: None.
Notes: None.

## Slide 5: TMP v. TTCP – What’s the Difference?
TMP – incorporates broader issues such as:
  Public awareness
  Mobility and safety impacts
  Stakeholder involvement
  Undergoes updates – is a “living document”
TTC Plan – limited to handling work zone traffic through the use of traffic control devices
  Implements the chosen strategies
  Focused on getting users through the work zone safely
Notes: Key Message: The Temporary Traffic Control Plan (TTCP) is a much more limited, static document that focuses only on safety, not mobility or other work zone impacts.
Background Information:
TMP development begins in the early planning stages of the project and incorporates a broad range of concerns, including stakeholder concerns, public awareness issues, and the impacts the project will have on the community’s ability to travel safely and efficiently through the work area.
The TMP is updated as the project goes through different stages of planning and design. Once the TMP is implemented during construction, it needs to be monitored. If any major work zone adjustments are needed, the TMP must be revised to reflect the changes. That is why a TMP is also referred to as a "living document".
Under the previous rule the Traffic Control Plan (TCP) was provided in the contract design plans with very little regard to the disruption to traffic. The goal was to provide a safe way through the construction. The thinking was that traffic would eventually find alternate routes and disperse on its own.
One should note the new rule uses Temporary Traffic Control Plan (TTC) while the old rule uses Traffic Control Plan (TCP). These terms are now used interchangeably .
Interaction: None.
Notes: None.

## Slide 6: Why is a TMP Needed?
Work zone management is increasingly complex:
  Increasing traffic volumes use the same roads that agencies must maintain and rehabilitate
  Requires traffic management efforts beyond Temporary Traffic Control (TTC) Plans
TMP provides a comprehensive approach to managing work zone impacts:
  Safety
  Mobility
Notes: Key Message: Increasing complexity of our work zones and higher volumes creates a need to account for broader impacts.
Background Information:
Our highways are at an age where they require more reconstruction and repair, resulting in more work zones.
Many urban areas have increasing congestion and morning and afternoon peak periods that last several hours, and there may even be a mid-day peak. This makes it increasingly challenging for work zone traffic management because a growing portion of road work is made up of maintenance, reconstruction, and improvements to existing roads. These roads already carry traffic and are an important part of the transportation system, so closing lanes and staging construction is challenging.
The TMP provides a comprehensive approach for looking at all the traffic-related impacts from the project and determining what strategies need to be in place to minimize the impacts. It also supports the process for estimating traffic impacts for upcoming work zones and helps agencies plan for and mitigate the effects of these work zones.
Interaction: Begin by asking class why they think a TMP might be needed.
Possible Problems: None

## Slide 7: TMP Benefits
Increases work zone safety for workers
Improves road user mobility and safety
More efficient/effective construction phasing, staging
Improves public awareness and minimizes complaints
Minimizes overall access impacts
Improves intra- and inter-agency coordination
Designates roles, responsibilities, and actions
Notes: Key Message: The most significant TMP benefits relate to the safety and mobility of the road user and workers.
Background Information:
Some of the key benefits of a TMP are to help:
  Address the broader safety and mobility impacts of work zones at the corridor and network levels.
  Improve work zone safety for construction workers and the traveling public.
  Minimize the traffic and mobility impacts of a work zone.
  Promote more efficient and effective construction phasing and staging, minimize contract duration, and control costs.
  Improve public awareness.
  Minimize complaints from the traveling public and local businesses and communities.
  Minimize circulation, access and mobility impacts to local communities and businesses.
  Improve intra- and inter-agency coordination.
  Identifies responsibilities and actions
  More satisfied road users, and
  Reduced agency cost.
Even if there is good planning and a TMP is developed for a project, unexpected issues can result if traffic diverts to the area as a result of another project nearby. So it is important to consider the impacts of other concurrent construction projects in the area. The TMP process can help foster this coordination by bringing stakeholders together.
Interaction: None
Possible Problems: None

## Slide 8: TMP Benefits: Caltrans Example
On the I-10 Long-Life Pavement Project, the TMP is credited with reducing:
  Traffic demand by an estimated 57%
  Queue lengths to 2 miles from the originally projected 44 miles
  Delays from an estimated 1 million to 16,000 total vehicle-hours of delay
Notes: Key Message: Benefits of TMPs are proven.
Background Information:
Caltrans began requiring TMPs in 2000 for all planned activities on the State highway system
Implementation of TMPs in CA has helped to reduce delays in work zones significantly and has been credited as being the driving force behind FHWA’s creation of the Rule.
From the FHWA presentation by Tracy Scriba, AASHTO Design Meeting July15, 2008
Interaction: None
Possible Problems: None

## Slide 9: Significant Projects’ Rule Definition
Projects that, alone or in combination with other concurrent projects nearby, have “sustained WZ impacts greater than what is considered tolerable based on State policy and/or engineering judgment…”
Lane closure greater than three days.
Image: ATSSA
Notes: Key Message: Define “significant projects” and their characteristics
Background Information:
As discussed in the module 2, the Rule defines a significant project as one that has the potential to cause sustained work zone impacts that are greater than what is considered tolerable based on agency policy or engineering judgment. A project can be significant because it causes these impacts on its own or in combination with other projects that will occur nearby at the same time.
At a minimum, all Interstate system projects within the boundaries of a designated Transportation Management Area that occupy a location for more than 3 days with intermittent or continuous lane closures are to be considered significant projects.
In summary, a significant project is one that is expected to cause a relatively high level of impacts or disruption.
Interaction: Begin with: “We have mentioned the term ‘significant project,’ but what does that mean? What is a significant project?”
Notes:
§ 630.1010 Significant projects.
  A significant project is one that, alone or in combination with other concurrent projects nearby is anticipated to cause sustained work zone impacts (as defined in § 630.1004) that are greater than what is considered tolerable based on State policy and/or engineering judgment. Furthermore, all Interstate system projects within the boundaries of a designated Transportation Management Area (TMA) that occupy a location for more than three days with either intermittent or continuous lane closures are to be considered as significant projects.
  The applicability of the provisions in §§ 630.1012(b)(2) and 630.1012(b)(3) is dependent upon whether a project is determined to be significant. The State shall identify upcoming projects that are expected to be significant. This identification of significant projects should be done as early as possible in the project delivery and development process, and in cooperation with the FHWA. The State’s work zone policy provisions, the project’s characteristics, and the magnitude and extent of the anticipated work zone impacts should be considered when determining if a project is significant or not.
  All Interstate system projects within the boundaries of a designated Transportation Management Area (TMA) that occupy a location for more than three days with either intermittent or continuous lane closures shall be considered as significant projects.
  For an Interstate system project or categories of Interstate system projects that are classified as significant through the application of the provisions in § 630.1010(c), but in the judgment of the State they do not cause sustained work zone impacts, the State may request from the FHWA, an exception to §§ 630.1012(b)(2) and 630.1012(b)(3).
  Exceptions to these provisions may be granted by the FHWA based on the State’s ability to show that the specific Interstate system project or categories of Interstate system projects do not have sustained work zone impacts.

## Slide 10: The Rule defines significant projects, however…
States determine significant projects through:
  Work zone policy provisions
  The project’s characteristics
  The magnitude of the anticipated work zone impacts
  Factors include whether there is a single large project or multiple projects in one area
Notes: Key Message: The State has a significant role in defining “significant projects”
Background Information:
As we discussed, significant projects are defined as those with the potential for higher levels of disruption.
The identification of significant projects early in the project delivery process will support effective allocation of resources later in the project development and execution process.
The Rule offers some flexibility in allowing the state transportation agency to identify significant projects. So how does the State determine this? There are a number of ways, including not only the expected impacts of a single work zone or project, but also the presence of several projects in one area that together may cause widespread disruptions to travel patterns and traffic flow.
Interaction: Ask “Who determines what is a significant project?”
Notes: Provided for instructor reference:
§ 630.1010 Significant projects.
  A significant project is one that, alone or in combination with other concurrent projects nearby is anticipated to cause sustained work zone impacts (as defined in § 630.1004) that are greater than what is considered tolerable based on State policy and/or engineering judgment. Furthermore, all Interstate system projects within the boundaries of a designated Transportation Management Area (TMA) that occupy a location for more than three days with either intermittent or continuous lane closures are to be considered as significant projects.
  The applicability of the provisions in §§ 630.1012(b)(2) and 630.1012(b)(3) is dependent upon whether a project is determined to be significant. The State shall identify upcoming projects that are expected to be significant. This identification of significant projects should be done as early as possible in the project delivery and development process, and in cooperation with the FHWA. The State’s work zone policy provisions, the project’s characteristics, and the magnitude and extent of the anticipated work zone impacts should be considered when determining if a project is significant or not.
  All Interstate system projects within the boundaries of a designated Transportation Management Area (TMA) that occupy a location for more than three days with either intermittent or continuous lane closures shall be considered as significant projects.
  For an Interstate system project or categories of Interstate system projects that are classified as significant through the application of the provisions in § 630.1010(c), but in the judgment of the State they do not cause sustained work zone impacts, the State may request from the FHWA, an exception to §§ 630.1012(b)(2) and 630.1012(b)(3).

## Slide 11: State Examples of Significant Project Criteria: Kentucky
Any interstate project > 3 days
Also has Design Hourly Vehicle (DHV) requirements
Any project on the National Highway System (NHS) or Interstate with detour
Notes: Key Message: States may identify “significant projects” differently
Background Information:
Here is how Kentucky defines a significant project:
Projects let by the Cabinet shall be referred to as either “Significant” or “Other”.
Significant Projects shall be:
  Any Interstate System project that is anticipated to occupy a location for more than 3 days
  Any project on any multilane roadway that is anticipated to occupy a location for more than 3 days where the existing directional DHV is over 1000 vehicles per hour, per lane, that would close a lane during the peak hours
  Any project on a 2 lane roadway that is anticipated to occupy a location for more than 3 days where the existing DHV (both directions) is over 1000 vehicles per hour that would close a lane during the peak hours
  Any project on the Interstate or National Highway System that would involve a detour
All projects not meeting the aforementioned requirements shall be referred to as Other Projects.
Interaction: TBD
Notes: TBD

## Slide 12: State Examples of Significant Project Criteria: Illinois
Significant project- provides a map showing routes that are considered significant
  Long term , work > than three days
  Short term, work < three days
Notes: Key Message: States define “significant projects” differently
Background Information: Illinois has very rural areas with high volume interstates and other roadways with low volume. It also has the urban area of Chicago where all roadways are considered significant. Significant projects are defined because an impact analysis would be required for those projects.
Here is how Illinois defines a significant project:
Significant Project – Long Term. Roadway segments identified on the Significant Route Location Maps involving work greater than 3 days duration are considered Significant Projects – Long Term. A Significant Project – Long Term requires an Impact Analysis be performed and requires a TMP.
Significant Project – Short Term. (Operations, Permit, Utility, and other short-term work.) Roadway segments identified on the Significant Route Location Maps involving work of 3 days or less.
Significant Route – Roadway segments where a lane closure on the roadway is expected to cause sustained work zone impacts that are not considered tolerable based on work zone mobility goals or public opinion.
Non-Significant Route – Work on a roadway that is not considered a significant route and that impacts the traveling public to a small degree due to low traffic volume, low public interest, and is short to moderate duration
Also has a significant route map and a flow chart to determine whether an impact analysis is required.
Interaction: None
Notes: None

## Slide 13: State Examples of Significant Project Criteria: Illinois (cont.)
Significant Route- Roadway where a lane closure causes sustained impacts
Non-Significant Route-is one that work on the roadway impacts the traveling public to a small degree
Notes: Key Message: States define “significant projects” differently
Background Information: Illinois has very rural areas with high volume interstates and other roadways with low volume. It also has the urban area of Chicago where all roadways are considered significant. Significant projects are defined because an impact analysis would be required for those projects.
Here is how Illinois defines a significant project:
Significant Project – Long Term. Roadway segments identified on the Significant Route Location Maps involving work greater than 3 days duration are considered Significant Projects – Long Term. A Significant Project – Long Term requires an Impact Analysis be performed and requires a TMP.
Significant Project – Short Term. (Operations, Permit, Utility, and other short-term work.) Roadway segments identified on the Significant Route Location Maps involving work of 3 days or less.
Significant Route – Roadway segments where a lane closure on the roadway is expected to cause sustained work zone impacts that are not considered tolerable based on work zone mobility goals or public opinion.
Non-Significant Route – Work on a roadway that is not considered a significant route and that impacts the traveling public to a small degree due to low traffic volume, low public interest, and is short to moderate duration
Also has a significant route map and a flow chart to determine whether an impact analysis is required.
Interaction: None
Notes: None

## Slide 14: State Examples of Significant Project Criteria: Michigan
If any of the following criteria exist:
  Work zone delay greater than 10 minutes
  Work zone level of service (LOS) is lower than or equal to LOS D, or it drops to LOS C if the current operation is LOS A
  Work zone volume/capacity ratio is greater than 0.80
Notes: Key Message:
Background Information: The Michigan Department of Transportation uses three thresholds to determine whether a
project is significant. The thresholds are based on delay, level of service, and the ratio of volume to capacity. If one or more of these thresholds are exceeded, then the project is considered significant. For example, if a work zone is expected to cause additional delay of 15 minutes, beyond any pre-existing delay, the project is considered as a significant project
in Michigan.
Like a number of other States, Michigan uses a computer program to analyze delay.
Interaction: None
Notes: Most states have developed similar significant project criteria which is in their Work Zone and Mobility policies.

## Slide 15: States’ Significant Project Criteria
Most States have developed similar criteria
Included in the states Work Zone Safety and Mobility Policies
Select “Significant Projects” under “Examples”:
https://ops.fhwa.dot.gov/wz/resources/final_rule/examples.htm
Notes: Key Message: Background Information:
Most States have developed similar significant project criteria. The significant project criteria is included in the states Work Zone Safety and Mobility Policies. To view what other states have for significant project criteria go to: “Significant Projects” under “Examples” in the list of resources at: https://ops.fhwa.dot.gov/wz/resources/final_rule/examples.htm
Interaction: None
Notes: None

## Slide 16: TMPs and Significant Projects
Why it is important to identify significant projects?
  Have potential to create greater impacts
  Requires more detail during project development and delivery
  Insures adequate funding for TMP
When should we identify significant projects?
  As early as possible, when the most options are available
Notes: Key Message: Agencies need to identify the most potentially disruptive projects early so they can spend time determining how best to mitigate anticipated negative impacts.
Background Information:
Identifying significant projects during the early planning stages is critical as they have the potential to cause greater work zone impacts and may also need additional coordination, scheduling, and resources during project planning, design, and implementation. Beginning such efforts early in project development will help the DOT allocate the necessary resources
to reduce and manage impacts to the traveling public, community, and businesses, and will allow for better coordination with other projects occurring in the area at the same time.
Interaction: None
Notes: None.

## Slide 17: When to Develop a TMP
Begin TMP development during planning and
progress through stages of the project:
  Planning/scoping
  Design
  Construction/implementation
Design-build projects – Initial TMP may include series of procedures for the contractor to follow
Notes: Key Message: Developing a TMP as early as possible increases your strategy options.
Background Information:
Ideally, TMP development should begin during project conceptualization or the early planning stages of a project. At this stage of the project, more alternatives and strategies are available for addressing the anticipated work zone impacts.
As the project progresses through the different stages of design, the TMP evolves. The strategies selected are reassessed to confirm that work zone impacts are addressed and the TMP is updated as needed.
The TMP is implemented during construction, and if any major work zone adjustments are needed, the TMP is revised to reflect the changes.
In Design/Build projects the construction proceeds along with the design and TMP development. The initial TMP may include a series of procedures that the contractor must follow, such as for detours, lane closure hours, MOT inspection, and public information. The contractor would fill in the TMP details as the project design progresses.
The TMP is a living document that needs to be updated regularly throughout the life of the project.
Source: https://ops.fhwa.dot.gov/wz/resources/final_rule/tmp_examples/tmp_training/tmp_module_2.htm
Interaction: None
Possible Problems: Recognize that some feasible alternatives may cause much greater traffic impacts than other alternatives. As the alternatives are being analyzed, these impacts should be considered as a factor in final strategy selection.

## Slide 18: Who Develops, Approves and Implements a TMP?
Development
  State/local agency or consultant and/or contractor
Approval
  State/local agency
Implementation
  Contractor and state/local agency
Monitoring
  State/local agency and contractor
Notes: Key Message: Identify different roles and responsibilities among State/local agency and contractor staff.
Background Information:
DOTs or their design consultants generally develop the TMP, while the implementation and monitoring is a joint effort between the contractor and the DOT.
The State or local transportation agency must approve the TMP before its implemented. However, in some practices, like design-build, the contractor develops the TMP and, once approved by the DOT, the contractor will be responsible for its implementation.
The next slides illustrate a an example of TMP processes.
Interaction: None
Possible Problems: None

## Slide 19
Image: FHWA
Notes: Key Message: Summarize the 6 steps of TMP development that occur during planning and design.
Background Information:
Step 1 is to compile information on project definition and scope, construction staging approaches, and preliminary management strategies.
Step 2 is to determine TMP needs based on whether the work qualifies as a significant project. The levels may be divided into a basic TMP (comprising only a temporary traffic control plan), an intermediate TMP (which will include a TTC plan and either a Transportation Operations plan, a Public information plan, or both, as appropriate). For a project with severe impacts, a major TMP will be needed, including TTC, TO, and PI plans.
Step 3 is to identify stakeholders.
Step 4 is to develop the TMP. For a basic TMP, this simply includes preparing a TTC plan. For an intermediate or major TMP, the process includes:
  Analyzing work zone impacts
  Drafting management strategies
  Estimating implementation costs
  Soliciting review and comments
For a basic TMP, we see that step 5, takes us back to step 1, compile project materials. For an intermediate or major TMP, the next step is step 6, which is to finalize construction phasing or staging and finalize the TMP. This includes obtaining agency approval of the TMP and gaining stakeholder buy-in.
Interaction: None
Notes: This diagram is from FHWA’s Developing and Implementing TMPs for Work Zones.

## Slide 20: TMP Development Process: Construction and Performance Monitoring
Image: FHWA
Notes: Key Message: Summarize the 4 steps of the TMP development process that occur during construction and performance assessment.
Background Information:
After the TMP has been approved and stakeholders have bought in, the next step is Step 7, which is to re-evaluate or revise the TMP as needed, followed by step 8, implementation.
At this point the process moves into the monitoring phase, where mobility, safety, community impacts, and management strategy effectiveness are gauged. In the event that the strategies are not working as well as anticipated, or if unanticipated impacts are occurring, we need to go back to step 7 and re-evaluate the TMP for areas where we can make improvements.
Performance assessment is a continuous process, and can provide insights into policies and procedures that may need to be refined at the agency or project level.
Interaction: None
Notes: This diagram is from FHWA’s Developing and Implementing TMPs for Work Zones.

## Slide 21: What Format does the TMP Take?
TMPs need to be documented, but the formats used vary:
  Single document with all materials
  Brief document with a summary of analyses and references to supporting information
  Templates
  Workbooks
Notes: Key Message: TMP formats may vary depending on the State’s requirements or the project size
Background Information:
TMPs are a formal plan that can be an all-inclusive document or a summary document with supporting information provided in appendices or project files. The final document format depends on the DOT and its Policy guidelines.
Some States use TMP templates or workbooks to aid staff in developing TMPs. Other States use a typical report format.
Interaction: None
Possible Problems: None

## Slide 22: Sample TMP Outline
Project Description
TMP Team—Roles and Responsibilities
Preliminary WZ Analysis
Existing Conditions
Operational Analysis:
  Safety and Traffic Analyses
WZ Impact Management Strategies:
  TTC Plan
  TO
  PI&O
Notes: Key Message: Provide an example of what TMP includes.
Background Information:
A typical TMP will contain many of these elements. However, it is important to keep in mind that some TMPs will be relatively simple, while others will be much more involved and detailed.
The scope and level of detail depends on a number of factors including whether a project is significant; the potential work zone impacts of the project; and agency policies, procedures, and guidelines.
In some States the TMP is a shared responsibility among many departments.
  For example, the traffic analysis may be completed by an agency’s Safety Office while the traffic control plan may be developed by the Traffic Office. This information needs to be conveyed to the TMP developers.
Interactions: None
Notes: None

## Slide 23: Sample TMP Outline (cont.)
Incident Management/ Contingency Plan
Special Considerations/ Notes
TMP Implementation/ Monitoring Requirements
Review/Approvals
Appendices
Notes: Key Message: Provide an example of what TMP includes.
Background Information:
A typical TMP will contain many of these elements. However, it is important to keep in mind that some TMPs will be relatively simple, while others will be much more involved and detailed.
The scope and level of detail depends on a number of factors including whether a project is significant; the potential work zone impacts of the project; and agency policies, procedures, and guidelines.
In some States the TMP is a shared responsibility among many departments.
  For example, the traffic analysis may be completed by an agency’s Safety Office while the traffic control plan may be developed by the Traffic Office. This information needs to be conveyed to the TMP developers.
Interactions: None
Notes: None

## Slide 24: TMP and State Processes
State Processes for developing TMPs vary
  Some are very detailed, extensive and stand alone guidance documents
  Some are very brief
Reasons for range of detail
  Some states added to existing guidance
  Some rewrote and completely updated due to the rule
Notes: Key Message: We will now take a brief look at how a few States have incorporated the TMP process.
Background Information:
Many States have developed their own guidance documents for developing TMPs. Some are very extensive and provide detailed information regarding significant projects, TMP development, Traffic Control Plans, Traffic operations, public information, TMP implementation and TMP monitoring, while others are very brief.
There are numerous reasons for the range of detail between states. Some have traffic control guidance detailed in other documents and the rule just added to them.
Other States took the opportunity to completely update their guidance documents and included the new guidelines from the rule.
Interactions: None
Notes: None

## Slide 25: Virginia TMP Processes
VDOT developed a TMP Guide:
  Guidelines for acquiring information to develop TMPs
  Guidance on each Project Team member's role and responsibilities in the development of TMPs
  Covers Project Managers, Roadway Designers, Traffic Engineers, WZ Safety Coordinators, Public Affairs Managers
Notes: Key Message: Virginia TMP requirements.
Background Information:
The Virginia DOT has developed a document outlining TMP development requirements for all projects.
This document provides guidelines to be used by Project Managers, Roadway Designers, Traffic Engineers, Work Zone Safety Coordinators, and Public Affairs Managers pertaining to acquiring the information to develop TMPs.
It also contains guidance on each Project Team member's role and responsibilities in the development of TMPs, and guidance to Project Managers on VDOT's TMP requirements based on the project's level of complexity.
Interactions: None
Notes: This slide shows the cover page one of VDOT’s TMPs, developed for a major Interstate interchange project on the Capital Beltway.

## Slide 26: Maryland TMP Development
“Transportation Management Plans: Guidelines for Development, Implementation and Evaluation”
  Extensive manual on TMPs
  Summary of work zone impact management strategies
  Public information and outreach plans development guidance
Notes: Key Message: Maryland TMP requirements.
Background Information:
Maryland developed quite an extensive manual on how to develop, implement and evaluate Transportation Management Plans, called “Transportation Management Plans: Guidelines for Development, Implementation and Evaluation .” This document provides guidance transportation management plan (TMP) development and on how and where a transportation management plan (TMP) fits into the processes and procedures that are part of the typical project delivery process.
This document has numerous Appendices listed some of which include:
  Summary of Work Zone Impact Management Strategies (PDF 69KB) - This document provides definitions of work zone impact management strategies, many specific to MdSHA, and is intended to be a reference for selecting work zone management strategies.
  Public Information and Outreach Plans Development Guidance (PDF 165KB) - Provides guidance on developing public information and outreach plans and information such as potential strategies, possible stakeholders and interested parties, sample goals and measures of effectiveness, and the process for establishing a public information and outreach effort.
  Guidance on Identifying significant Projects
  Guidance on Work Zone Analysis
  Work Zone Design Checklist
Interactions: None
Notes: None

## Slide 27: Maryland TMP Development (2 of 2)
MOT Red Flag Summary

Image: Maryland SHA
Notes: Key Message: Maryland’s notable practice.
Background Information:
One of the other appendices listed in the Maryland TMP plan is the “Maintenance of Traffic (MOT) Red Flag Summary.”
The goal of the Maintenance of Traffic (MOT) Red Flag Summary is to identify any existing barriers that may affect safety and mobility during construction or that may pose significant construction issues. Red flags are meant to identify locations that may entail additional study coordination; creative management, design or construction approaches; or increased right-of-way or construction costs.
MOT Red Flag Summary asks questions like:
  Can traffic be detoured?
  Is the existing shoulder in good enough condition to support traffic during construction?
  Could additional width be required on culverts or bridges to maintain traffic?
  Could a crossover be needed?
Interactions: None
Notes: None

## Slide 28: Missouri DOT TMP Strategy Database
Helps MoDOT staff:
  Select WZ management strategies and
  Develop TMPs in a more systematic way
Suggests possible appropriate WZ management strategies based on user inputs
  Time concerns
  Public impact
  Location
  Traffic flow
Notes: Key Message: Missouri’s notable practice.
Background Information:
Missouri DOT developed a Transportation Management Plan (TMP) Strategy Database to aid in the selection of work zone management strategies and development of TMPs for its road projects in a more systematic way.
Organized around four major triggers (project goals) focusing on time concerns, public impact, location, and traffic flow.
Under each area, users can select options such as "short-term project" or "concerns for worker safety" and the system will then display the possible strategies that will meet the goals of each project.
The strategies are accompanied by additional pertinent information, such as whether increased enforcement or public information is needed.
Use the database at the very beginning of work zone planning in order to choose the most effective methods from the start, with re-evaluation occurring in the design stage. Construction personnel can use the program to find a solution if concerns arise while the work zone is in operation.
As part of TMP development and documentation, MoDOT writes an executive summary that describes the project, identifies whether it is a significant project, and describes the TMP strategies that will be implemented for the project. These summaries will be attached to the output from the database.
Database was developed by the Work Zone Quality Circle, MoDOT's work zone management task force, and is based on the work zone management strategies matrix found in Developing and Implementing Transportation Management Plans for Work Zones.
Interactions: None
Notes: None

## Slide 29: Missouri DOT TMP Strategies Database
Meant to be used at the very beginning of WZ planning to identify effective methods, with re-evaluation occurring in the design stage.
Images: Missouri DOT
Notes: Key Message: Missouri’s notable practice.
Background Information:
The TMP Strategy Database is an Access database that returns possible appropriate work zone management strategies based on user inputs.
The database is organized around four major triggers (project goals) focusing on time concerns, public impact, location, and traffic flow.
  Under each project goal, users can select options such as “short-term project” or “concerns for worker safety” and the system will then display the possible strategies that will meet the goals of each project. The strategies are accompanied by additional pertinent information, such as whether increased enforcement or public information is needed.
MoDOT said it intends to use the TMP Database at the very beginning of work zone planning in order to choose the most effective methods from the start, with re-evaluation occurring in the design stage. Construction personnel will also be able to use the program to find a solution if concerns arise while the work zone is in operation.
The database was developed by the Work Zone Quality Circle, MoDOT’s work zone management task force, and is based on the work zone management strategies matrix found in the FHWA-developed guide entitled Developing and Implementing Transportation Management Plans for Work Zones Guidebook.
Interactions: None
Notes: None

## Slide 30: Illinois TMP Component Checklist
Image: Illinois DOT
Notes: Key Message: Illinois’ notable practice
Background Information:
Illinois prepared a new policy and then included the policy in the rewrite of its Design manual.
This is the Illinois TMP component checklist for large projects.
They also include an example template of a TMP for a small project on a significant route.
Interactions: None
Notes: None

## Slide 31: Illinois TMP Component Checklist (cont.)
Image: Illinois DOT
Notes: Key Message: Illinois’ notable practice
Background Information:
Illinois prepared a new policy and then included the policy in the rewrite of its Design manual.
This is the Illinois TMP component checklist for large projects.
They also include an example template of a TMP for a small project on a significant route.
Interactions: None
Notes: None

## Slide 32: FHWA TMP Templates
FHWA website for TMP information:
http://ops.fhwa.dot.gov/wz/resources/final_rule/tmp_examples/tmp_dev_resources.htm
  Sample Transportation Management Plans and Templates
  TMP Template 1: Minor-to-Moderate Impacts
  TMP Template 2: Moderate-to-Major Impacts
Notes: Key Message: FHWA’s website has lists of resources
Background Information:
Provides samples, templates, and tips to help transportation agencies develop and implement their own TMPs. The website includes a link to the entire document, which includes the sample plans and templates, and links to the individual templates in editable Microsoft Word format so that agencies can fill in and tailor the templates to their projects.
  Sample Transportation Management Plans and Templates
  TMP Template 1: Minor-to-Moderate Impacts
  TMP Template 2: Moderate-to-Major Impacts
FHWA is currently developing a tool for developing TMP for Design-Build projects.
Interactions: None
Notes: None

## Slide 33: TMP Implementation Costs
TMP Implementation Cost Include:
TMP development process
Strategies
Monitoring
Post project activities
Estimating the cost of the TMP is crucial because it:
May be impossible to obtain additional funding later
Avoids under-allocation of funds
Image: FHWA
Notes: Key Message: Estimating TMP cost early is crucial, so be sure to take into account the cost of each element.
Background Information:
The TMP cost includes the TMP development process, the implementation of the selected strategies, monitoring during construction, and any post project activities. TMP cost will vary based on project size, the extent of project impacts, location, and duration of the project. Generally the larger and more complex a project is, the greater the overall TMP cost.
Estimating the costs to implement the TMP and including these costs within the overall project cost is critical, as it may be difficult to obtain additional funding at a later time.
When there is more than one project occurring in an area, it may be possible to share some TMP costs across projects, such as costs for a public outreach campaign or the use of a motorist assist patrol to address disabled vehicles.
Interactions: None.
Notes: None

## Slide 34: Paying for TMP Implementation
Determine who is responsible for implementing each strategy
Construction contractor
  Include means of payment in contract
Other contractor
  Establish or modify other contract
Agency
  Coordinate with relevant agency departments
Notes: Key Message: Guidelines for paying for TMP implementation
Background Information:
Cost estimates for the various TMP strategies should be itemized and documented when feasible, with cost responsibilities, opportunities for sharing or coordinating with other projects, and funding sources specified.
TMP strategies can be funded as part of the construction contract, in separate agreements with other contractors, and within the owner-agency.
  For example, if one of the TMP strategies is to implement a temporary intelligent transportation system for work zone monitoring and management, the agency might include that strategy in the construction contract or might implement it through a separate agreement with a consultant or vendor.
For public information strategies, an agency might choose to use a separate consultant contract with a pubic relations firm or have the outreach strategies done by the agency's own pubic information officer.
Provisions for a TMP must be included in the project's plans, specifications, and estimates, or PS&Es. The PS&Es must either contain all the elements of an agency-developed TMP that will be implemented by the construction contractor, or include provisions for the contractor to develop and implement a TMP.
Specific pay item provisions for the TMP also need to be included. Pay item provisions can be individual pay items, lump sum, or a combination of these methods, or as performance-based specifications that stipulate performance criteria and standards. TMP strategies should not be considered incidental to a contract.
Interactions: None
Notes: None

## Slide 35: In summary, TMPs:
Are required for all Federal-aid projects
Are a plan showing how the traffic will be managed during construction
Address work zone safety and mobility impacts
Should be started early in project development and updated throughout
Needs to be approved, implemented, and monitored in the field
Notes: Key Message: Summarize key points
Background Information:
To review what we learned in this module:
DOTs must create a TMP for every Federal-aid road project.
TMPs are a formal plan that shows how traffic will be managed during construction.
TMPs reduce and manage the safety and mobility impacts of work zones
Developing an effective TMP is an effort that should be started early in project development and then updated as the project progresses through preliminary engineering, design, and construction.
A TMP must be approved by the DOT before implementation. After it is implemented in the field, it needs to be monitored to see if it is effectively managing traffic.
Interactions: Questions?
Notes: None

## Slide 36: Questions
Notes: Key Message: Questions
Est. Presentation Time: Less than 1 minute(s)
Explanation of Cues/Builds: None
Suggested Comments: Let’s take your questions.
Suggested Questions: Any questions before we move to the next module?
Additional Information: None
Possible Problems: If no questions, you may want to ask your own.