## Slide 1: Developing and Implementing Transportation Management Plans
4. TMP Coordination
Image: ATSSA
Notes: Key Message: Title slide
Background Information:
One important element to an effective TMP is "coordination."
This module discusses coordination during the TMP development and implementation process, and the parties that should be involved.
The module discusses coordination issues that need to be considered and illustrates ways to achieve coordination while developing TMPs.
Interactions: None

## Slide 2: TMP Coordination Module Topics
Stakeholders
Internal Project Coordination
Coordinating Multiple Projects
Interagency Coordination
Roles and Responsibilities
TMP Teams
Exercise
Notes: Key Message: Introduce module topics
Background Information:
TMP coordination discusses stakeholders; internal project coordination; coordinating multiple projects; interagency coordination; roles and responsibilities; and TMP teams. The module concludes with an exercise to help you apply what you have learned.
Interactions: None
Notes: None

## Slide 3: Stakeholders
Image: FHWA
Notes: Key Message: Discuss each of the stakeholders
Background Information:
Coordinate with key stakeholders to identify work zone impact issues to consider and management strategies to address them
Coordination within and across agencies and other stakeholders at different stages of the project is crucial for the successful development and implementation of a TMP.
Regular meetings are one way to bring all stakeholders together and share the same information in a timely and accurate manner. Note that meetings can be scheduled monthly, as needed or scheduled at the conclusion of each meeting. Depending on the project and issues, some stakeholders attendance could be more important than others.
The list of stakeholders needs to be carefully thought out and may include agencies outside the project jurisdiction.
  For example, if the project is along an evacuation route, then Federal agencies like the Department of Homeland Security may need to be notified.
  Another consideration is emergency response. While coordination with emergency responders is always important, if the project is near a hospital additional stakeholders from EMS need to be at the table.
The stakeholders list can be added to as the project progresses and new needs arise.
Interactions: Start discussions with students and the roles and responsibilities of each of the stakeholders.
Notes: None

## Slide 4: Internal Project Coordination
Alternatives Analysis
  Identify work zone impacts
  TTC options associated with feasible alternatives
  Brainstorm alternatives
  Selection of the preferred alternatives
Notes: Key Message: Talk about Internal Project Coordination
Background Information:
The TMP is a living document that needs to be developed and adjusted as the project progresses throughout the various phases and even during construction as major changes take place. Greater consideration of work zone impacts as project decisions are made during scoping, alternatives analysis, and design, the greater the chance that solutions to traffic issues can be engineered into the design.
In traditional design/bid/build projects, the goal should be to complete most of the TMP by 60% design. The TMP development needs to be closely coordinated with key stakeholders throughout all stages of design. During construction the TMP manager needs to work closely with the contractor and affected stakeholders as major updates/changes can result due to post design changes.
For design-build projects, the TMP should be developed within 30-60 days of notice-to-proceed (NTP) and should lay out the procedures and process to be followed in the future design phases.
Interactions: None
Notes: None

## Slide 5: Internal Project Coordination
Preliminary Engineering
  Consider TTC and impacts in sizing structure widths
  Identify right-of-way and environmental impacts issues
Notes: Key Message: Talk about Internal Project Coordination
Background Information:
The TMP is a living document that needs to be developed and adjusted as the project progresses throughout the various phases and even during construction as major changes take place. Greater consideration of work zone impacts as project decisions are made during scoping, alternatives analysis, and design, the greater the chance that solutions to traffic issues can be engineered into the design.
In traditional design/bid/build projects, the goal should be to complete most of the TMP by 60% design. The TMP development needs to be closely coordinated with key stakeholders throughout all stages of design. During construction the TMP manager needs to work closely with the contractor and affected stakeholders as major updates/changes can result due to post design changes.
For design-build projects, the TMP should be developed within 30-60 days of notice-to-proceed (NTP) and should lay out the procedures and process to be followed in the future design phases.
Interactions: None
Notes: None

## Slide 6: Internal Project Coordination (cont.)
Design
  Develop phasing and staging plans in consultation with the key stakeholders
Construction
  Maintain close coordination with affected stakeholders as TMP is implemented
Notes: Key Message: Talk about Internal Project Coordination
Background Information:
The TMP is a living document that needs to be developed and adjusted as the project progresses throughout the various phases and even during construction as major changes take place. Greater consideration of work zone impacts as project decisions are made during scoping, alternatives analysis, and design, the greater the chance that solutions to traffic issues can be engineered into the design.
In traditional design/bid/build projects, the goal should be to complete most of the TMP by 60% design. The TMP development needs to be closely coordinated with key stakeholders throughout all stages of design. During construction the TMP manager needs to work closely with the contractor and affected stakeholders as major updates/changes can result due to post design changes.
For design-build projects, the TMP should be developed within 30-60 days of notice-to-proceed (NTP) and should lay out the procedures and process to be followed in the future design phases.
Interactions: None
Notes: None

## Slide 7: Coordinating Multiple Projects In The Same Corridor Or Region Enables Agencies To:
Effectively manage overall work zone impacts
Effectively use resources
Avoid conflicts in roles and responsibilities
Avoid additional costs
Avoid conflicts in TTC plans and other future strategies
Notes: Key Message: Coordinating multiple projects has a variety of benefits – and reduces headaches!
Background Information:
Coordination among owners of different road projects that can affect each other is crucial to achieving the objectives of any TMP. Poor coordination can result in significant traffic delays, conflicting messages leading to unsafe driving conditions, and a public relations "nightmare" – things that can be avoided with good, proactive coordination.
So it is important to consider the impacts of other concurrent construction projects in the area. The TMP process can help foster this coordination by bringing common stakeholders together. Project schedules can be coordinated and public outreach efforts and traffic management efforts can sometimes be shared across projects.
In some cases, agencies have developed a regional TMP to help coordinate efforts across all the projects in an area or on a corridor. Oregon DOT's corridor-level TMP approach ensures that all the projects and their individual project TMPs within the corridor are integrated, resulting in less conflict and more efficient use of resources.
Coordination can help to more effectively manage the available transportation network capacity.
Interactions: Introduce Oregon’s example and discuss what example this state may have or past projects. Oregon Department of Transportation (ODOT) developed a series of corridor-level TMPs under its bridge program, providing an integrated strategy for delivering all required bridge repairs and replacements within a specific corridor.
Would this reduce work zones in future years?
Notes: None

## Slide 8: Interagency Coordination
Critical where project impacts cross jurisdictional lines
Key Issues:
  Identify agency personnel
  Define roles and responsibilities
  Have periodic meetings
  Share information
Notes: Key Message: Be aware of other agency stakeholders to include in coordination efforts
Background Information:
Interagency coordination depends on the project size, area, location, and impacts. Often a significant project that is within 25-50 miles of a State border may affect the adjacent State. In large urban areas, where towns are right next to each other, projects at the local level and permit projects such as utility work in particular require interagency coordination. Honest and open communication is the key to soliciting interagency support.
For example, Arizona DOT's Communication Division has frequent management meetings with all agencies involved in nearby projects.
Interactions: None
Notes: None

## Slide 9: Interagency Coordination
Utilities
Transit
Business/property owners
Emergency services
Public facilities
Image: FHWA
Notes: Key Message: There are different types of stakeholders to consider including in coordination activities
Background Information:
Coordination with other stakeholders can also be critical at various stages of projects. Other stakeholders may include utility companies, transit providers, businesses, emergency services, and large public facilities such as schools and sports stadiums.
Interactions: None
Notes: None

## Slide 10: Defining Roles and Responsibilities
Helps with coordination:
  Project related
  Agency wide
Contact information is documented:
  Key project personnel
  Utilities
  Essential services
Stakeholders are aware of their roles and responsibilities
Notes: Key Message: discuss roles and responsibilities
Background Information:
Defining roles and responsibilities during TMP development is key to successful project coordination. Roles and responsibilities are defined Agency wide and on a project-by-project basis.
Documenting the contact information and roles and responsibilities in the TMP helps ensure that the stakeholders are aware of their roles and responsibilities. This also helps the TMP Manager or any other TMP-related personnel to easily access the contact information, as needed. This information will also be very helpful in bringing any key project replacement personnel up to date.
In cases where the roles and responsibilities are not well defined and/or all contact information is not available at the beginning stages of the project, the information can be filled in as the project progresses.
Interactions: You can document a role, but making sure the utilities can perform (relocate) on your schedule is another thing.
Notes: None

## Slide 11: Distribution of Roles and Responsibilities
TMP Development
  Agency or contractor personnel who have primary responsibility for developing TMP and overall coordination
Notes: Key Message: Responsibilities should be spread out among different individuals and stakeholders
Background Information:
The general roles and responsibilities related to TMPs can be thought of in three categories:
  Development,
  Review and approval, and
  Implementation.
The development of a TMP involves steps such as
  Consulting with stakeholders,
  Assessing potential work zone impacts, and
  Identifying strategies to help manage the impacts.
TMP development may use a team approach, particularly for larger projects.
All TMPs must be approved before being implemented.
DOTs have to determine where these responsibilities should be assigned based on job classification. In some cases, the same person can be used on multiple roles, although this should be minimized to avoid a conflict of interest.
TMP implementation requires trained, responsible personnel with sufficient knowledge and authority to implement the various elements of the TMP.
Both the agency and the contractor are required to designate a "responsible person" for this purpose.
Interactions: None
Notes: None

## Slide 12: Distribution of Roles and Responsibilities (cont.)
TMP Review and Approval
  Agency individual(s) who give final approval to TMP
TMP Implementation
  Agency and contractor personnel with primary responsibility to implement the TMP (responsible persons)
Notes: Key Message: Responsibilities should be spread out among different individuals and stakeholders
Background Information:
The general roles and responsibilities related to TMPs can be thought of in three categories:
  Development,
  Review and approval, and
  Implementation.
The development of a TMP involves steps such as
  Consulting with stakeholders,
  Assessing potential work zone impacts, and
  Identifying strategies to help manage the impacts.
TMP development may use a team approach, particularly for larger projects.
All TMPs must be approved before being implemented.
DOTs have to determine where these responsibilities should be assigned based on job classification. In some cases, the same person can be used on multiple roles, although this should be minimized to avoid a conflict of interest.
TMP implementation requires trained, responsible personnel with sufficient knowledge and authority to implement the various elements of the TMP.
Both the agency and the contractor are required to designate a "responsible person" for this purpose.
Interactions: None
Notes: None

## Slide 13: Roles and Responsibilities- Examples
Public Information
  Individual responsible for real-time public awareness of work zone issues, as the project advances
Emergency Services Contacts
  Stakeholders who need to be kept informed because they provide emergency or critical services
Notes: Key Message: Continue discussing roles and responsibilities
Background Information:
The list of stakeholders affected by a road project can be extensive.
Stakeholders may include those who perform public outreach, provide emergency services, and enforce laws, to name a few. Many times key persons are left out.
Often engineers think only within their own jurisdictions, while the project impacts can extend to other agencies, jurisdictions, and even other States.
The key stakeholder roles need to be clearly defined and contact information made available for use at a moment's notice
Interactions: None
Notes: None

## Slide 14: Agencies include:
Local – Police, Fire/EMS, Utilities, Hospitals, Schools
State – State Highway Patrol, Neighboring State DOTs
Federal – Department of Homeland Security
Notes: Key Message: Continue discussing roles and responsibilities
Background Information:
The list of stakeholders affected by a road project can be extensive.
Stakeholders may include those who perform public outreach, provide emergency services, and enforce laws, to name a few. Many times key persons are left out.
Often engineers think only within their own jurisdictions, while the project impacts can extend to other agencies, jurisdictions, and even other States.
The key stakeholder roles need to be clearly defined and contact information made available for use at a moment's notice
Interactions: None
Notes: None

## Slide 15: TMP Teams
Dependent on project:
  Size
  Location
  Area
  Extent of impacts
Benefits:
  Effective coordination and work zone management
  Well defined roles and responsibilities
Image: FHWA
Notes: Key Message: Discuss TMP Teams
Background Information:
Forming a TMP team to help with TMP development, coordination, review, and implementation can be helpful. Several States use TMP teams, primarily on significant projects.
A well-balanced team includes a range of appropriate stakeholders. Regular team meetings including the project designer, resident engineer, law enforcement officials, contractor, community representatives, and other stakeholders on major projects can help ensure that work zone management will be effective. A preliminary meeting of this type during the early stage of TMP development helps to identify potential work zone issues early in the process and to clearly define roles and responsibilities.
The sample table shown here can be useful for documenting the contact information and roles and responsibilities of TMP team members. The table can be modified as the TMP Progresses,
Interactions: None
Notes: None

## Slide 16: Exercise- Project Coordination
A transportation agency is planning several road projects
These projects include significant infrastructure improvements in close proximity (within 1 square mile) to each other
Notes: Key Message: provide exercise background information
Background Information:
The main corridor is a 6-lane arterial with an ADT of 65,000 vehicles; approximately 60% is commuter traffic.
Interactions: None
Notes: None

## Slide 17: Exercise- Project Coordination
The projects were designed at different times, as noted below, but lack of funding delayed construction
The DOT now has programmed funding to undertake all projects in fall 2021
The main corridor is a 6-lane arterial with an ADT of 65,000 vehicles; approximately 60% is commuter traffic
Notes: Key Message: Provide background information on exercise
Background Information:
A transportation agency is planning several road projects.
These projects include significant infrastructure improvements in close proximity (within 1 square mile) to each other.
The projects were designed at different times, as noted below, but lack of funding delayed construction. The DOT now has programmed funding to undertake all projects in fall 2021.
The main corridor is a 6-lane arterial with an ADT of 65,000 vehicles; approximately 60% is commuter traffic.
Interactions: None
Notes: ADA = average daily traffic

## Slide 18: Projects Include (design dates in parenthesis)
(2018): Resurface/Rehabilitate Brentwood Road
(2018): Replace Bridge over New York Avenue
(2016): Reconstruct the New York Avenue including bridge (C1)
(2016): Traffic Safety Improvement Project at intersection
(2014): Reconstruction of 1st Street
Notes: Key Message: provide background information on exercise
Background Information:
The projects in the vicinity include(design dates in parenthesis):
Project A (2018): Resurface/Rehabilitate Brentwood Road
Project B(2018): Replace Bridge over New York Avenue
Project C(2016): Reconstruct the New York Avenue including bridge (C1)
Project D(2016): Traffic Safety Improvement Project at intersection
Project E (2014): Reconstruction of 1st Street
Interactions: None
Notes: None

## Slide 19: Exercise- Project Coordination
As the Project Engineer for one of five construction projects, identify some key issues that could arise if all projects start together, as planned, for Fall 2021?
What are some possible ways to handle coordination?
Notes: Key Message: Review exercise questions
Background Information:
1. As the Project Engineer for one of five construction projects, identify some key issues that could arise if all projects start together, as planned, for Fall 2021? Examples of conflicts include: Overlap of construction limits, Contradictory temporary signing and pavement marking plans, Contradictory lane shifts, closures, and sidewalks, and Contradictory work zone information provided to public. Project coordination is required to ensure that all MOT strategies, including temporary lane closures and various traffic switches are coordinated to minimize road user confusion and impacts. Because of the close proximity of the projects C, D, and E to each other, it is crucial to have lane closures between projects well coordinated and consistent to avoid driver confusion and potential unsafe situations.
2. What are some possible ways to handle coordination? Coordination within and across agencies and other stakeholders of all the projects is crucial for the successful development and implementation of a TMP. Some possible ways to achieve this coordination are: A joint stakeholder meeting to coordinate development of individual project TMPs. An impact assessment of the combined impacts of the projects on mobility and safety, using updated traffic data since several of these projects were designed years earlier. Development of an area-wide TMP including all the projects (A through E) and project stakeholders. Clearly defining roles and responsibilities. A working meeting among all project engineers prior to construction initiation. Regular (e.g., weekly) project meetings to discuss upcoming lane closures, traffic shifts, etc. Central public relations personnel for all projects to ensure consistent public message. Quarterly stakeholder meetings with emergency services, utilities, transit, etc., to keep all abreast of upcoming events.
Interactions: None
Notes: None

## Slide 20: Module Recap
Name some of the stakeholders of highway projects?
Name some interagency coordination issues
Notes: Key Message: Review and discuss impact assessments
Background Information: Review questions
Interactions: None.
Notes: None.

## Slide 21: Questions
Notes: Key Message: Questions
Est. Presentation Time: Less than 1 minute(s)
Explanation of Cues/Builds: None
Suggested Comments: Let’s take your questions.
Suggested Questions: Any questions before we move to the next module?
Additional Information: None
Possible Problems: If no questions, you may want to ask your own.