## Slide 1: 7. Full Road Closure Case Study
Work Zone Strategies
https://patch.com/pennsylvania/northwhitehall/coplay-creek-road-closed-for-repairs_345b7cce
Notes: Key Message: Module Opening
Est. Presentation Time: As needed
Explanation of Cues/Builds: None
Suggested Comments: Let’s move to the next module. In this module {name}, we will.. {next slide}
Suggested Questions: None
Possible Problems: None

## Slide 2: Module Objectives
Examine an example of a full road closure in Portland, OR
Discuss the project’s:
  Background
  Planning
  Operations
  Benefits
  Lessons learned
Notes: Key Message: State the module objectives
Est. Presentation Time: Less than 1 minute(s)
Explanation of Cues/Builds: None
Suggested Comments: These are the objectives of this module. We will look at a full road closure case study in Portland, OR. This case study is included in this course to illustrate the considerations and benefits of applying some of the strategies we have learned to a major project. We hope that you learn some of the considerations that went into this particular project with the hope that you can apply similar considerations to your projects. In a way, this case study brings together the concepts we have learned in this course.
Suggested Questions: None
Additional Information: None
Possible Problems: None

## Slide 3: Case Study Introduction
I-84 Banfield Freeway in Portland, OR
Oregon Department of Transportation (ODOT)
This project illustrates a successful application of the full closure approach
Notes: Key Message: Case study introduction
Est. Presentation Time: Less than 1 minute(s)
Explanation of Cues/Builds: None
Suggested Comments: This case study describes the planning, implementation, benefits, and lessons learned by the Oregon Department
of Transportation (ODOT) during an overlay project on Interstate 84 (I-84) in Portland, Oregon. This case study illustrates a successful application of the full closure approach. It is intended to provide transportation agency personnel and elected officials with a better understanding of the considerations necessary to implement full road closure on a project, and the benefits that can be obtained. ODOT started a project in June of 2002 that included paving, striping, barrier replacement, and inlet and manhole adjustments. The project covered approximately five miles on I-84 in Portland between Interstate 5 (I-5) and Interstate 205 (I-205). The contract specifications originally called for traditional maintenance of traffic during part width construction. However after the project was let, ODOT decided to have the paving portion of the project done during two weekend full closures to expedite the project.
Suggested Questions: None
Additional Information: None
Possible Problems: None

## Slide 4: Source
FHWA report
Available online
Image: FHWA
Notes: Key Message: Report availability
Est. Presentation Time: Less than 1 minute(s)
Explanation of Cues/Builds: None
Suggested Comments: The information presented in this module was obtained from this FHWA report, available online.
Suggested Questions: None
Additional Information: http://ops.fhwa.dot.gov/wz/docs/Portland_v3/full_closure_portlan.pdf
Possible Problems: None

## Slide 5: Project Background
I-84, a major commuter route in downtown Portland
PROBLEM: Serious rutting problems
  Hydroplaning hazard
SOLUTION: Fill the ruts and add a 2-inch asphalt overlay
Notes: Key Message: Define project
Est. Presentation Time: 1-2 minute(s)
Explanation of Cues/Builds: None
Suggested Comments: I-84, also known as the Banfield Freeway, was originally scheduled for rehabilitation during the summer of 2005.
In early 2002, ODOT decided to move the project up to the 2002 construction season to eliminate a serious rutting problem, and to take advantage of available funding. I-84, which serves as an interstate freight route, a major commuter route to downtown Portland, and connects into I-5, was badly rutted in all lanes due to age, heavy vehicle use, and studded tires. The ruts contributed to a hydroplaning hazard. The goal of the project was to improve the safety of the Interstate by filling the ruts and by adding a 2-inch asphalt overlay to the original concrete roadway.
Suggested Questions: None
Additional Information: None
Possible Problems: None

## Slide 6: Project Location
http://www.i5portland.com/images/interstate_84_portland_map.gif

## Slide 7: Project Background
Project included:
  Asphalt paving
  Durable striping
  Replacement of 3-miles of 36-in median barrier
  Adjustments to more than 250 inlets and embedded manholes
Notes: Key Message: Define project
Est. Presentation Time: Less than 1 minute(s)
Explanation of Cues/Builds: None
Suggested Comments: Overall, the project included asphalt paving, durable striping, replacement of three miles of 36-inch median barrier, and adjustments to more than 250 inlets and manholes imbedded in the roadway.
Suggested Questions: None
Additional Information: None
Possible Problems: None

## Slide 8
Image: Mapquest
Image: Oregon DOT
Notes: Key Message: Illustrate project location
Est. Presentation Time: Less than 1 minute(s)
Explanation of Cues/Builds: None
Suggested Comments: This is where the project was located.
Suggested Questions: None
Additional Information: Left figure: cones show location of closure, dots show alternate routes. Picture on right is to better illustrate the location.
Possible Problems: None

## Slide 9: I-84
Busiest Portland freeway
146K to 180K ADT
ODOT determined to keep it open during weekday daytime hours
Night work was required
Accelerated schedule was needed so paving & striping could be completed before rainy season
Image: Oregon DOT
Notes: Key Message: I-84 background
Est. Presentation Time: Less than 1 minute(s)
Explanation of Cues/Builds: None
Suggested Comments: Since this section of I-84 is the busiest section of freeway in Oregon, with average daily traffic volumes from
146,000 to 180,000 vehicles, ODOT determined that all traffic lanes needed to remain open during weekday daytime hours. Consequently, night work was required, and ODOT’s Community Affairs staff had to obtain a noise permit for nighttime construction from the City of Portland Noise Review Board. In early June, ODOT’s construction engineers decided to accelerate the project with full closure, so that the paving as well as striping could be completed before the fall and winter rainy seasons.
Suggested Questions: None
Additional Information: None
Possible Problems: None

## Slide 10: I-84
Image: Oregon DOT
Notes: Key Message: I-84 background
Est. Presentation Time: Less than 1 minute(s)
Explanation of Cues/Builds: None
Suggested Comments: This is a photo of I-84.
Suggested Questions: None
Additional Information: None
Possible Problems: None

## Slide 11: The Plan
Directional closures for two weekends in August
  One direction each weekend
  As opposed to 32 nights as originally scheduled!
Notes: Key Message: Describe the plan
Est. Presentation Time: Less than 1 minute(s)
Explanation of Cues/Builds: None
Suggested Comments: The plan would involve directional closures for two weekends in August—one direction each weekend— as opposed to the 32 nights originally specified in project plans. Since the full closure would require some night work, a noise permit was still necessary. The permitting process normally takes from six months to one year, but the Community Affairs and Public Affairs staff acted quickly to raise awareness about the project and were able to obtain the permit in one month.
Suggested Questions: None
Additional Information: None
Possible Problems: None

## Slide 12: Project Characteristics
$5 million construction cost
180,000 ADT
  7% commercial vehicles
5.5 miles of pavement rehab
6-lane freeway (33 lane miles)
Full closure dates:
  August 2-5, 2002
  August 9-12, 2002
Notes: Key Message: Project characteristics
Est. Presentation Time: Less than 1 minute(s)
Explanation of Cues/Builds: None
Suggested Comments: Self explanatory
Suggested Questions: None
Additional Information: None
Possible Problems: None

## Slide 13: Contract Modification
Originally conventional
Modified at a reduced price, resulting in a credit of $101,000:
  More efficiency
  Fewer traffic control devices
Notes: Key Message: Contract modification
Est. Presentation Time: Less than 1 minute(s)
Explanation of Cues/Builds: None
Suggested Comments: Because the contract specifications originally called for traditional maintenance of traffic during part width
construction and the project had already been let, ODOT needed to modify the contract for the full closure. Since the use of full closure increased contractor efficiency and required fewer traffic control devices, ODOT was able to renegotiate the original contract at a reduced price. A change order was negotiated with the contractor, resulting in a credit back to the project of $101,000.
Suggested Questions: None
Additional Information: None
Possible Problems: None

## Slide 14: Why Use Full Closure?
Avoid hydroplaning hazard
Avoid Fall and Winter rains
Increase safety of both motorists and workers
Image: ATSSA
Notes: Key Message: Why full closure?
Est. Presentation Time: Less than 1 minute(s)
Explanation of Cues/Builds: None
Suggested Comments: The ODOT construction engineers decided to use full closure to: 1. Avoid a hydroplaning hazard to motorists traveling
on the Interstate. Using full closure expedited the I-84 project and made it possible to complete the repaving and striping before the fall and winter rains. 2. Increase the safety of both workers and motorists by eliminating the worker–traffic interaction.
Suggested Questions: None
Additional Information: None
Possible Problems: None

## Slide 15: Planning
Most important component
Involves:
  Developing TMP
  Informing all stakeholders
  Identifying alternate routes/modes
Image: FHWA
Notes: Key Message: Planning
Est. Presentation Time: Less than 1 minute(s)
Explanation of Cues/Builds: None
Suggested Comments: The most critical component to ensuring a successful full road closure is planning. This involves developing
an effective plan for traffic management, informing and collaborating with all potential stakeholders, and implementing an effective public outreach campaign. This campaign should keep the stakeholders informed and identify alternate routes or alternate modes of travel for the traveling public.
Suggested Questions: None
Additional Information: None
Possible Problems: None

## Slide 16: Alternate Routes
Because of ongoing work on nearby I-5, traffic modeling was used to evaluate overall traffic patterns
  EMME/2 model
Five major routes were identified and analyzed
Notes: Key Message: Alternate routes
Est. Presentation Time: 2 minute(s)
Explanation of Cues/Builds: None
Suggested Comments: Since I-84 is one of the busiest roads in Oregon and because of ongoing work nearby on I-5 close to the I-84 interchange, traffic modeling was used to ‘‘evaluate the overall traffic patterns and changes in traffic patterns with the directional closure on the I-84 freeway.”1 This evaluation determined the impact on all major routes likely to carry the traffic diverted from I-84. ODOT also needed to identify mitigation measures that could be implemented to maintain reasonable traffic flow in the area. Traffic conditions were analyzed in July prior to beginning
the project. ODOT projected ‘‘before,” ‘‘during,” and ‘‘net change” in weekend peak period traffic on all routes in the corridor. ODOT used the EMME/2
traffic assignment model to assess traffic conditions, with peak-period traffic volumes as the base condition. An assignment showing traffic volumes in the work area for both eastbound and westbound traffic was prepared. A ‘‘difference” assignment was developed to represent the net change in traffic on all adjacent routes.
Suggested Questions: None
Additional Information: EMME is a bilingual acronym for Équilibre Multimodal, Multimodal Equilibrium. EMME/2 was specifically designed for multimodal networks. With EMME/2, all the relevant means of transportation can be modeled in an integrated way. http://www.inro.ca/products/e2fea.pdf.
Possible Problems: None

## Slide 17: Alternate Routes
EMME estimated that alternate route traffic would increase by 500-700 vph
  Comparable to existing peak-period weekday traffic
Signals of alternate routes we set to weekday peak-period settings during the closures
Notes: Key Message: Alternate route discussion
Est. Presentation Time: 2 minute(s)
Explanation of Cues/Builds: None
Suggested Comments: Traffic data showed that the volumes on Saturday and Sunday were approximately 80 percent and 75 percent of a normal weekday, respectively. Five major routes were identified as receiving the majority of the traffic diversion in both directions during a full closure. The EMME/2 model and existing traffic counts estimated that traffic resulting from the I-84 closure could increase as much as 500 to 700 vehicles per hour (vph) on each of these primary routes receiving the diverted traffic.3 Other routes were expected to increase between 100 and 500 vph. These increased levels were comparable to existing weekday peak-period traffic. To accommodate the increased demand, the signals on the alternate
routes would be set to weekday peak-period settings during the closures. ODOT also developed several scenarios for the I-84 closure that included impacts on and resulting from possible I-5 closures for roadwork
Suggested Questions: None
Additional Information: None
Possible Problems: None

## Slide 18: I-84 Closure: Impact on I-5
Analysis showed that any simultaneous closures should only be directional
  I-84 EB could be closed during I-5 SB closure
  I-84 WB closure could be closed during I-5 NB closure
Notes: Key Message: Alternate route discussion
Est. Presentation Time: Less than 1 minute(s)
Explanation of Cues/Builds: None
Suggested Comments: . Initial analysis showed ODOT that to maintain adequate traffic flow, any simultaneous closures on the two roads should only be directional closures. Based on subsequent analysis, ODOT concluded that eastbound I-84
could be closed during a southbound I-5 closure, and a westbound I-84 closure could occur with an I-5 northbound closure, with manageable impacts to area traffic.
Suggested Questions: None
Additional Information: None
Possible Problems: None

## Slide 19: Interagency Coordination
ODOT coordinated with:
  City of Portland
  Port of Portland
  Tri-Met (mass transit)
Images: City of Portland
Notes: Key Message: Interagency coordination
Est. Presentation Time: Less than 1 minute(s)
Explanation of Cues/Builds: None
Suggested Comments: In planning and during the full closures, ODOT needed to coordinate with other agencies that would be affected
by the closures. Three of the more closely associated agencies involved with ODOT in the planning stage were the City of Portland, Port of Portland, and Tri-Met.
Suggested Questions: None
Additional Information: None
Possible Problems: None

## Slide 20: All Three..
Issued media releases
Had joint media conferences
Added special messages regarding the closures to their websites
DOT
Press
Release
Notes: Key Message: Interagency coordination
Est. Presentation Time: Less than 1 minute(s)
Explanation of Cues/Builds: None
Suggested Comments: ODOT’s Public Affairs staff issued several media releases and held a joint media conference with Tri-Met, the City of Portland, and the Port of Portland. All three jurisdictional partners added special messages regarding the weekend closures to their websites.
Suggested Questions: None
Additional Information: None
Possible Problems: None

## Slide 21: City of Portland
Made adjustments to signal timing on alternate routes
Image: ATSSA
Notes: Key Message: Interagency coordination
Est. Presentation Time: Less than 1 minute(s)
Explanation of Cues/Builds: None
Suggested Comments: The ODOT traffic engineers coordinated with the City of Portland engineers to make the signal timing adjustments to the alternate routes.
Suggested Questions: None
Additional Information: None
Possible Problems: None

## Slide 22: Port of Portland
Owns & maintains Portland International Airport (PIA)
I-84 is its primary route
Frequent communication efforts were made
Notes: Key Message: Interagency coordination
Est. Presentation Time: Less than 1 minute(s)
Explanation of Cues/Builds: None
Suggested Comments: The primary route to the Portland International Airport from downtown is on I-84. Therefore, early and frequent communication efforts were crucial between ODOT and the Port of Portland, which owns and maintains the Airport.
Suggested Questions: None
Additional Information: None
Possible Problems: None

## Slide 23: Tri-Met
Light rail system (MAX) that parallels I-84 and serves PIA
Communication reduced impacts on alternate routes
Images: City of Portland
Notes: Key Message: Interagency coordination
Est. Presentation Time: Less than 1 minute(s)
Explanation of Cues/Builds: None
Suggested Comments: The Tri-Met mass transit agency operates a light rail system (MAX) that parallels I-84 and serves the Portland International Airport, so communication between these agencies was helpful to reduce traffic impacts on the alternative routes.
Suggested Questions: None
Additional Information: None
Possible Problems: None

## Slide 24: Other Stakeholders
EMS
Police
Hospitals
Schools
Residents
Businesses
Trucking firms
Cab companies
Tourism bureau
Travel agents
Special event planners
Contractor working on I-5
Notes: Key Message: Interagency coordination
Est. Presentation Time: Less than 1 minute(s)
Explanation of Cues/Builds: None
Suggested Comments: Self explanatory
Suggested Questions: None
Additional Information: None
Possible Problems: None

## Slide 25: Public Information and Outreach
A well-organized PR campaign was needed
Started in March
Primary activities in July & August
Informed all stakeholders
GOALS:
  Divert 160K drivers per weekend to alt. routes & mass transit
  Gain project acceptance
Notes: Key Message: Public outreach
Est. Presentation Time: Less than 1 minute(s)
Explanation of Cues/Builds: None
Suggested Comments: For a full closure project to be successful, a well organized public relations campaign is needed. Planning activities began in February, and some public outreach for the overall project began in March before the decision to use full closure. The primary activities of the public awareness campaign for the full closure project occurred in July and August. Through the campaign, ODOT worked to identify, involve, and inform all potential stakeholders. The goal of the campaign was to successfully divert approximately 160,000 drivers per weekend to alternate routes or to mass transit.
Suggested Questions: None
Additional Information: None
Possible Problems: None

## Slide 26: Outreach Means
Personal telephone calls and radio ads
Direct mailings to:
  Homes & businesses in corridor
  Taxi companies
  Tourism bureau
  Travel agents
Freeway CMS
Notes: Key Message: Public outreach means
Est. Presentation Time: Less than 1 minute(s)
Explanation of Cues/Builds: None
Suggested Comments: The strategy was to reach key stakeholders directly. In the months prior to the weekend closures, ODOT reached stakeholders through a number of means, including these
Suggested Questions: None
Additional Information: VMS = variable message sign
Possible Problems: None

## Slide 27: Outreach Means
A project website
A telephone info line
Media alerts/events
Information kiosk at a large regional mall
Countertop informational displays at local businesses
Notes: Key Message: Public outreach means
Est. Presentation Time: Less than 1 minute(s)
Explanation of Cues/Builds: None
Suggested Comments: The strategy was to reach key stakeholders directly. In the months prior to the weekend closures, ODOT reached stakeholders through a number of means, including these
Suggested Questions: None
Additional Information: None
Possible Problems: None

## Slide 28: About the Outreach Campaign
Gained acceptance of the project from residential neighbors despite night work
Cost was less than $50K (less than 1% of the construction cost)
Notes: Key Message: Public outreach campaign
Est. Presentation Time: Less than 1 minute(s)
Explanation of Cues/Builds: None
Suggested Comments: Not only did the campaign get stakeholders involved, but it also gained acceptance of the project from residential neighbors despite nighttime construction work. By making the residents in the neighborhoods aware of the project, acceptance of the construction was increased. The overall cost of the campaign was less than $50,000, or less than one percent of the total construction cost.
Suggested Questions: None
Additional Information: None
Possible Problems: None

## Slide 29: Operations During the Weekend Closures: Traffic…
Indeed resembled typical weekday volumes
Moved better than expected in alternate routes
Flowed well despite simultaneous closured on I-5
160K vehicles were successfully diverted
Notes: Key Message: Operations
Est. Presentation Time: 1-2 minute(s)
Explanation of Cues/Builds: None
Suggested Comments: The assumption that traffic during the full weekend closures would resemble typical weekday volumes proved
correct. Given appropriate signal retimings on alternate routes, traffic moved better than expected. During the first weekend closure, the matter was complicated by a simultaneous closure of the Portland ‘‘Belt Loop’’ that connects with I-5. The coordination of both projects and the extensive outreach program allowed traffic to flow despite the multiple closures. The second weekend closure was complicated by the annual Providence Bridge Pedal event because the event closed some of the alternate routes planned for the full closure. Again, the coordination with event staff proved invaluable; ODOT traffic personnel indicated that fewer traffic issues resulted than normally ensued during the Bridge Pedal event. ODOT estimated that 160,000 vehicles per weekend were successfully diverted, with minimal disruptions on alternate routes. Tri-Met indicated a small increase in MAX ridership during the weekend closures, and the Port of Portland did not hear of any problems for passengers finding their way to and from the airport.
Suggested Questions: None
Additional Information: None
Possible Problems: None

## Slide 30: Operations During the Weekend Closures
MAX reported small increase in ridership during the closures
Airport passengers did not report any problems finding their way to the airport
Image: ATSSA
Notes: Key Message: Operations
Est. Presentation Time: 1 minute(s)
Explanation of Cues/Builds: None
Suggested Comments: Tri-Met indicated a small increase in MAX ridership during the weekend closures, and the Port of Portland did not hear of any problems for passengers finding their way to and from the airport.
Suggested Questions: None
Additional Information: None
Possible Problems: None

## Slide 31: Operations
Closures took one hour to deploy
Incident management patrols were deployed
Image: FHWA
Notes: Key Message: Operations
Est. Presentation Time: 1 minute(s)
Explanation of Cues/Builds: None
Suggested Comments: The full closures took approximately one hour to deploy. The ODOT team had maintenance workers in trucks to help with incident management.
Suggested Questions: None
Additional Information: None
Possible Problems: None

## Slide 32: Operations
60-70 workers could work simultaneously
Two-asphalt plants w/backup plan
On-time completion
Image: FHWA
Notes: Key Message: Operations
Est. Presentation Time: 1 minute(s)
Explanation of Cues/Builds: None
Suggested Comments: When the full closures were in place, the contractor had 60 to 70 workers on the asphalt paving. Since the project involved such a big asphalt-paving job, the contractor used two asphalt plants and implemented a backup plan in case one of the asphalt plants broke down during the closures. This came in handy as one of the asphalt plants did break down during the second weekend closure. The contractor reacted to the problem quickly and transferred to the backup asphalt plant, enabling the project to be completed on time.
Suggested Questions: None
Additional Information: None
Possible Problems: None

## Slide 33: Benefits/Impacts of I-84 Full Road Closure
Benefit | Comment
Duration | Reduced 85%
Worker & traveler safety | Improved
Cost | Reduced $100K
Quality | Improved ride
Public sentiment | Positive
Notes: Key Message: Benefits
Est. Presentation Time: 1 minute(s)
Explanation of Cues/Builds: None
Suggested Comments: Self explanatory
Suggested Questions: None
Additional Information: None
Possible Problems: None

## Slide 34: Lessons Learned
Alternate Routes: Availability is critical
Adequate Lead-Time: Critical for project planning and coordination
Scope: Plan for closures PRIOR to letting the contract
Notes: Key Message: Lessons learned
Est. Presentation Time: 1 minute(s)
Explanation of Cues/Builds: None
Suggested Comments:
-Alternate Routes. The availability of alternative routes is critical to the success of a full closure project. Traffic was less congested than the traffic model predicted, possibly due to trip elimination or mode diversion.
-Adequate Lead-Time. Project personnel should allow adequate lead-time for project planning and coordination. With the contract having been approved on June 22, inadequate lead-time was an issue affecting project personnel. Although the rehabilitation was completed with no major issues, the project team related that stress resulted from not having adequate time to plan for full road closure. With more lead-time it would have been beneficial to include the barrier replacement, inlet and manhole work, and striping in the work done during the full closure. The project development team did not have enough lead-time to plan for every aspect of the project.
-Project Scope: Plan for the use of full closure prior to letting the contract. The project scope of work originally called for the maintenance of traffic during paving operations. Project cost would have been reduced considerably by the competitive bid process, had the contract specifications called for bids based on the use of full closure.
Suggested Questions: None
Additional Information: Treat as a summary
Possible Problems: None

## Slide 35: Lessons Learned
Contingency Plans: Must be developed
Traffic Control within the Work Zone: Consider establishing an agreement with contractor on construction vehicle speeds within the work zone
Notes: Key Message: Lessons learned
Est. Presentation Time: 1 minute(s)
Explanation of Cues/Builds: None
Suggested Comments:
-Contingency Planning: Develop contingency plans for a variety of events that could delay rehabilitation during a full closure. Contingency plans were important in making the full closure run smoothly. Two asphalt plants supplied material to the project site. During the second weekend closure (eastbound paving) one plant broke down. An alternate plant, which was part of a backup plan, was used to complete the project without delay. As with any project, needing to implement a contingency plan can create additional costs. For the I-84 project, the backup plant was farther away, so using the plant increased the cost of transporting materials. These costs were borne by the contractor. A contingency plan is particularly important for full closure projects since they generally have strict dates for reopening roads, and missing those deadlines may result in significant penalties to the contractor, negative public relations, and/or traffic problems.
-Traffic Control Within the Work Zone: Consider establishing an agreement with the contractor on construction vehicle speeds within the work zone. With the elimination of other vehicle traffic on the closed road, workers may tend to drive construction vehicles at high speeds. These unsafe speeds can pose a hazard to other personnel working on the closed roadway.
Suggested Questions: None
Additional Information: Treat as a summary
Possible Problems: None

## Slide 36: Summary
With adequate planning, public outreach, stakeholder involvement, and alternate routes, full road closures has the potential to accelerate projects, improve quality and safety, and reduce costs
Notes: Key Message: Summary
Est. Presentation Time: 1 minute(s)
Explanation of Cues/Builds: None
Suggested Comments: Use of the full closure method on I-84 was an innovative idea that was deemed to be a success. With the
availability of many alternate routes, signal timing changes on the alternate routes, a large-scale public outreach effort, and the communication between agencies, ODOT’s use of full closure on I-84 resulted in timely completion of the project with increased quality and reduced risk for workers and motorists. For transportation professionals who must rehabilitate roadways and reduce the impacts of work zones on workers and motorists, full road closure is one potential method that can achieve both goals. With adequate planning, public outreach, stakeholder involvement, and alternate routes, full road closure has the potential to simultaneously accelerate projects, improve quality and safety, and reduce costs.
Suggested Questions: None
Additional Information: Treat as a summary
Possible Problems: None

## Slide 37: Knowledge Check
Why do you think the full closure on I-84 was successful? Why?
Which strategies were used for:
  TTC Plan?
  PI&O?
  TO?
Notes: Key Message: Recap slide
Est. Presentation Time: 2-3 minutes
Explanation of Cues/Builds: None
Suggested Comments: Self explanatory. Try to gauge understanding by asking these questions and others.
Suggested Questions: Shown.
Additional Information: None
Possible Problems: None

## Slide 38: Questions
Notes: Key Message: Questions
Est. Presentation Time: Less than 1 minute(s)
Explanation of Cues/Builds: None
Suggested Comments: Let’s look at your questions.
Suggested Questions: Any questions before we move on?
Additional Information: None
Possible Problems: None