## Slide 1: -MODULE 5- Result Application
Work Zone Traffic Impact Analysis
Image: ATSSA
Notes: Key Message: Introduce module
Est. Presentation Time: Less than 1 minute(s)
Explanation of Cues/Builds: None
Suggested Comments: We will now discuss how to apply the results of the work zone analysis tools
Suggested Questions: None
Additional Information: None
Possible Problems: None

## Slide 2: Module Objectives
Discuss the application of work zone traffic impact analysis (and tools)
Discuss key questions the results may help us answer
Discuss how to use (apply) the results given by the models
Notes: Key Message: State the module objectives
Est. Presentation Time: Less than 1 minute(s)
Explanation of Cues/Builds: None
Suggested Comments: None
Suggested Questions: None
Additional Information:
Possible Problems: None

## Slide 3: Now that we have results, what can we do?
Revise the design/ construction strategy
Revise the staging approach for the project
Answer key questions
Notes: Key Message: Discuss result applications
Est. Presentation Time: Less than 1 minute(s)
Explanation of Cues/Builds: None
Suggested Comments: Based on the results of the analysis, the agency may choose to either revise the management strategies and/or the construction/staging approach for the project. This represents the iterative aspect of the work zone impacts assessment process. Decision making at this juncture is driven by the required level of performance for the work zone (as determined by the agency and/or design team, or as defined by applicable policies and standards). The answer to key questions such as costs, queue lengths and other performance measures is now known. These answers may lead to design revisions.
Suggested Questions: None
Additional Information: None
Possible Problems: None

## Slide 4: Results Help With Design Decisions
Reassess and confirm whether the project is a “Significant Project”
Develop recommendations for final construction approach and construction staging
Identify final design and contracting strategies – consider innovative design and contracting approaches
Notes: Key Message: Discuss result applications
Est. Presentation Time: Less than 1 minute(s)
Explanation of Cues/Builds: None
Suggested Comments: The results from transportation analytical can serve to improve decision-making as well as improve overall understanding of relationships between the many forces affecting work zone decision-making: mobility, financial, environmental and safety. Work zone analysis should never be used to make key decisions but instead developed as a trusted resource for understanding the potential mobility impacts and using this information to inform key decisions. The informative value of analysis used by decision-makes will be directly related to how well the analyst has considered both the context for analysis (decisions to be supported and relevant performance measures) and the context for validation (data and staff resources). The job of the work zone analyst extends beyond merely conducting an analysis and reporting results; but to provide decision-makers with a broader understanding that connects the findings of the analysis within the decision-making context. Placed in context, a well-summarized level of understanding can be provided to decision-makers and other staff working on the project, even if decision-makers do not have first-hand experience with the analytical approach. Perform a detailed project-level work zone impacts assessment progressively and comprehensively through the various design iterations.
• Reassess and confirm whether the project is a significant project
• Develop recommendations for final construction approach and construction staging.
• Identify final design and contracting strategies – consider innovative design and contracting
approaches.
Suggested Questions: None
Additional Information: None
Possible Problems: None

## Slide 5: Contracting Strategies
Traditional Design-bid-build process
Design-build
Contractor- developed TMP
Performance-based TMP
Notes: Key Message: Discuss result applications
Est. Presentation Time: Less than 1 minute(s)
Explanation of Cues/Builds: None
Suggested Comments: The contracting strategy may be chosen based on the results. Options available are:
Traditional Design-Bid-Build process. In this case, the final plans, TMP, PS&E and bid package are developed by the agency (or consultant as appropriate).
• Design-Build. This involves a stage-by-stage approach to designing and building the project, where design and construction take place in tandem. When construction is taking place on one phase, the subsequent phase is designed. This generally saves project time and money. This approach is more often adopted for major infrastructure reconstruction or rehabilitation projects and is performed by a team of engineering consultants and contractors.
• Contractor Developed TMP. In this case, the agency includes basic TMP requirements and recommendations in the bid package, rather than the agency developing the TMP itself. Contractors may then include appropriate TMPs in their bids.
• Performance Based TMP. In this case, work zone performance requirements are established by the agency. Contractors may then include TMPs that help meet those performance requirements in their bids.
Suggested Questions: None
Additional Information: None
Possible Problems: Some of this material is covered in the “Strategies” course. Participants that have gone through that course may find it repetitive. Treat as a review.

## Slide 6: Results Help With Design Decisions (cont.)
Develop final recommendations & plans for work zone management strategies
Estimate the final costs for the chosen work zone management strategies
Notes: Key Message: Discuss result applications
Est. Presentation Time: 1-2 minute(s)
Explanation of Cues/Builds: None
Suggested Comments: Perform a detailed project-level work zone impacts assessment progressively and comprehensively through the various design iterations.
• Develop final recommendations and plans for work zone management strategies.
• Estimate the final costs for the chosen work zone management strategies.
Suggested Questions: None
Additional Information:
Possible Problems: None

## Slide 7: Results Help With Design Decisions (cont.)
Identify performance requirements
Develop the TMP, appropriate PS&Es and other documents that are required to implement the TMP
Develop contracting documents
PS&Es
Notes: Key Message:
Est. Presentation Time: Less than 1 minute(s)
Explanation of Cues/Builds: None
Suggested Comments: Perform a detailed project-level work zone impacts assessment progressively and comprehensively through the various design iterations.
• Identify performance requirements for the work zone.
• Develop the TMP, appropriate PS&Es (Plans, Specifications and Estimates) and other documents that are required to implement
the TMP.
• Develop contracting documents.
Suggested Questions: None
Additional Information:
Possible Problems: None

## Slide 8: Who Does This?
The TMP may be developed by the agency itself – either in-house or by using a consultant
All TMPs that are developed by a non-agency entity must be approved by the agency
The agency may also have the TMP reviewed, stamped and approved by a licensed Professional Engineer
Notes: Key Message: Discuss typical responsibilities
Est. Presentation Time: Less than 1 minute(s)
Explanation of Cues/Builds: None
Suggested Comments: The TMP may be developed by the agency itself – either in-house or by using a consultant. Alternatively, the agency may choose to allow the contractor to develop a TMP prior to start of work, and/or use performance-based specifications. If the agency chooses to use a contractor developed TMP (instead of an agency developed TMP), appropriate specifications for the TMP are developed, rather than the TMP itself. In either case, TMP development will be governed by agency-developed recommendations and/or performance specifications. All TMPs that are developed by a non-agency entity (e.g., contractor, consultant) must to be approved by the agency. The agency may also have the TMP reviewed, stamped, and approved by a licensed Professional Engineer.
Suggested Questions: None
Additional Information: None
Possible Problems: None

## Slide 9: What are the Specifics?
Signage requirements
Taper lengths
Device spacing
Detour signs
Use of police
Nighttime decisions
Image: FHWA
Notes: Key Message: Discuss TCP content
Est. Presentation Time: Less than 1 minute(s)
Explanation of Cues/Builds: None
Suggested Comments: The results can then be used to develop a solid TCP as part of the TMP, that incorporates devices, techniques and procedures to improve the safety and mobility of the work zone. Some of these are listed here. For example, if queues will be formed and congestion is expected for a portion of the project, the designer may choose to reduce the devices spacing, to discourage drivers from making certain maneuvers. The results may also prompt the designer to seek police services, for example.
Suggested Questions: None
Additional Information:
Possible Problems: None

## Slide 10: What Additional Features Need To Be Incorporated?
Lighting and visibility needs
Presence of law enforcement
Advance warning (PCMS)
Etc.
Image: ATSSA
Notes: Key Message: Discuss TCP content
Est. Presentation Time: Less than 1 minute(s)
Explanation of Cues/Builds: None
Suggested Comments: The results can then be used to develop a solid TCP as part of the TMP, that incorporates devices, techniques and procedures to improve the safety and mobility of the work zone. Some of these are listed here.
Suggested Questions: None
Additional Information:
Possible Problems: None

## Slide 11: For example, for an ITS System..
Detector requirements
Information communication and dissemination requirements
Number of tow-trucks needed for incident response and management
Incident management policies
Others?
Image: FHWA
Notes: Key Message: Application of results
Est. Presentation Time: Less than 1 minute(s)
Explanation of Cues/Builds: None
Suggested Comments: The results can then be used to develop requirements and specifications for an ITS system, for example.
Suggested Questions: None
Additional Information:
Possible Problems: None

## Slide 12: Or for a Real Time WZ Traveler Info System..
Whether PCMS will be needed to provide in route information
Project web site
Project telephone hotline
E-mail alerts
Media contacts, etc.
Image: NJ Turnpike Authority
Notes: Key Message: Application of results
Est. Presentation Time: Less than 1 minute(s)
Explanation of Cues/Builds: None
Suggested Comments: The results can then be used to develop requirements and specifications for an WZ traveler information system, for example.
Suggested Questions: Which TMP component are we addressing here? PI.
Additional Information:
Possible Problems: None
Image Credit: https://www.njta.com/media/1762/njta-guideline-vms-systems-2017-03-20.pdf

## Slide 13: What Are The Expected WZ Impacts Of The Project?
Expected queue lengths and delays?
Expected crashes/crash rate?
Analysis/estimation of the WZ impacts?
How does the TMP mitigate these impacts?
Image: FHWA
Notes: Key Message: What Are The Expected WZ Impacts Of The Project?
Est. Presentation Time: Less than 1 minute(s)
Explanation of Cues/Builds: None
Suggested Comments: The results can help answer key questions, or sometimes clarify the
Suggested Questions: None
Additional Information:
Possible Problems: None

## Slide 14: What Are The Estimated Costs?
To implement the chosen strategies?
For the TMP components?
Notes: Key Message: Application of results
Est. Presentation Time: Less than 1 minute(s)
Explanation of Cues/Builds: None
Suggested Comments: The results can then be used to estimate costs perhaps for a benefit/cost analysis.
Suggested Questions: None
Additional Information:
Possible Problems: None

## Slide 15: Applying Results
Improve overall understanding of the work zone
Modeling should never be used to make key decisions but as a trusted resource, a tool
Work zone analysis extends beyond running the model and reporting results
Notes: Key Message: Application of results (summary)
Est. Presentation Time: Less than 1 minute(s)
Explanation of Cues/Builds: None
Suggested Comments: Modeling should never be used to make key decisions but as a trusted resource, a tool. Remember that these tools are just that, a tool to help you make key decisions. Other factors must also be considered. It is not a black box!
Suggested Questions: None
Additional Information: This is a summary slide.
Possible Problems: None

## Slide 16: Other Factors to Consider
Constructability
Public, management and political acceptance
Safety performance measures
Engineering judgment!
Others?
Image: FHWA
Notes: Key Message: Application of results (summary)
Est. Presentation Time: Less than 1 minute(s)
Explanation of Cues/Builds: None
Suggested Comments: These factors include cost, safety, constructability, public, management and political acceptance and most importantly: Engineering judgment!
Suggested Questions: None
Additional Information: This is a summary slide.
Possible Problems: None

## Slide 17: Work Zone Safety Performance Measures
Work Zone Safety Performance Measures Guidance Booklet
Image: FHWA
Notes: Key Message: Introduce WZ Safety Performance Measures Guidance Booklet
Est. Presentation Time: Less than 1 minute(s)
Explanation of Cues/Builds: None
Suggested Comments: The purpose of this guidance booklet is to introduce the concept of performance measures and performance data collection for work zone safety. Performance measures are sets of defined, outcome-based conditions or response times that are used to evaluate success. Performance measures focus on what to achieve, not how to achieve it. Measures come in all different shapes and sizes.
Suggested Questions: None
Additional Information: Available at atssa.com
Possible Problems: None
17

## Slide 18: Example of Safety Performance Measures
Performance Measures
Performance Goal – “Pass” |  |  |  |  |  | 
5 - Excellent | 4 - Good | 3 - Fair | 2 – Poor |  | 1 – Very Poor | 
Work zone crash rate 20% less than pre-construction crash rate | Work zone crash rate equal to pre-construction crash rate | Work zone crash rate 20% higher than pre-construction crash rate | Work zone crash rate 30% higher than pre-construction crash rate |  | Work zone crash rate more than 30% higher than pre-construction crash rate | 
Levels of Performance
Image: FHWA
Notes: Key Message: Provide an example of a multi-level performance measure for work zone safety
Est. Presentation Time: 1-2 minutes
Explanation of Cues/Builds: None
Suggested Comments: Using work zone crash rate as a measure of effectiveness, an example of a 5-level performance measure is shown. In this example, Level 4 (Good) is defined as the performance goal or the “passing” level. The full set of levels of performance here, including the designated goal, make up the performance measure. Another example of a multi-level performance measure is traffic level of service.
If you are using pass-fail performance measures then you would only have the performance goal, you would not have the additional levels of performance listed in the chart.
Suggested Questions: None
Additional Information:
This particular measure likely would apply to a long-term work zone; however, performance measures are not solely for long-term work zones. Even short-term temporary work zones can have major safety and traffic implications, and performance measures (such as maximum allowable queue length) can be generated and used to define acceptable performance.
The actual values for the various levels of performance need to be tailored to suit the locality and the specific project.
Possible Problems: None

## Slide 19: Examples of Safety Performance Measures
Pass/fail – Incident Rate (IR) for worker injuries is less than 4.0
Subjective – Drivers feel safe traveling through work zones
Surrogate/Congestion – No stopped queues in the work zone longer than ¼ mile
Policy – Respond to all customer complaints within 24 hours
State/Agency Level – No construction-related fatalities in work zones State-wide in the year
Notes: Key Message: Discuss examples of different types and levels of performance measures
Est. Presentation Time: 1-2 minutes
Explanation of Cues/Builds: None
Suggested Comments: An example of an objective, multi-level measures for a project was provided on the previous slide. These are examples of other types of performance goals. Some goals will result in quantitative results, while others may be more qualitative.
Surrogate and safety-related congestion measures can play an important role when the work zone is short in duration or when crash data may not be readily available. A number of congestion measures have a strong relation to safety. For example, the presence of stopped queues creates traffic shock-waves that can contribute to crashes when sight distance is limited.
The Incident Rate refers to the OSHA worker injury rate.
The subjective measure could be examined using driver intercept surveys or web surveys.
Suggested Questions: What are some other examples of safety-related performance goals that you can think of? Can you name another congestion-related goal that may affect safety?
Additional Information: None
Possible Problems: None

## Slide 20: Module Recap
Why are the result applications important?
What can we do with the results of the analysis tools?
Which key questions can the results help us answer?
How can we evaluate results?
Notes: Key Message: Recap module
Est. Presentation Time: 1 minute(s)
Explanation of Cues/Builds: None
Suggested Comments: None
Suggested Questions: None
Additional Information: None
Possible Problems: Avoid telling the audience the answers to these questions. Their purpose is to gauge understanding. You may add other questions.